## Data (hidden)
[9 empty] | 1 - 10% | 10 - 25% | 25 - 50% | 50 - 90% | 90 - 100%
[7 empty] | Impact (Severity) | VH | [8 empty] | 5 | 5 | 10 | 15 | 20 | 25
[8 empty] | H | [8 empty] | 4 | 4 | 8 | 12 | 16 | 20
[8 empty] | M | [8 empty] | 3 | 3 | 6 | 9 | 12 | 15
[8 empty] | L | [8 empty] | 2 | 2 | 4 | 6 | 8 | 10
[8 empty] | VL | [8 empty] | 1 | 1 | 2 | 3 | 4 | 5
[9 empty] | VL | L | M | H | VH |  |  |  |  | 1 | 2 | 3 | 4 | 5
Probability (Likelihood)
[29 empty] | Phase Gate WBS Level 2 List | [5 empty] | Phase Gate Details
[29 empty] | Gate.0_Needs.Confirmation.RR.ABP | Gate.1_Business.Case | Gate.2_Delivery.Strategy.Tender.Preparation | Gate.3_Investment.Decision.Procurement | Gate.4_Readiness.For.Service.Construction | Gate.5_Benefits.Realization.Operation | Gate0_Needs.Confirmation.RR.ABP | Gate1_Business.Case | Gate2_Delivery.Strategy.Tender.Preparation | Gate3_Investment.Decision.Procurement | Gate4_Readiness.For.Service.Construction | Gate5_ Benefits.Realization.Operation
[29 empty] | Feasibility Studies | Engineering Cost | Contract Development | BAC Recommendation | Backfill | Benefits Audit | AMP Projects and Systems Sizing | Business Case Documentation | Industrial Day | Bid and Award Process | Acceptance | Benefits Realization Review
[29 empty] | Geotech | Geotech | Contractor Engagement | Evaluation of Offers | Basins & Ponds | Performance Metrics | Concept Study | Project Cost Approval | Invitation of Bidders | Submission of Bids | Commissioning
[29 empty] | HOA Engagement | HOA Engagement | Cost Estimate Final | Instruction to Bidders | Below ground services | Review Declared Benefits | Master Planning | Scope Time Cost Firm up | Market Sounding | Tender Commercial Review | Construction
Probability |  | Impact/Prob |  | Risk Index | Overall Status | Concatenated | Impact | Probability | Risk Index | [5 empty] | Risk Strategy (Mitigation) | [13 empty] | LGU Engagement | Land Conversion | Design Criteria | Opening of Bids | Civil and Site Development Works |  | New Project Discovery | Feasibiity Studies | Preparation of Tender | Tender Due Diligence | Equipment & Systems Installation
Very Low | 1 | Very Low | 1 | High | RED | Very Low Very Low | Very Low | Very Low | Low |  |  | High | Very Low | Medium | Risk Avoidance | Stop, or walk away from, the project. | [12 empty] | Needs Definition | LGU Engagement | Development of Project WBS | Project Bidding | Concrete Pour |  | Opportunity Exploitation |  | Contract Drafting | Tender Negotiation | Mobilization
Low | 2 | Low | 2 | Medium | YELLOW | Very Low Low | Very Low | Low | Low |  |  | High | Low | High | Risk Sharing | Sharing (dividing) common risk to stake holders or to joint ventures or partnership. | [12 empty] | NGA Engagement | NGA Engagement | Engineering Drawings | Project Re-Bidding | Construction Drawing Preparation |  | Preliminary Design |  | TOR Preparation | Tender Technical Review | Permitting
Medium | 3 | Medium | 3 | Low | GREEN | Very Low Medium | Very Low | Medium | Low |  |  | High | Medium | High | Risk Reduction | Reducing probability of occurrence or the severity of the consequences of an unwanted risk through Control. | [12 empty] | Optioneering | Project Approval | Geotech | Tender Bulletin | Construction Staging |  | Preliminary Feasibility Study |  | Preparation of Owner's Requirements |  | Pipe Installation
High | 4 | High | 4 |  |  | Very Low High | Very Low | High | Low |  |  | High | High | High | Risk Transfer | Shift the burden of the risk consequence to another party or entity. | [12 empty] | Planning | Project Timeline | HOA Engagement |  | Contractor's Procurement of Materials and Equipment |  | Programme Budget Setting |  | Preparation of Specifications |  | Testing
Very High | 5 | Very High | 5 |  |  | Very Low Very High | Very Low | Very High | Low |  |  | High | Very High | High | Risk Acceptance | Project will proceed but do nothing on the identified risk. | [12 empty] | Project Approval | Project Scheme Design | Instruction to Bidders |  | DW Borehole Development |  | Rate Rebasing Master Budget |  | Preparation of Reference Design
[6 empty] | Low Very Low | Low | Very Low | Low |  |  | Low | Very Low | Low | [14 empty] | Project Budget Analysis | Site Acquisition | LGU Engagement |  | DW Borehole Drilling |  | Regulatory Requirement Translation |  | Preparation of Detail Design
[6 empty] | Low Low | Low | Low | Low |  |  | Low | Low | Low | [14 empty] | Project Planning | Site Development Plan | Market Soundings |  | DW Borehole Investigation |  | Feasibility Studies
[6 empty] | Low Medium | Low | Medium | Low |  |  | Low | Medium | Low | Risk Status | [13 empty] | Project Research | Stakeholder Engagement | NGA Engagement |  | DW Borehole Rehab |  | Pre-Feasibility Studies
[6 empty] | Low High | Low | High | Low |  |  | Low | High | Medium | RETIRED | [13 empty] | Project Sizing | WBS Development | Project Plan Schedule |  | DW Electro-Mech works
[6 empty] | Low Very High | Low | Very High | Medium |  |  | Low | Very High | Medium | OPEN | [13 empty] | Regulatory Review |  | Scope Development |  | DW Geores
[6 empty] | Medium Very Low | Medium | Very Low | Low |  |  | Medium | Very Low | Low | [14 empty] | Site Acquisition |  | Site Acquisition |  | DW Install Submersible Pump
[6 empty] | Medium Low | Medium | Low | Medium |  |  | Medium | Low | Medium | Decision: | [13 empty] | Stakeholder Engagement |  | Site Development Plan |  | Earth Retaining Works
[6 empty] | Medium Medium | Medium | Medium | Medium |  |  | Medium | Medium | Medium | YES | [13 empty] | Water Source Investigation |  | Specifications Requirements |  | Earthworks
[6 empty] | Medium High | Medium | High | Medium |  |  | Medium | High | High | NO | [15 empty] | Stakeholder Engagement |  | Electrical Works
[6 empty] | Medium Very High | Medium | Very High | High |  |  | Medium | Very High | High | [16 empty] | Submission of Tender |  | Engineer & Control
[6 empty] | High Very Low | High | Very Low | Low | [21 empty] | TOR preparation |  | Equipment Set-Up |  | Project.Gates
[6 empty] | High Low | High | Low | Medium | [23 empty] | Excavate & Backfill |  | Gate0_Needs.Confirmation.RR.ABP
[6 empty] | High Medium | High | Medium | High | [23 empty] | Excavate & Fill |  | Gate1_Business.Case
[6 empty] | High High | High | High | High | [5 empty] | Risk Priority | [17 empty] | Excavate & Pour Footing |  | Gate2_Delivery.Strategy.Tender.Preparation
[6 empty] | High Very High | High | Very High | High | [5 empty] | Critical | [17 empty] | Excavation Pipe Laying |  | Gate3_Investment.Decision.Procurement
[6 empty] | Very High Very Low | Very High | Very Low | Medium | [5 empty] | Non-Critical | [17 empty] | Fence |  | Gate4_Readiness.For.Service.Construction
[6 empty] | Very High Low | Very High | Low | High | [23 empty] | Fill Site |  | Gate5_ Benefits.Realization.Operation
[6 empty] | Very High Medium | Very High | Medium | High | [23 empty] | Filling Works
[6 empty] | Very High High | Very High | High | High | [23 empty] | Finish Grade & Seed
[6 empty] | Very High Very High | Very High | Very High | High | [23 empty] | Finishes
[33 empty] | Form & Pour Slab |  | Project.Gates.WBS
[33 empty] | Form & Pour walks |  | Gate.0_Needs.Confirmation.RR.ABP
[33 empty] | Form & Pour Walls |  | Gate.1_Business.Case
[33 empty] | Form Works |  | Gate.2_Delivery.Strategy.Tender.Preparation
[6 empty] | Project.Gate | Project.Phase |  | Impact.Areas | [23 empty] | HVAC & Electrical |  | Gate.3_Investment.Decision.Procurement
[6 empty] | Gate.0_Needs.Confirmation.RR.ABP | Needs Confirmation (RR/ABP) |  | NO | [23 empty] | Initial Start Up & Test |  | Gate.4_Readiness.For.Service.Construction
[6 empty] | Gate.1_Business.Case | Business Case |  | YES | [23 empty] | Install Elec Switchboards |  | Gate.5_Benefits.Realization.Operation
[6 empty] | Gate.2_Delivery.Strategy.Tender.Preparation | Delivery Strategy (Tender Preparation) | [25 empty] | Install Electro-Mech
[6 empty] | Gate.3_Investment.Decision.Procurement | Investment Decision (Procurement) | [25 empty] | Install Energy Meters
[6 empty] | Gate.4_Readiness.For.Service.Construction | Readiness For Service (Construction) | [25 empty] | Install FDAS
[6 empty] | Gate.5_Benefits.Realization.Operation | Benefits Realization (Operation) | [25 empty] | Install Fire Fighting System
Install Genset
Install I&C
Install IT Equipment
Install Lab Instruments
[7 empty] | RISK INDEX | [25 empty] | Install Motor Drives
[8 empty] | Probability | [24 empty] | Install Network Meters
[7 empty] | Prob Range: | 50-90% | 10-25% | 25-50% | 90-100% | 0-10% | [5 empty] | Very Low | Low | Medium | High | Very High | [10 empty] | Install Network Valves
[6 empty] | Impact |  | High | Low | Medium | Very High | Very Low | [5 empty] | 1-10% | 10-25% | 25-50% | 50-90% | 90-100% | [10 empty] | Install Outdoor MCC
[7 empty] | High | High | Medium | High | High | Low | [5 empty] | 1% | 10% | 25% | 50% | 90% | [10 empty] | Install process and systems equipment
[7 empty] | Low | Low | Low | Low | Medium | Low | [5 empty] | 2% | 11% | 26% | 51% | 91% | [10 empty] | Install Remote Instruments
[7 empty] | Medium | Medium | Medium | Medium | High | Low | [5 empty] | 3% | 12% | 27% | 52% | 92% | [10 empty] | Install Utility Power
[7 empty] | Very High | High | High | High | High | Medium | [5 empty] | 4% | 13% | 28% | 53% | 93% | [10 empty] | Masonry & Openings
[7 empty] | Very Low | Low | Low | Low | Low | Low | [5 empty] | 5% | 14% | 29% | 54% | 94% | [10 empty] | Masonry to Floor Level
[18 empty] | 6% | 15% | 30% | 55% | 95% | [10 empty] | Metal Works
[18 empty] | 7% | 16% | 31% | 56% | 96% | [10 empty] | Mobilization
[7 empty] | RISK STRATEGY | [10 empty] | 8% | 17% | 32% | 57% | 97% | [10 empty] | Paint & Finishes
[7 empty] | Nature | Threats | Opportunities | [8 empty] | 9% | 18% | 33% | 58% | 98% | [10 empty] | Permitting
[7 empty] | Threats | Avoid | Exploit | [8 empty] | 10% | 19% | 34% | 59% | 99% | [10 empty] | Piling and Drilling Foundation
[7 empty] | Opportunities | Transfer | Share | [9 empty] | 20% | 35% | 60% | 100% | [10 empty] | Pipe & Electric Under Slab
[8 empty] | Mitigate | Enhance | [9 empty] | 21% | 36% | 61% | [11 empty] | Pipe Network Installation
[8 empty] | Accept | Accept | [9 empty] | 22% | 37% | 62% | [11 empty] | Pipe Sewer Installation
[19 empty] | 23% | 38% | 63% | [11 empty] | Pipe Transmission Installation
[19 empty] | 24% | 39% | 64% | [11 empty] | Piping Works
[19 empty] | 25% | 40% | 65% | [11 empty] | Plumbing
[20 empty] | 41% | 66% | [11 empty] | Project Handover
[20 empty] | 42% | 67% | [11 empty] | Project Substancial Completion
[7 empty] | Risk Evaluation: Classification |  |  |  | Risk Relationship | [8 empty] | 43% | 68% | [11 empty] | Project Testing & Commissioning
[7 empty] | Accepted |  |  |  | Independent | [8 empty] | 44% | 69% | [11 empty] | Road Safety Systems
[7 empty] | Rejected |  |  |  | Dependent | [8 empty] | 45% | 70% | [11 empty] | Road Works
[7 empty] | Significant |  |  |  | Interdependent | [8 empty] | 46% | 71% | [11 empty] | Roads Re-Blocking
[11 empty] | None | [8 empty] | 47% | 72% | [11 empty] | Roof Framing
[20 empty] | 48% | 73% | [11 empty] | Roofing
[20 empty] | 49% | 74% | [11 empty] | Set Equipment
[20 empty] | 50% | 75% | [11 empty] | Set Precast Station
[21 empty] | 76% | [11 empty] | Set Pumps & Vault
[7 empty] | Project.Type |  | Project Headlines | [11 empty] | 77% | [11 empty] | Set Station Pipes
[7 empty] | A |  | WS | [11 empty] | 78% | [11 empty] | Signages
[7 empty] | B |  | WW | [11 empty] | 79% | [11 empty] | Site Development
[7 empty] | C |  | CWN | [11 empty] | 80% | [11 empty] | Site Entrance
[7 empty] | D1 |  | CWS | [11 empty] | 81% | [11 empty] | Site Fencing
[7 empty] | D2 | [13 empty] | 82% | [11 empty] | Soil Stabilization
[7 empty] | E | [13 empty] | 83% | [11 empty] | Steel Works
[7 empty] | OH | [13 empty] | 84% | [11 empty] | Strip Topsoil
[7 empty] | IT | [13 empty] | 85% | [11 empty] | Temfacil
[21 empty] | 86% | [11 empty] | Temporary Backfill
[21 empty] | 87% | [11 empty] | Temporary excavation & Shoring
[21 empty] | 88% | [11 empty] | Temporary Roads
[21 empty] | 89% | [11 empty] | Tree Cutting
[21 empty] | 90% | [11 empty] | Trenchless micro-tunnelling works
Tunnel earth works handling
Tunnel electro-mechanical installations
Tunnel horizontal boring works TBM
Tunnel metal works
Tunnel pre-cast segment handling
Tunnel pre-cast segment making and storage
Tunnel segment mounting
Tunnel water proofing
Utility Comms
Utility Power
Utility Water
Walk Ways
Waterproofing Works
5 x 5 Heat Map
[23 empty] | Potential Impact | Very High (Extreme)
High (High)
Moderate (Medium)
Low (Low)
Very Low (Negligible)
[25 empty] | Very Low | Low | Moderate | High |  | Very High
[25 empty] | (Remote) | (Unlikely) | (Possible) | (Likely) |  | (Pobable)
Likelihood
[24 empty] | % Ranges | 0 - 10 % | 10 - 25 % | 25 - 50 % | 50 - 90 % |  | 90 - 100 %

## PRR (hidden)
Doc No: CPMG-PMO-PRR
PROJECT RISK REPORT |  |  | Report No: 01
Project / Programme Name: | Proj Mgr: | #REF! |  | Date:
#REF!
Project Risk Performance Dashboard
Project Risk Distribution Charts
Analysis and Recommendation:
Reference Data:
[5 empty] | Total No of Risk |  | #REF!
[5 empty] | Total Risk Cost, Php |  | #REF!
[5 empty] | Total Revenue Potential Loss, Php |  | #REF!
[5 empty] | Total Project Risk Cost |  | #REF!
[5 empty] | Total Proj Risk Delay, Days |  | #REF!
[5 empty] | High Risk Cost |  | #REF!
[5 empty] | High Cost Risk Event |  | #REF!
[5 empty] | High Risk Delay |  | #REF!
[5 empty] | High Delay Risk Event |  | #REF!
[5 empty] | Total Reserve Cost |  | #REF!
[5 empty] | Total Mitigation Cost |  | #REF!
[5 empty] | Total Savings after Mitigation |  | #REF!
[5 empty] | Critical Risk No |  | #REF!
[5 empty] | Non-Critical Risk No |  | #REF!
[5 empty] | Engineering |  | #REF!
[5 empty] | Environmental |  | #REF!
[5 empty] | Operation |  | #REF!
[5 empty] | Political |  | #REF!
[5 empty] | PQM |  | #REF!
[5 empty] | Procurement |  | #REF!
[5 empty] | Engineering |  | #REF! | #REF!
[5 empty] | Environmental |  | #REF! | #REF!
[5 empty] | Operation |  | #REF! | #REF!
[5 empty] | Political |  | #REF! | #REF!
[5 empty] | PQM |  | #REF! | #REF!
[5 empty] | Procurement |  | #REF! | #REF!
[5 empty] | Engineering |  | #REF!
[5 empty] | Environmental |  | #REF!
[5 empty] | Operation |  | #REF!
[5 empty] | Political |  | #REF!
[5 empty] | PQM |  | #REF!
[5 empty] | Procurement |  | #REF!
[5 empty] | Risk Open |  | #REF!
[5 empty] | Risk Retired |  | #REF!
[5 empty] | Residual Risk Index | Low | #REF!
[5 empty] | Residual Risk Index | Medium | #REF!
[5 empty] | Residual Risk Index | High | #REF!
TOTAL NO OF RISK
23
CRITICAL RISK
20
NON-CRITICAL RISK
3
OVERALL RISK RATING
MEDIUM
GROSS RISK COST
0M
PROJ RISK COST
0M
RISK REVENUE LOSS
0M
CONTINGENCY RESERVE
0M
CUMULATIVE DELAYS
0D
HIGH RISK COST
0M
PR.RR18-02466.17
MITIGATION COST
0M
RISK COST AVOIDED
0M

## Revision Record (hidden)
Revision Record
Version | Description | Author | Date
Rev 1.0 | First beta release. | DSE | 2021-06-01
Rev 1.1 | Inclusion of Monte Carlo Models and Formulas using freeware Argo | DSE | 2022-01-15
Rev 1.2 | Change Monte Carlo model software to RiskAMP. | DSE | 2022-09-01

## Guide
User Guide
This simple guideline provides quick information to get the user up to speed in using this project risk register template and provide guidance in the project risk assessment process. Below are the quick links for different topics which the user can follow help familiarized working with this template.
1.0 | Risk Process Flow Chart
2.0 | Impact Matrix
3.0 | Probability Matrix
4.0 | Heat Map and Risk Index
5.0 | Definition of the different Project Gates
1.0 | RISK PROCESS FLOW CHART PROJ TYPES ABC | Home
2.0 | IMPACT MATRIX | Home
3.0 | PROBABILITY MATRIX | Home
4.0 | HEAT MAP | Home | Description of Project Types
|  |  | Type | Name | Physical Parts
|  |  | A | Complex Systems | · Large pipeline networks
· New facilities
- Treatment plants (including utilities)
- Pumping stations
- Reservoirs
- Lifting stations (for Used Water)
|  |  | B | Simple systems/new facilities/new pipeline systems | · New large/medium pipeline networks (if any)
· New facilities (if any)
- Pumping stations
- Reservoirs
- Lifting stations (for Used Water)
|  |  | C | Rehab/replacement of networks | · Pipeline networks
|  |  | D1 | Retrofitting of facilities | · Mostly civil works
· Minor modifications to plant Process & Instrumentation Design (P&ID)
|  |  | D2 | Refurbishment of facilities | · Replacement of equipment and auxiliaries including P&ID
|  |  | E | Small pipeline laying | · Small pipelines
|  |  | OH | Overhead | Fleet, Properties
5.0 | PROJECT GATES | Home

## RBS
RISK BREAKDOWN STRUCTURE
Level 1 | Internal Project Risk | [8 empty] | External Project Risk (based on PESTLE Analaysis)
Level 2 | Executive | Operation | Human Resource | Procurement | Engineering | Work Health Safety | Organization | Strategy | PQM | Political | Economic | Social | Technology | Legal | Environmental
Level 3 | IR.EXE.010 | IR.OPS.010 | IR.HR.010 | IR.PRO.010 | IR.ENG.010 | IR.WHS.010 | IR.ORG.010 | IR.STR.010 | IR.PQM.010 | ER.POL.010 | ER.ECO.010 | ER.SOC.010 | ER.TEC.010 | ER.LEG.010 | ER.ENV.010
| Project Support | Business Interruption | Strategic | Needs Analysis Planning | Scope | Chemicals Substance Hazard | Company Culture | Project Concept Strategy | Scope Cost Time | Government Stability | Inflation | Lifestyle | Rate of Change | Taxation | Infrastructure |  |  | Note: ROW issues are regulatory issues.
| IR.EXE.020 | IR.OPS.020 | IR.HR.020 | IR.PRO.020 | IR.ENG.020 | IR.WHS.020 | IR.ORG.020 | IR.STR.020 | IR.PQM.020 | ER.POL.020 | ER.ECO.020 | ER.SOC.020 | ER.TEC.020 | ER.LEG.020 | ER.ENV.020
| Executive Stakeholder Conflicts | Human Factor | Compliance | Specifications | Design | Flammable Substances | Change Management | Initial Systems Design | Project Acceptance | Employment & Operational Laws | Taxes & Duties | Attitude & Beliefs | Use of Outsourcing | Employment | Cyclical Weather
| IR.EXE.030 | IR.OPS.030 | IR.HR.030 | IR.PRO.030 | IR.ENG.030 | IR.WHS.030 | IR.ORG.030 | IR.STR.030 | IR.PQM.030 | ER.POL.030 | ER.ECO.030 | ER.SOC.030 | ER.TEC.030 | ER.LEG.030 | ER.ENV.030
| Executive Turnover | Equipment Failure | Operational | Purchasing Method | Technology Adoption | Biological Infectious Diseases | Joint Ventures | Initial Scope Budget Time | Equipment Quality Issues | Government Leadership | Finance & Credit | Social Mobility | Research & Development | Consumer | Energy Availability & Cost
|  | IR.OPS.040 | IR.HR.040 | IR.PRO.040 | IR.ENG.040 | IR.WHS.040 | IR.ORG.030 | IR.STR.040 | IR.PQM.040 | ER.POL.040 | ER.ECO.040 | ER.SOC.040 | ER.TEC.040 | ER.LEG.040 | ER.ENV.040
|  | Work Health & Safety | Financial | Purchasing Documentation | Quality Systems | Physical Hazards | Mission Vision | Project Pre.Charter Review | Process Quality Issues | Trade Restrictions or Reform | Working Practices | Education | Knowledge Management System | Advertising | Social Implications
|  | IR.OPS.050 |  | IR.PRO.050 | IR.ENG.050 | IR.WHS.050 | IR.ORG.030 | IR.STR.050 | IR.PQM.050 | ER.POL.050 | ER.ECO.050 | ER.SOC.050 | ER.TEC.050 | ER.LEG.050 | ER.ENV.050
|  | System Failure |  | Inviting Clarifying Closing Offers | Cost Estimate | Manual Tasks Hazards | Coordination & Communication | Feasibilty Studies Options | Project Change Management | Tax Regulations | Exchange Rates | Demographics | Eliminate Bottlenecks | Import and Export | Disposal of Materials
|  | IR.OPS.060 |  | IR.PRO.060 | IR.ENG.060 | IR.WHS.060 | IR.ORG.030 | IR.STR.060 | IR.PQM.060 | ER.POL.060 | ER.ECO.060 | ER.SOC.060 | ER.TEC.060 | ER.LEG.060 | ER.ENV.060
|  | Outsourcing |  | Evaluating Offers | Project Timeline | Environmental Hazards | Leadership Issues | Contingency Provisioning | Communication | Corruption Levels | Cost of Living | Ethics & Religion | Network Coverage | Occupational Health & Safety | Ecological Consequences
`
|  | IR.OPS.070 |  | IR.PRO.070 |  | IR.WHS.070 | IR.ORG.030 |  | IR.PQM.070 | ER.POL.070 | ER.ECO.070 | ER.SOC.070 | ER.TEC.070 | ER.LEG.070 | ER.ENV.070
|  | Insufficient Process |  | Selection Successful Tenderer |  | Psychosocial Hazards | Reesource Optimization |  | Project Execution Issues | Bureaucracy Issues | GDP & GNP | Historical Issues | Production Efficiency | Compliance | Legislation
|  | IR.OPS.080 |  | IR.PRO.080 |  |  | IR.ORG.030 |  |  | ER.POL.080 | ER.ECO.080 | ER.SOC.080 | ER.TEC.080 | ER.LEG.080 | ER.ENV.080
|  | Process Failure |  | Negotiations |  |  | Prgam Services Collaboration |  |  | Stability of Neighbors | Globalization | Cross.Cultural Communication | Quality & Pricing | Regulatory Bodies | Contamination
|  | IR.OPS.090 |  | IR.PRO.090 |  |  | IR.ORG.030 | [5 empty] | ER.TEC.090 |  | ER.ENV.090
|  | System Quality |  | Contract Management |  |  | Business Continuity | [5 empty] | Intellectual Property |  | Geographic Location
|  |  |  | IR.PRO.100 | [8 empty] | ER.TEC.100 |  | ER.ENV.100
|  |  |  | Procurement Process Evaluation | [8 empty] | Patents & Licenses |  | Biohazard Pandemic
|  |  |  | IR.PRO.110 | [8 empty] | ER.TEC.110
|  |  |  | Disposals | [8 empty] | Government Activity & Legislation
[24 empty] | Internal | [8 empty] | External
[16 empty] | Risk Category Concatenated | Category1 | Category2 | Category3 | Risk.Code | Category1 | Internal | External | Executive | Operation | Human.Resource | Procurement | Engineering | Work.Health.Safety | Organization | Strategy | PQM | Political | Economic | Social | Technology | Legal | Environmental
[16 empty] | Internal Executive Project.Support | Internal | Executive | Project.Support | IR.EXE.010 | Internal | Executive | Political | Project.Support | Business.Interruption | Strategic | Needs.Analysis.Planning | Scope | Chemicals.Substance.Hazard | Company.Culture | Project.Concept.Strategy | Scope.Cost.Time | Government.Stability | Inflation | Lifestyle | Rate.of.Change | Taxation | Infrastructure
[16 empty] | Internal Executive Executive.Stakeholder.Conflicts | Internal | Executive | Executive.Stakeholder.Conflicts | IR.EXE.020 | External | Operation | Economic | Executive.Stakeholder.Conflicts | Human.Factor | Compliance | Specifications | Design | Flammable.Substances | Change.Management | Initial.Systems.Design | Project.Acceptance | Employment.Operational.Laws | Taxes.Duties | Attitude.Beliefs | Use.of.Outsourcing | Employment | Cyclical.Weather
[16 empty] | Internal Executive Executive.Turnover | Internal | Executive | Executive.Turnover | IR.EXE.030 |  | Human.Resource | Social | Executive.Turnover | Equipment.Failure | Operational | Purchasing.Method | Technology.Adoption | Biological.Infectious.Diseases | Joint.Ventures | Initial.Scope.Budget.Time | Equipment.Quality.Issues | Government.Leadership | Finance.Credit | Social.Mobility | Research.Development | Consumer | Energy.Availability.Cost
[16 empty] | Internal Operation Business.Interruption | Internal | Operation | Business.Interruption | IR.OPS.010 |  | Procurement | Technology |  | Health.Safety | Financial | Purchasing.Documentation | Quality.Systems | Physical.Hazards | Mission.Vision | Project.Pre_Charter.Review | Process.Quality.Issues | Trade.Restrictions.Reform | Working.Practices | Education | Knowledge.Management.System | Advertising | Social.Implications
[16 empty] | Internal Operation Human.Factor | Internal | Operation | Human.Factor | IR.OPS.020 |  | Engineering | Legal |  | System.Failure |  | Inviting.Clarifying.Closing.Offers | Cost.Estimate | Manual.Tasks.Hazards | Coordination.Communication | Feasibility.Studies.Options | Project.Change.Management | Tax.Regulations | Exchange.Rates | Demographics | Eliminate.Bottlenecks | Import.Export | Disposal.Materials
[16 empty] | Internal Operation Equipment.Failure | Internal | Operation | Equipment.Failure | IR.OPS.030 |  | Work.Health.Safety | Environmental |  | Outsourcing |  | Evaluating.Offers | Project.Timeline | Environmental.Hazards | Leadership.Issues | Contingency.Provisioning | Communication | Corruption.Levels | Cost.Living | Ethics.Religion | Network.Coverage | Occupational.Health.Safety | Ecological.Consequences
[16 empty] | Internal Operation Health.Safety | Internal | Operation | Health.Safety | IR.OPS.040 |  | Organization |  |  | Insufficient.Process |  | Selection.Successful.Tenderer |  | Psychosocial.Hazards | Resource.Optimization |  | Project.Execution.Issues | Bureaucracy.Issues | GDP.GNP | Historical.Issues | Production.Efficiency | Workplace.Compliance | Legislation
[16 empty] | Internal Operation System.Failure | Internal | Operation | System.Failure | IR.OPS.050 |  | Strategy |  |  | Process.Failure |  | Negotiations |  |  | Program.Services.Collaboration |  |  | Stability.Neighbors | Globalization | Cross_Cultural.Communication | Quality.Pricing | Regulatory.Bodies | Contamination
[16 empty] | Internal Operation Outsourcing | Internal | Operation | Outsourcing | IR.OPS.060 |  | PQM |  |  | System.Quality |  | Contract.Management |  |  | Business.Continuity | [5 empty] | Intellectual.Property |  | Geographic.Location
[16 empty] | Internal Operation Insufficient.Process | Internal | Operation | Insufficient.Process | IR.OPS.070 | [6 empty] | Procurement.Process.Evaluation | [8 empty] | Patents.Licenses |  | Biohazard.Pandemic
[16 empty] | Internal Operation Process.Failure | Internal | Operation | Process.Failure | IR.OPS.080 | [6 empty] | Disposals | [8 empty] | Government.Activity.Legislation
[16 empty] | Internal Operation System.Quality | Internal | Operation | System.Quality | IR.OPS.090
[16 empty] | Internal Human.Resource Strategic | Internal | Human.Resource | Strategic | IR.HR.010 | Risk.Priority.Level
[16 empty] | Internal Human.Resource Compliance | Internal | Human.Resource | Compliance | IR.HR.020 | 1
[16 empty] | Internal Human.Resource Operational | Internal | Human.Resource | Operational | IR.HR.030 | 2
[16 empty] | Internal Human.Resource Financial | Internal | Human.Resource | Financial | IR.HR.040 | 3
[16 empty] | Internal Procurement Needs.Analysis.Planning | Internal | Procurement | Needs.Analysis.Planning | IR.PRO.010
[16 empty] | Internal Procurement Specifications | Internal | Procurement | Specifications | IR.PRO.020
[16 empty] | Internal Procurement Purchasing.Method | Internal | Procurement | Purchasing.Method | IR.PRO.030
[16 empty] | Internal Procurement Purchasing.Documentation | Internal | Procurement | Purchasing.Documentation | IR.PRO.040 |  |  |  | Work Health Safety Hazards:
[16 empty] | Internal Procurement Inviting.Clarifying.Closing.Offers | Internal | Procurement | Inviting.Clarifying.Closing.Offers | IR.PRO.050 |  |  |  | chemicals and substances hazards . such as hazardous substances and dangerous goods, asbestos, lead and waste management
[16 empty] | Internal Procurement Evaluating.Offers | Internal | Procurement | Evaluating.Offers | IR.PRO.060 |  |  |  | flammable substances . such as LPG, acetylene, methane, ethanol, petrol, acetone, resins, and thinners for their fire and explosion risks and prevention
[16 empty] | Internal Procurement Selection.Successful.Tenderer | Internal | Procurement | Selection.Successful.Tenderer | IR.PRO.070 |  |  |  | biological hazards and infectious diseases . such as legionella and hendra virus
[16 empty] | Internal Procurement Negotiations | Internal | Procurement | Negotiations | IR.PRO.080 |  |  |  | physical hazards . such as equipment, confined spaces, electrical hazards and working at heights
[16 empty] | Internal Procurement Contract.Management | Internal | Procurement | Contract.Management | IR.PRO.090 |  |  |  | manual tasks hazards . such as the use of the human body to perform any kind of manual task
[16 empty] | Internal Procurement Procurement.Process.Evaluation | Internal | Procurement | Procurement.Process.Evaluation | IR.PRO.100 |  |  |  | environmental hazards . such as noise, lighting, surrounding environment (including uneven floor surfaces, etc.), cold, dust and heat stress
[16 empty] | Internal Procurement Disposals | Internal | Procurement | Disposals | IR.PRO.110 |  |  |  | psychosocial hazards . such as fatigue, work.related stress, workplace harassment and occupational violence.
[16 empty] | Internal Engineering Scope | Internal | Engineering | Scope | IR.ENG.010
[16 empty] | Internal Engineering Design | Internal | Engineering | Design | IR.ENG.020
[16 empty] | Internal Engineering Technology.Adoption | Internal | Engineering | Technology.Adoption | IR.ENG.030
[16 empty] | Internal Engineering Quality.Systems | Internal | Engineering | Quality.Systems | IR.ENG.040
[16 empty] | Internal Engineering Cost.Estimate | Internal | Engineering | Cost.Estimate | IR.ENG.050
[16 empty] | Internal Engineering Project.Timeline | Internal | Engineering | Project.Timeline | IR.ENG.060
[16 empty] | Internal Work.Health.Safety Chemicals.Substance.Hazard | Internal | Work.Health.Safety | Chemicals.Substance.Hazard | IR.WHS.010
[16 empty] | Internal Work.Health.Safety Flammable.Substances | Internal | Work.Health.Safety | Flammable.Substances | IR.WHS.020
[16 empty] | Internal Work.Health.Safety Biological.Infectious.Diseases | Internal | Work.Health.Safety | Biological.Infectious.Diseases | IR.WHS.030
[16 empty] | Internal Work.Health.Safety Physical.Hazards | Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040
[16 empty] | Internal Work.Health.Safety Manual.Tasks.Hazards | Internal | Work.Health.Safety | Manual.Tasks.Hazards | IR.WHS.050
[16 empty] | Internal Work.Health.Safety Environmental.Hazards | Internal | Work.Health.Safety | Environmental.Hazards | IR.WHS.060
[16 empty] | Internal Work.Health.Safety Psychosocial.Hazards | Internal | Work.Health.Safety | Psychosocial.Hazards | IR.WHS.070
[16 empty] | Internal Organization Company.Culture | Internal | Organization | Company.Culture | IR.ORG.010
[16 empty] | Internal Organization Change.Management | Internal | Organization | Change.Management | IR.ORG.020
[16 empty] | Internal Organization Joint.Ventures | Internal | Organization | Joint.Ventures | IR.ORG.030
[16 empty] | Internal Organization Mission.Vision | Internal | Organization | Mission.Vision | IR.ORG.040
[16 empty] | Internal Organization Coordination.Communication | Internal | Organization | Coordination.Communication | IR.ORG.050
[16 empty] | Internal Organization Leadership.Issues | Internal | Organization | Leadership.Issues | IR.ORG.060
[16 empty] | Internal Organization Resource.Optimization | Internal | Organization | Resource.Optimization | IR.ORG.070
[16 empty] | Internal Organization Program.Services.Collaboration | Internal | Organization | Program.Services.Collaboration | IR.ORG.080
[16 empty] | Internal Organization Business.Continuity | Internal | Organization | Business.Continuity | IR.ORG.090
[16 empty] | Internal Strategy Project.Concept.Strategy | Internal | Strategy | Project.Concept.Strategy | IR.STR.010
[16 empty] | Internal Strategy Initial.Systems.Design | Internal | Strategy | Initial.Systems.Design | IR.STR.020
[16 empty] | Internal Strategy Initial.Scope.Budget.Time | Internal | Strategy | Initial.Scope.Budget.Time | IR.STR.030
[16 empty] | Internal Strategy Project.Pre_Charter.Review | Internal | Strategy | Project.Pre_Charter.Review | IR.STR.040
[16 empty] | Internal Strategy Feasibility.Studies.Options | Internal | Strategy | Feasibility.Studies.Options | IR.STR.050
[16 empty] | Internal Strategy Contingency.Provisioning | Internal | Strategy | Contingency.Provisioning | IR.STR.060
[16 empty] | Internal PQM Scope.Cost.Time | Internal | PQM | Scope.Cost.Time | IR.PQM.010
[16 empty] | Internal PQM Project.Acceptance | Internal | PQM | Project.Acceptance | IR.PQM.020
[16 empty] | Internal PQM Equipment.Quality.Issues | Internal | PQM | Equipment.Quality.Issues | IR.PQM.030
[16 empty] | Internal PQM Process.Quality.Issues | Internal | PQM | Process.Quality.Issues | IR.PQM.040
[16 empty] | Internal PQM Project.Change.Management | Internal | PQM | Project.Change.Management | IR.PQM.050
[16 empty] | Internal PQM Communication | Internal | PQM | Communication | IR.PQM.060
[16 empty] | Internal PQM Project.Execution.Issues | Internal | PQM | Project.Execution.Issues | IR.PQM.070
[16 empty] | External Political Government.Stability | External | Political | Government.Stability | ER.POL.010
[16 empty] | External Political Employment.Operational.Laws | External | Political | Employment.Operational.Laws | ER.POL.020
[16 empty] | External Political Government.Leadership | External | Political | Government.Leadership | ER.POL.030
[16 empty] | External Political Trade.Restrictions.Reform | External | Political | Trade.Restrictions.Reform | ER.POL.040
[16 empty] | External Political Tax.Regulations | External | Political | Tax.Regulations | ER.POL.050
[16 empty] | External Political Corruption.Levels | External | Political | Corruption.Levels | ER.POL.060
[16 empty] | External Political Bureaucracy.Issues | External | Political | Bureaucracy.Issues | ER.POL.070
[16 empty] | External Political Stability.Neighbors | External | Political | Stability.Neighbors | ER.POL.080
[16 empty] | External Economic Inflation | External | Economic | Inflation | ER.ECO.010
[16 empty] | External Economic Taxes.Duties | External | Economic | Taxes.Duties | ER.ECO.020
[16 empty] | External Economic Finance.Credit | External | Economic | Finance.Credit | ER.ECO.030
[16 empty] | External Economic Working.Practices | External | Economic | Working.Practices | ER.ECO.040
[16 empty] | External Economic Exchange.Rates | External | Economic | Exchange.Rates | ER.ECO.050
[16 empty] | External Economic Cost.Living | External | Economic | Cost.Living | ER.ECO.060
[16 empty] | External Economic GDP.GNP | External | Economic | GDP.GNP | ER.ECO.070
[16 empty] | External Economic Globalization | External | Economic | Globalization | ER.ECO.080
[16 empty] | External Social Lifestyle | External | Social | Lifestyle | ER.SOC.010
[16 empty] | External Social Attitude.Beliefs | External | Social | Attitude.Beliefs | ER.SOC.020
[16 empty] | External Social Social.Mobility | External | Social | Social.Mobility | ER.SOC.030
[16 empty] | External Social Education | External | Social | Education | ER.SOC.040
[16 empty] | External Social Demographics | External | Social | Demographics | ER.SOC.050
[16 empty] | External Social Ethics.Religion | External | Social | Ethics.Religion | ER.SOC.060
[16 empty] | External Social Historical.Issues | External | Social | Historical.Issues | ER.SOC.070
[16 empty] | External Social Cross_Cultural.Communication | External | Social | Cross_Cultural.Communication | ER.SOC.080
[16 empty] | External Technology Rate.of.Change | External | Technology | Rate.of.Change | ER.TEC.010
[16 empty] | External Technology Use.of.Outsourcing | External | Technology | Use.of.Outsourcing | ER.TEC.020
[16 empty] | External Technology Research.Development | External | Technology | Research.Development | ER.TEC.030
[16 empty] | External Technology Knowledge.Management.System | External | Technology | Knowledge.Management.System | ER.TEC.040
[16 empty] | External Technology Eliminate.Bottlenecks | External | Technology | Eliminate.Bottlenecks | ER.TEC.050
[16 empty] | External Technology Network.Coverage | External | Technology | Network.Coverage | ER.TEC.060
[16 empty] | External Technology Production.Efficiency | External | Technology | Production.Efficiency | ER.TEC.070
[16 empty] | External Technology Quality.Pricing | External | Technology | Quality.Pricing | ER.TEC.080
[16 empty] | External Technology Intellectual.Property | External | Technology | Intellectual.Property | ER.TEC.090
[16 empty] | External Technology Patents.Licenses | External | Technology | Patents.Licenses | ER.TEC.100
[16 empty] | External Technology Government.Activity.Legislation | External | Technology | Government.Activity.Legislation | ER.TEC.110
[16 empty] | External Legal Taxation | External | Legal | Taxation | ER.LEG.010
[16 empty] | External Legal Employment | External | Legal | Employment | ER.LEG.020
[16 empty] | External Legal Consumer | External | Legal | Consumer | ER.LEG.030
[16 empty] | External Legal Advertising | External | Legal | Advertising | ER.LEG.040
[16 empty] | External Legal Import.Export | External | Legal | Import.Export | ER.LEG.050
[16 empty] | External Legal Occupational.Health.Safety | External | Legal | Occupational.Health.Safety | ER.LEG.060
[16 empty] | External Legal Workplace.Compliance | External | Legal | Workplace.Compliance | ER.LEG.070
[16 empty] | External Legal Regulatory.Bodies | External | Legal | Regulatory.Bodies | ER.LEG.080
[16 empty] | External Environmental Infrastructure | External | Environmental | Infrastructure | ER.ENV.010
[16 empty] | External Environmental Cyclical.Weather | External | Environmental | Cyclical.Weather | ER.ENV.020
[16 empty] | External Environmental Energy.Availability.Cost | External | Environmental | Energy.Availability.Cost | ER.ENV.030
[16 empty] | External Environmental Social.Implications | External | Environmental | Social.Implications | ER.ENV.040
[16 empty] | External Environmental Disposal.Materials | External | Environmental | Disposal.Materials | ER.ENV.050
[16 empty] | External Environmental Ecological.Consequences | External | Environmental | Ecological.Consequences | ER.ENV.060 | [18 empty] | Internal | [8 empty] | External
[16 empty] | External Environmental Legislation | External | Environmental | Legislation | ER.ENV.070 | [18 empty] | Executive | Operation | Human.Resource | Procurement | Engineering | Work.Health.Safety | Organization | Strategy | PQM | Political | Economic | Social | Technology | Legal | Environmental
[16 empty] | External Environmental Contamination | External | Environmental | Contamination | ER.ENV.080 | [18 empty] | Project.Support | Business.Interruption | Strategic | Needs.Analysis.Planning | Scope | Chemicals.Substance.Hazard | Company.Culture | Project.Concept.Strategy | Scope.Cost.Time | Government.Stability | Inflation | Lifestyle | Rate.of.Change | Taxation | Infrastructure
[16 empty] | External Environmental Geographic.Location | External | Environmental | Geographic.Location | ER.ENV.090 | [18 empty] | Executive.Stakeholder.Conflicts | Human.Factor | Compliance | Specifications | Design | Flammable.Substances | Change.Management | Initial.Systems.Design | Project.Acceptance | Employment.&.Operational.Laws | Taxes.&.Duties | Attitude.&.Beliefs | Use.of.Outsourcing | Employment | Cyclical.Weather
[16 empty] | External Environmental Biohazard.Pandemic | External | Environmental | Biohazard.Pandemic | ER.ENV.100 | [18 empty] | Executive.Turnover | Equipment.Failure | Operational | Purchasing.Method | Technology.Adoption | Biological.Infectious.Diseases | Joint.Ventures | Initial.Scope.Budget.Time | Equipment.Quality.Issues | Government Leadership | Finance.&.Credit | Social.Mobility | Research.&.Development | Consumer | Energy.Availability.&.Cost
[40 empty] | Health.Safety | Financial | Purchasing.Documentation | Quality.Systems | Physical.Hazards | Mission.Vision | Project.Pre-Charter.Review | Process.Quality.Issues | Trade.Restrictions.or.Reform | Working.Practices | Education | Knowledge.Management.System | Advertising | Social.Implications
[40 empty] | System.Failure |  | Inviting.Clarifying.Closing.Offers | Cost.Estimate | Manual.Tasks.Hazards | Coordination.&.Communication | Feasibility.Studies.Options | Project.Change.Management | Tax.Regulations | Exchange.Rates | Demographics | Eliminate.Bottlenecks | Import.&.Export | Disposal.of.Materials
[40 empty] | Outsourcing |  | Evaluating.Offers | Project.Timeline | Environmental.Hazards | Leadership.Issues | Contingency.Provisioning | Communication | Corruption.Levels | Cost.of.Living | Ethics.&.Religion | Network.Coverage | Occupational.Health.&.Safety | Ecological.Consequences
[40 empty] | Insufficient.Process |  | Selection.Successful.Tenderer |  | Psychosocial.Hazards | Resource.Optimization |  | Project.Execution.Issues | Bureaucracy.Issues | GDP.&.GNP | Historical.Issues | Production.Efficiency | Compliance | Legislation
[40 empty] | Process.Failure |  | Negotiations |  |  | Program.&.Services.Collaboration |  |  | Stability.of.Neighbors | Globalization | Cross-Cultural.Communication | Quality.&.Pricing | Regulatory.Bodies | Contamination
[40 empty] | System.Quality |  | Contract.Management |  |  | Business.Continuity | [5 empty] | Intellectual.Property |  | Geographic.Location
[42 empty] | Procurement.Process.Evaluation | [8 empty] | Patents.&.Licenses |  | Biohazard.Pandemic
[42 empty] | Disposals | [8 empty] | Government.Activity.&.Legislation
[39 empty] | Risks associated with the failure to provide executive support to the project; project team did not receive sufficient authority to execute critical decisions. | Risks arising from members of executive management that are combative to the project; there is a disagreement over project issues at executive level. | Risks associated with the changes in the company leadership, executives leaving the company, disruption at the leadership level. | Risks arising from structure fires, utility services damage, loss of electricity or running water, equipment failure, third-party disruptions, crime or vandalism, natural disasters. | Risks associated with human errors in the workplace with factors such as psychological, physiological, behavioral, lapses, mistakes and violations. | Risks associated with machine failure such as malfunction, incompatibility, intermittent failure, permanent failure, component fatigue, system failure, structural collapse, etc. | Internal H&S hazard in the operational workplaces such as in the offices, field works, project sites and plants which may affect project objectives. | Risks associated with failure of a system or network or series of equipment with inter-dependencies; failure of automation, telemetry and SCADA system. | Risks associated with outsourced talents, workforce, specialists and consultants) | Risks associated with a process employed that is not meeting the required performance or output. | Risks associated with the failure of a process such as in construction methodology and plant processes. | Risks associated with the failure of quality process in project sites or plant, failure to implement project controls and project management systems. | People-related issues that limit the ability to achieve strategic objectives. Key Sub-Areas: Talent Management and Succession, Planning, Ethics and Tone at the Top, Alignment of Pay and Performance. | Processes/controls to keep a company out of trouble. Note that reducing these risks has little bearing on being able to make the business better. Key Sub-Areas: Regulatory compliance, Fraud, Monitoring regulatory changes. | Operational (Meeting organizational objectives through effective/efficient use of human resources. Key Sub-Areas: Internal controls, Policies and procedures, Resource vendor management and sourcing, Employee training and development. | Global organizations view this, along with compliance, as the most traditional categories of risk. Key Sub-Areas: Equity/incentive compensation, Financial accounting and disclosure, HR performance metrics and cost management. | Risks arising from project statement, user needs, funding, timeframe and probity. | Developing the Specification (Risks associated with product or systems specification, project definition, statement of requirements. | Selecting the Purchasing Method creates Risks in failure to identify potential sources and selecting procurement method. | Purchasing Documentation Risks arising from unacceptable Terms and Conditions and inadequate project information. | Inviting, clarifying and closing offers (Risks associated with Tender bid bulletin, favoritism, breach of confidentiality, and insufficient number of bidders. | Risks in failure to follow bidding protocol, breach of security, offers fail to meet demands and subjective decisions. | Risks associated with selecting appropriate suppliers and selecting inappropriate product or Vendor/Contractor. | Risks associated with project expectation, deadlock on details of agreement or policy, failure to secure mandatory conditions, unfair contract conditions and failure to reflect terms offered in the contract. | Risks in variations, Supplier unwilling to accept contract, failure of either party to fulfill contract, inadequate contract administration, unauthorize early works, unauthorize increase in scope of works, loss of intellectual property, failure to meet liabilities of third parties, loss or damage to goods in transit, fraud and key personnel not available. | Risks associated with failure to evaluate procurement and management processes. | Risks associated with rigged auction bidding and inadequate tender management. | Risks resulting from poor scope definition, ambiguity, unclear, over scope, under scope, scope variations, scope creep and unrelated scope. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology. | Risks associated with Quality Management Systems (QMS) issues, such as project process documentation, planning, reviews and resourcing. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions. | Risks associated with project schedule, work breakdown schedule, etc. | Risks arising from hazardous substances and dangerous goods, asbestos, lead and waste management | LPG, acetylene, methane, ethanol, petrol, acetone, resins, and thinners for their fire and explosion risks and prevention. | Risks related to infectious diseases and its outbreaks such as legionella, Hendra virus, SARS, insect bites, snake bites, etc. | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc. | Risks in the use of the human body to perform any kind of manual tasks. | Risks in noise, lighting, surrounding environment (including uneven floor surfaces, etc.), cold, dust and heat stress | Risks arising from fatigue, work-related stress, workplace harassment and occupational violence. | Risks associated with the failure in mismatch between the company culture/structure/process and the project undertaking. | Risks associated with changes to management or major restructuring due to merger or acquisition throwing the project into chaos. | Risks from joint venture undertakings. | Risks arising from changes on company mandates, objectives and rationale. | Risks arising from failure to establish strategic mechanisms on coordination & communication, creating confusion and disturbances. | Risks for failure to establish formal leadership on key positions and functions within the organization; erosion of organizational authority. | Risks due to failure of resource allocation and resource optimization. | Risks for failure to achieve outcome due to lack or insufficient cooperation between programme level and services level initiatives. | Risks arising from the Organization’s failure to identify and formulate policies for business continuity efforts such as resiliency, recovery time and contingency plan. | Risks associated with project concept, projects with accepted inherent risks | Risks associated with erroneous initial designs without proper basis or filled with unfounded assumptions. | Risks resulting from issues on project initial scoping, budgeting and scheduling. | Risks associated with projects at its early stage Gate 0 without conducting a proper value assurance review. | Risks arising from lack of feasibility studies, or studies with full of errors, wrong assumptions and poor strategy. | Risks due to lack of contingency provision or misguided contingency. | Risks due to issues on project management scope, cost and time changes or variations that are unplanned and unrestrained affecting the project objectives. | Risks due to project acceptance issues such as non-conformance, plant performance deficiencies, unresolved punch list, etc., which will greatly impact project and business objectives and goals. | Risks arising from equipment quality issues such as defective products or equipment, non-standard installation, early failures, etc., which will directly impact the project objectives. | Risks arising from plant process control system issues, unsuitable process for the type of influent properties, process not meeting regulation requirements, process input requirements not sustainable, etc. | Risks resulting from changes in the management of project such as new project manager, scale down of work forces, change of Contractor and/or vendor, etc. | Risks arising from poor project communication such as incomplete or unsuitable weekly project report information, failure to communicate through proper channels critical project risk and issues, failure to complete project information, unwillingness to follow project management tools | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical. | Project risks from local or national level such as political war, insurgents, public unrest, change of government and election turmoil. | Project risks due to changes in labor law, worker’s compensation, employment discrimination, labor relations, family and medical leave, immigration, employee benefits, social security, wrongful termination, occupational safety and health hazard, social security retirement insurance (SSS/GSIS) and minimum wage. | Project risks arising from poor leadership in the government, national or local, e.g., failure in administrative processes, public decision making, relationships, public services and economic development. | New import/export tariff rates, trade ban, trade sanctions and trade barriers. | Business and income tax reforms, changes in federal tax codes, laws and regulations. | National and local corruption level index is high (e.g., Corruption Perception Index CPI score, https://www.transparency.org): bribery, clientelism, embezzlement, lobbying and patronage cases are high. | A bureaucracy is a large organization composed of appointed officials in which authority is divided among several managers. Issues in bureaucracy are red tape, conflict, duplication, imperialism, and waste. | Project risks arising from territorial claims, cessation of bilateral political coordination between countries, processes in neighboring countries that might destabilize the region, organized international crime, and infiltration. | Project risk due to changes in inflation rates (CPI, annual variation in %) based on domestic performance and the international market. | Tax and duty rates are long term factors affecting projects. | Sources of risk factors from sources and availability of funds for projects, credit lines and institution investment policies | Project risks due to working practices, de-skilling, e.g., loosing jobs due to implementation of machines and automation, people don’t speak to each other to get help as much anymore as they can find solution in the web, work motivation. | Exposure to changes in foreign exchange rates fundamentally affects the project budget, and subsequently scope and schedule performances. | The negative impact of high cost of living in meeting project objectives and implementation. | The impact of GDP and GNP rating in meeting project objectives and implementation. | The impact of globalized economy on managing projects: impact on project management processes, impact on absorptive (learning) capacity on cross-cultural context, impact on temporal alignment (project schedule, WBS), impact on social alignment (offshoring, co-sourcing), impact on vendor engagement. | A way of living of individuals or the society as a whole expressed in works and behavior patterns that impacts the project objectives. | These are assumptions and convictions a person hold to be true based on past experiences, on individual and communal level, that impact the objectives of the project. | It is a change in social status relative to one's current social location within a given society and may impact project objectives. | The education level of individual or of the society in general will have wide ranging impact on the success of project objectives. | Social demographics has to do with the statistical characteristics of human population, including population density, ethnicity, education level, health, economic status, religious affiliation, etc., which may impact the success or failure of the project objectives. | The moral belief systems and ethical values of individuals, community and society that affects the progress of the project objectives. These are expressed in the veneration of shrines, heritage areas, value systems, customs, manner and behavior transcended in the work and market places. | Social historical issues mostly are related to places, customs and people that may directly or indirectly impact the project objectives. | Cross-cultural communication are susceptible to mis-understanding resulting to mis-coordination and has the potential to affect the project objectives. | The evolving risk of emerging technologies such as adoption of new plant process, a new control and automation system, or a new chemical agent. | Risks associated with the use of outside or foreign supplier of goods and/or services in lieu of internal resources. Project is exposed to loss of control, loss of innovation, loss of organizational trust, and higher than expected transaction cost. | Recent trend in R&D and technology direction will have impact on project objectives. | Development or the lack of it in management system will have direct or indirect impact on project objectives. Knowledge-based management system based on old paradigm may not be suitable on new frontier projects; aggressive adoption of new management system may create confusion and gaps resulting in inefficiency with the end result of affecting the project objectives. | Risks associated in the use of technology in removing bottlenecks and improving business processes. | Risks associated with the availability and quality of communication network coverage for cloud-based solution impacting the project objectives. | Risks associated with the implementation of systems and processes affecting production efficiencies that will impact the project objectives. | The quality and pricing of technology devices, systems and processes will have an impact on the project objectives, e.g., risk of getting inferior products on a very highly competitive, unregulated and disruptive market. | Risks associated with issues on IP affecting the project objectives; e.g., infringement on intellectual property. | Risks associated with patents and licenses affecting the business objectives, e.g. expired government-issues license to operate. | Risks associated with Government initiatives, or the lack of it, on innovation, cybercrime, license regulation, adoption of new systems and technologies that will impact the project objectives. | Legal issues on taxation of business and projects, e.g., tax framework for Internet use, taxation for highly regulated utility product and services such as water distribution. | Legal issues on employment policies and laws, its implication affecting the nature of the business and project objectives; e.g., employee use of social media, marijuana in the work place, independent contractors/consultants. | Legal issues arising from the use of and consumption of product and services rendered by the Entity which will impact project objectives; e.g. consumer fraud issues, product safety and defects, personal injuries resulting from dangerous or defective products, false advertising and deceptive business practices. | Legal issues arising from advertisement and community engagement, such as fora on social and political issues surrounding the business and the project, posting of contents that violates terms and conditions, copyright | Legal issues on trade restrictions, supply contract, VAT, product compliance to technical requirements, product safety compliance issues, labeling and packaging and infringement on intellectual property rights. | Legal issues on occupational health and safety and safety in the workplace which will impact the project objectives. | These are employer’s legal issues requiring compliance to the Government’s requirements on workplaces, such as general employment lay, drug testing program, employment practice audits, employee investigations, etc. | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects. | These are built properties like buildings and infrastructures affecting the project objectives. | Typhoons, heavy rains, draught and other natural weather condition having direct or indirect impact on project objectives. | Impact of energy rate to production cost, affecting operation risk of projects. | Acceptability of the project to the surrounding community, affecting project schedule, cost and scope. | Availability of disposal location, specialist contractor for disposal handling, internal resource capability for disposal of materials; these factors will affect project objectives. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding. | Impact of environmental legislation to the project objectives. | Projects with plant process effluent (gas, solid, liquid) can be a source of contamination to the environment. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development. | Biological risk belonging to WHO Risk Group 4, a virus outbreak in a large community and spreading across the country or even globally without known treatment or preventive measures causing a pandemic that paralyzes the Government, commerce and industry.
[39 empty] | Project.Support | Executive.Stakeholder.Conflicts | Executive.Turnover | Business.Interruption | Human.Factor | Equipment.Failure | Health.Safety | System.Failure | Outsourcing | Insufficient.Process | Process.Failure | System.Quality | Strategic | Compliance | Operational | Financial | Needs.Analysis.Planning | Specifications | Purchasing.Method | Purchasing.Documentation | Inviting.Clarifying.Closing.Offers | Evaluating.Offers | Selection.Successful.Tenderer | Negotiations | Contract.Management | Procurement.Process.Evaluation | Disposals | Scope | Design | Technology.Adoption | Quality.Systems | Cost.Estimate | Project.Timeline | Chemicals.Substance.Hazard | Flammable.Substances | Biological.Infectious.Diseases | Physical.Hazards | Manual.Tasks.Hazards | Environmental.Hazards | Psychosocial.Hazards | Company.Culture | Change.Management | Joint.Ventures | Mission.Vision | Coordination.Communication | Leadership.Issues | Resource.Optimization | Program.Services.Collaboration | Business.Continuity | Project.Concept.Strategy | Initial.Systems.Design | Initial.Scope.Budget.Time | Project.Pre_Charter.Review | Feasibility.Studies.Options | Contingency.Provisioning | Scope.Cost.Time | Project.Acceptance | Equipment.Quality.Issues | Process.Quality.Issues | Project.Change.Management | Communication | Project.Execution.Issues | Government.Stability | Employment.Operational.Laws | Government.Leadership | Trade.Restrictions.Reform | Tax.Regulations | Corruption.Levels | Bureaucracy.Issues | Stability.Neighbors | Inflation | Taxes.Duties | Finance.Credit | Working.Practices | Exchange.Rates | Cost.Living | GDP.GNP | Globalization | Lifestyle | Attitude.Beliefs | Social.Mobility | Education | Demographics | Ethics.Religion | Historical.Issues | Cross_Cultural.Communication | Rate.of.Change | Use.of.Outsourcing | Research.Development | Knowledge.Management.System | Eliminate.Bottlenecks | Network.Coverage | Production.Efficiency | Quality.Pricing | Intellectual.Property | Patents.Licenses | Government.Activity.Legislation | Taxation | Employment | Consumer | Advertising | Import.Export | Occupational.Health.Safety | Workplace.Compliance | Regulatory.Bodies | Infrastructure | Cyclical.Weather | Energy.Availability.Cost | Social.Implications | Disposal.Materials | Ecological.Consequences | Legislation | Contamination | Geographic.Location | Biohazard.Pandemic
[39 empty] | Issues on lack of executive support on the project by the Board. | Issues on Mancom member openly against the project | Changes in corporate leadership risk. | Crime or vandalism risk. | Behavioral risk. | Machine component fatigue risk. | H&S field works risk. | Network SCADA and Telemetry failure risk. | Outsourcing engineering consultant firm/entity risk. | Issues on deep data, metrics and analytics on performance measurement | Construction process failure risk. | Construction quality management failure risk. | Ethical issues at executive level risk. | Issues with DOLE regulatory compliance | HR internal controls risk. | Compensation and salary risk. | Impractical timeframe risk. | Biased specification specification. | Failure to identify potential sources risk. | Bid documents not acceptable risk | Issues on tender clarifications. | Bid failure risk | Failure on due diligence risk. | Deadlock on details of agreement risk. | Failure to meet liabilities of third parties (eg. royalties or third party property insurance) risk. | Risk on failure to evaluate procurement and management processes. | Collusive bidding at auction risk. | Failure to identify project drivers risk. | Code compliance design issues. | Construction methodology risk. | Issues on design review exercises. | Cost escalation risk due to inflation, availability of materials and location. | Issues on not aligned project timelines and WBS. | Aerially deposited lead risk | Risk on acetone hazards. | Canine bite rabis infection risk. | Cold Environments risk | Manual lifting hazard risk. | Air quality and air pollution hazard risk. | Fatigue hazard risk. | Risk in company culture mismatch with project undertaking. | Change management risk | Joint ventures risk. | Change in company mandate risk. | Risk on failure to establish mechanism on coordination. | Risk on erosion of organizational authority. | Risk due to failure of resource allocation. | Insufficient cooperation between programme and services level risk. | Risk due to issues on contingency plans. | Budget limitation risk | Risk on errors on simulation. | Risk on intial project budgetary cost. | Issues on project pre-charter review document missing or undocumented. | Risk on errors in simulation. | Risk on project with inadequate provision for contingency cost. | Risk on cost changes | Issues on incomplete systems and tie-ups | Change of equipment brand model issues. | Issues on the use and operation of new technologies. | Change of Contractor risk. | Failure to communicate critical project risk and issues. | Contractor general performance issues. | Change of government risk. | Employee wrongful termination risk. | Issues in economic development. | Risk in the import and export rates policies. | Issues in business and income tax reforms. | Issues on high local corruption level index. | Risk on conflict of interest issues. | Issues on cessation of bilateral political coordination between countries. | Higher borrowing cost risk. | Issues on Customs tax and duties rates. | Credit rating assessment risk. | Risk due to failure of human interaction and communication. | Forex rates fluctuation risk. | Risk in high cost of living. | Risk due to GDP growth rate issues. | Risk on absortive capacity on cross-cultural context. | Risk in behavior pattern of individual or society. | Issues on community open resistance to the project. | Risk in the change of social status relative to current social location. | Risk on educational level of the community. | Issue on the statistical characteristics of human population. | Issues on heritage areas. | Issues on customs with deep historical significance. | Issues on local dialects. | Risk in the adoption of innovative technologies. | Risk in the use of external resource. | Risk in the new development in R&D. | Risk in inefficiency due to the ineffective management system. | Risk in the use of technology in removing bottlenecks. | Risk due to network communication availability. | Risk on the use of technology on systems and processes. | Risk on the cost of technology. | Risk on infringement. | Risk on using patented products. | Risk on Government lack of technology and systems innovation. | Risk on legal issues on tax framework for water utility services. | Risk on legal issue on use of social media in the workplace. | Risk on legal issue on the public use of MWO water supply. | Risk on legal issue on advertisement. | Trade restriction risk. | Risk on legal issue on occupational health safety. | Risk on compliance to Government requirements on employment lay. | Issues on MOA of plant installation in private properties | Issues on above grade structures and facilities | Risk on typhoons. | Risk on fluctuating energy cost. | Issues on community open resistance to the project. | Issue on availability of disposal location. | Risk on Downstream effect. | Environmental law risk. | Risk on carbon emmission using diesel Genset. | Issues on conflict or clashes with other foreseeable built structures or below ground networks. | Risk on pandemic.
[39 empty] | Issues on lack of sufficient authority of the project team. | Mancom project issues disagreement risk. | Issues on disruptions at the executive level. | Equipment and machine failure risk. | Lapses risk. | Machine incompatibility risk. | H&S office premises risk. | Plant automation failure risk. | Outsourcing minor works specialist vendors or contractors risk | Issues on IT & Data Network process. | IT & Data Network process failure risk. | Plant quality management failure risk. | Issues & challenges on on talent planning. | Issues with LGU particular or special provisions labor code compliance | HR policies and procedure risk. | Equity and incentive package. | Insufficient funding risk. | Definition of inappropriate product or service risk. | Selecting inappropriate method risk. | Erroneous contract risk | Risk on actual or perceived breach of confidentiality. | Breaches of security risk. | Selecting an inappropriate contractor risk. | Failure to reflect the terms offered and agreed in the contract risk. | Fraud risk. | Risk on failure to identify and address problems. | Inadequate disposal tender management risk. | Over scope risk. | Constructability issues. | Failure to identify tie-ins risk. | Risk on complete failure to fulfill Quality Management Systems of project. | Cost risk due to expediting. | Risk arising from moving project timelines and schedules. | Asbestos risk. | Risk on acetylene hazards. | Insect bites risk | Collision and Impact risk. | Manual works hazard risk. | Dust hazard risk. | Occupational violence risk. | Risk in company process mismatch with project undertaking. | Company major restructuring risk. | Undertaking risk. | Change in company objectives risk. | Risk on failure to establish mechanism on corporation communication. | Risk on failure to establish formal leadership on key functions. | Risk due to failure of resource optimization. | Risk for failure to achieve outcome due to poor collaboration. | Risk due to lack or resiliency. | Community opposition risk. | Risk on initial design due to unaccounted regulatory requirements. | Risk on intial project schedule and timeline. | Risk on project benefits not properly articulated or not documented. | Risk on project with erroneous feasibility study report. | Risk on project without provision for contingency cost. | Risk on schedule changes | Issues on the availability of required subject matter expert. | Defective product or equipment risk. | Plant process control system issues. | Change of Owner's Engineer Consultant risk. | Failure to communicate through proper channels risk. | Issues on availability of construction documents and information at site. | Election turmoil risk. | Employees benefits risk. | Issues in public decision making. | Risk in trade ban. | Issues on compliance tax risk. | Issues on high national corruption level index. | Risk on delays on the issuance of permits. | Issues on sovereign territorial claims. | Issues on goods competitive disadvantage. | Issues on tax reforms. | Institution investment policies risk. | Risk due to work force de-skilling issues. | Transaction exposure risk. |  | Risk due to GNP growth rate issues. | Risk on project management processes. | Risk in changing lifestyle. | Issues on personal and communal value system. |  | Risk on the education level of available local talents and resource. | Issues on economic status. | Issues on the veneration of shrines. | Issues on local places with historical significance. | Issues on perceived community values and customs. | Risk in the adoption of new cloud-based SCADA system. | Risk in the use of foreign services. | Risk in the obselences of the installed plant still in its prime economic condition. | Risk in the adoption of unsuitable management system. | Risk in the use of technology to improve business processes. | Issues on internet bandwidth availability. | Risk on technologies affecting efficiencies and production. | Risk on the quality of technological equipment. | Risk on intellectual property rights. | Risk on using patented process. | Risk on Government initiative on cybercrime. | Risk on legal issues on tax framework on PPP portfolio projects. | Risk on legal issue on the use of substance in the workplace. | Risk on legal issue of consumer fraud. | Risk on legal issue on community engagement. | Supply contract risk. | Risk on legal issue on safety in the workplace.. | Risk on compliance to Government requirements on drug testing. | Issues on MOA of plant installation in public and Government properties | Issues on below grade utilities and structures. | Risk on heavy rains. | Risk on availability of energy at site. | Issues on project negatively affecting the community. | Issue on availability of specialist contractor disposal handling. | Risk on ecological consequences. | Risk on changes on Environmental laws and regulations. | Risk on chemical contamination. | Issues on deforestation. | Risk on community quarantine.
[41 empty] | Issues on incumbent executives leaving the company. | Loss of electric power supply risk. | Mistakes risk. | Machine intermittent failure risk. | H&S plant and warehouse premises risk. | UW Lift stations failure risk. | Outsourcing specialist and expert matter consultant risk. | Issues on plant and production processes. | Plant process failure risk. | Project control & monitoring failure risk. | Issues on compensation package | Labor code regulation changes risk. | HR resource vendor management risk. | HR cost management | Needs overstatement risk. | Inadequate statement of requirements risk. |  | Issue on not enough time for Contractor/Vendor to prepare bids. | Risk on actual or perceived favouritism in providing information. | Decision made on subjective grounds risk. | Selecting an inappropriate supplier or vendor risk. | Inadvertently creating a contract without the delegate’s prior approval risk. | Inadequately administering the contract risk. |  |  | Poor scope definition risk. | Design approval issues. | Issues on executives not supporting new emerging technologies. | Risk on failure on live project planning. | Cost risk due to unaccounted environmental impact of the project. | Risk on incomplete project timelines. | Dangerous goods risk. | Risk on ethanol hazards. | Localized contagious virus risk | Compressed Gases |  | Gassy or potentially gassy operations risk. | Workplace harassment risk. | Risk in company structure mismatch with project undertaking. | Merger & acquisition risk. |  | Change in company rationale risk. |  | Risk on failure to establish formal leadership on key positions. |  |  | Risk due to recovery time issues. | Cost risk. | Risk on initial designs based on unfounded assumptions. | Risk on intial project scope, budget, schedule and timeline. | Risk on project pre-charter review not conducted. | Risk on project with feasibility studies having insufficient options. | Unfounded provisioning for contingency risk. | Risk on scope changes. | Plant performance deficiency risk. | Early failures risk. | Plant process input requirements not sustainable. | Change of Supplier or Vendor risk. | Incomplete weekly project report risk. | Issues on availability of space for construction machineries and equipment. | Military movements risk | Employment discrimination risk. | Issues in public relationships. | Risk in trade barriers. | Issues on financial accounting tax risk. | Risk on high bribery issues. | Risk on delays on the processing and issuance of Government documents. | Risk on infiltration issues. | Purchasing power risk. | Issues on VAT on import and export of goods. | Issues on credit lines. | Work motivation issue. | Translation exposure risk. |  |  | Risk on social alignment such as offshoring and co-sourcing. | Risk in way of living of individual or society. | Risk on conflicts of beliefs. |  |  | Issus on religious affiliation. | Risk on communal and societal customs, manner and behavior. | Issues on society and its history. | Risk in failure to communicate. | Risk in the adoption of new plant process. | Risk in the use of foreign supplied goods and materials. | Risk in the obsolences of processes due to the latest R&D global direction. | Risk in the aggressive adoption of new management system. |  | Risk on GSM coverage at remote project site. |  | Risk on the quality of technology process and systems. |  | Risk on using patented systems. | Risk on Government license regulation. |  |  | Risk on legal issue on product safety and defects. | Risk on legal issue on fora on social & political issues surrounding the project. | Risk on VAT laws. | Issues on DOLE regulatory requirements. | Risk on compliance to Government requirements employment practice audit. | Issues on land acquisitions | Issues on excavation along newly built roads. | Risk on draught. |  | Risk on community acceptance of the project. | Issue on MWO internal resource capability for disposal of materials. | Risk on impact on air. | Risk on environmental sanction | Risk on environmental surface contamination. | Issues on municipal boundary dispute of project location. | Risk on large-scale viral infection.
[42 empty] | Loss of potable water risk. | Physiological risk. | Machine malfunction risk. | H&S project site risk. | Water network booster failure risk. | Outsourcing student internship (OJT) program risk. | Issues on process employed on SCADA & Telemetry. | SCADA & Telemetry process failure risk. | Project management failure risk. | Issues on talent performance | Talent regularization issues. | HR talent sourcing risk. | HR financial accounting and disclosure risk. | Needs understatement risk. | Narrow definition or brand model partisan risk. |  | Providing inadequate information risk. | Risk on failure to adequately address enquiries from tenderers. | Failure to follow effective evaluation procedures risk. | Selecting inappropriate product risk. | Risk on bloated or over budget bids. | Issue on Supplier or Contractor unwilling to accept contract. |  |  | Risk on scope not related to the project. | Design deficiency risk. | Issues on technology adoption not aligned with business strategy. | Risk on failure on process documentation. | Cost risk due to unaccounted hazardous waste removal and containment. | Risk on insufficient project timelines. | Leaks or release in air of toxic gas risk. | Risk on handling hydro-carbon derived hazardous materials. | Snake bites risk. | Confined space risk. |  | Lighting hazard risk. | Work-related stress risk. | [8 empty] | Risk on failure to formulate policies on business continuity. | Environmental risk. | Risk on initial designs without proper basis. | Risk on intial project scoping. |  | Risk on project with feasibility studies having poor strategies. |  | Risk on unplanned time extension | Risk on mismatch on original and final project benefits. | Issues on installed products that are not type-approved. | Plant process not meeting regulation requirements risk. | New construction manager risk. | Poor project communication risk. | Issues on civil and site development works | Paramilitary and insurgent movements risk. | Family and medical leave risk. | Issues in public services. | Risk in trade sanctions. | Issues on operational tax risk. | Risk on high clientelism issues. | Risk on duplication issues. | Risk on organized international crime. | Risk due to changes in inflation rates. | Risk on additional duties and taxes on import and export of goods. | Sources of funds risk. |  |  |  |  | Risk on temporal alignment such as WBS and project schedule. | Risk in work values of individual or society. | Risk on diversity in society and community. |  |  | Risk on community health. | Risk on value systems. |  | Risk on the erosion of stakeholder local engagement. | Risk in the use of new control and automation system. |  |  | Risk in the use of obsolete project management system. |  |  |  | Issues on using inferior products |  | Risk on using expired government-issued license. | Risk on Government adoption on new systems. |  |  | Risk on legal issue on personal injuries resulting from the use of contaminated water. | Risk on legal issue on posting of contents violating terms & conditions. | Risk on product compliance to technical requirements. |  | Risk on compliance to Government requirements on employee investigations. | Issues on land conversions | Risk on available space due to existing facilities and structures. | Risk on natural weather conditions. |  |  | Issue on illegal disposal | Risk on impact on biodiversity. |  | Risk on fuel oil seepage. | Issues on not enough plot of land or properties for project development. | Risk on viral infection on project site and barracks.
[42 empty] | MWO building premises and structure fire risk. | Psychological risk. | Machine permanent failure risk. | H&S transport and mobility risk. | Water network system valving failure risk. | Outsourcing temporary rank and file staff risk. | Issues on quality management process system. |  |  | Talent management risk. |  | HR talent training and development risk. | HR performance metrics | Probity issues. |  |  | Risk on contract not suitable for project. | Risk on insufficient number of accredited and qualified product vendors and suppliers | Failure to identify a clear winner risk. |  | Risk on failure to secure agreement in relation to Capdev Contracts Confidentiality Policy. | Key personnel not available risk. |  |  | Risk on strategic scope not translated to engineering scope. | Design flaw risk. | Risk on adopting new process technology. | Risk on failure to do project reviews. | Engineering cost estimate higher than ABP cost risk. | Risk on very long project timelines. | Waste management risk | Risk on hydro derivative gas accumulation from STP tanks and chambers. |  | Drowning risk |  | Noise hazard risk. | [10 empty] | Governance and Regulation risk. | Risk on initial plant sizing due to inconsistent load requirement analysis. |  |  | Risk on project with feasibility studies using unfounded assumptions. |  | Risk on unplanned variation order | Risk on plant full performance test using partial loading only. | Non-standard installation risk. | Plant, system or process performance guarantee risk. | New project manager risk. | Risk on unwilingness to follow project management tools. | Issues on construction equipment repair and maintenance. | Political war risk. | Immigration policies risk. | Local government poor leadership risk. |  | Issues on portfolio tax risk. | Risk on high embezzlement issues. | Risk on imperialism issues. | Risk on regional destabilization due to processes in neighboring countries. |  | Risk on changes on Customs tax and duties rates. | [5 empty] | Risk on vendor engagement. |  | Risk on individual or communal assumptions and convictions. |  |  | Risk on education level. |  |  |  | Risk in the use of new model equipment. | [6 empty] | Risk on disruptive market technology. |  |  | Risk on Government adoption on new technologies. |  |  | Risk on legal issue on falsified advertising. | Risk on legal issue on copyright. | Product safety compliance issue. |  |  | Issues on the use of Government-owned raw water input common facilities. | Risk on un-accounted facilities in conflict with the project. | Risk on thunderstorm. |  |  |  | Risk on impact on climate. |  | Risk on process plant effluent. | Issues on protected areas. | Risk on viral infection on the nearest community of the project.
[42 empty] | Natural disaster risk. | Violations risk. | Supporting Structure collapse risk. |  | Water reservoir filling rate failure risk. |  |  |  |  | Talent succession risk. |  |  |  | User needs misinterpretation risk. |  |  | Terms and conditions unacceptable to tenderers risk. | Risk on insufficient number of accredited consultants | Issues on Bidders requesting for time extension on tender submission. |  | Risk on failure to secure mandatory conditions. | Loss of intellectual property risk. |  |  | Risk on undefined or varying WBS. | Design not in MWO Standard risk. | Risk on adopting proprietary technology. | Risk on project resourcing. | Issues on project base cost estimate. |  |  | Risk on LPG hazards |  | Electrical hazard risk. |  | Project sitea area prone to landslide risk. | [10 empty] | HOA MOA issues | Risk on initial plant sizing due to inconsistent water source analysis. |  |  | Risk on project without feasibility studies. |  | Risk on unrestrained cost escalation | Risk on plant partial system test. |  | Process proving issues | Scaledown of work forces risk. | Unsuitable project report information risk. | Issues on construction site hazard management. | Public unrest risk. | Issues in social security retirment insurance SSS GSIS policies. | National government poor leadership risk. |  | Issues on reputational tax risk. | Risk on high lobbying issues. | Risk on LGU/NGA approval or no objection of design and studies. | [10 empty] | Risk on norms on the society. |  |  | Risk on ethnicity. |  |  |  | Risk in the use of newly developed checmial agents. | [12 empty] | Risk on legal issue on deceptive business practice. |  | Labeling and packaging issues. |  |  | Risk on change of regulations. | [5 empty] | Risk on impact on ecosystems. |  |  | Issues on sewer influent flow rate. | Risk on industrial, commercial business limited mobility
[42 empty] | Third-party disruption risk. |  | System failure risk. |  | Water transmission pipe failure risk. |  |  |  |  | Tone at the top risk. | [6 empty] | TOR incomplete with loop holes risk. | Risk on insufficient number of accredited contractors. | Issues on Tender Evaluation |  | Risk on not matching the expectations of buyer and tenderer. | Loss or damage to goods in transit risk. |  |  | Scope creep risk. | Design not in MWSS Standards or MWSS TAGS risk. | Risk on failure of the leadership to adopt to emerging technologies. |  | Issues on project phasing. |  |  | Risk on methane hazards. |  | Fires risk |  | Surrounding environment hazard risk. | [10 empty] | Inadequate or wrong assumptions risk | Risk on over design of plant and systems. |  |  | Risk on using wrong models. |  | Risk on unrestrained project schedule delays | Risk on project benefits without proper metrics. |  | Unsuitable plant process issues. | Issues on project key personnel change. | Project design and construction coordination issues with critical Stakeholders. | Issues on construction site proper house keeping. | Terrorist activities risk. | Labor relations risk. | Risk in the failure of administrative processes. |  | Issues on tax risk management. | Risk on patronage issues. | Risk on red tape issues. | [10 empty] | Risk on paradigm shift. |  |  | Risk on population density. |  |  |  | Risk in the use of proprietary technologies. | [14 empty] | Infringement on intellectual property rights. |  |  | Risk on corporate legislation. | [5 empty] | Risk on impact on fisheries and migrations. |  |  | Issues on site accessibility
[42 empty] | Utility services damage risk. | [15 empty] | TOR inimical to MWO risk. | Risk on insufficient number of accredited specialists. | Issues on Tender offers exceeding the budget. |  | Unfair or onerous requirements on the tenderer in the contract conditions risk. | Risk on Contractor or Vendor started work without NTP or signed Contract. |  |  | Scope variations risk. | Insufficient details on the design risk. | Risk on failure to create guidelines and policies on the new adopted technology. |  | Lead times risk. |  |  | Risk on paint hazards. |  | Hand / Arm Vibration risk |  | Temperature stress risk | [10 empty] | Inadequate Planning Risk | Risk on system sizing due to over population. | [5 empty] | Risk on system non-conformance. |  |  |  | Issues on insufficient or outdated construction progress report. | Issues on Contractor's performance on project management. | Travel restrictions risk. | Minimum wage issues. |  |  | Issues on transactional tax risk. |  | Risk on wastage issues. | [10 empty] | Risk on perceived value system. | [24 empty] | Risk on industry legislation. | [5 empty] | Risk on impact on flora and fauna. |  |  | Issues on unsuitable project site location.
[59 empty] | Risk on insufficient number of responses. | Issues on Tender offers excessively below budget. |  |  | Risk on failure of Contractor to provide timely construction equipment and materials as per project timeline. |  |  | Under scope risk. | Issues in Health and Safety in Design. | Risk on failure to do due diligence before adopting new technologies. |  | Mode of payment risk. |  |  | Risk on petrol hazards. |  | Hot Environments risk | [12 empty] | Issues on failure to exhaust all areas of potential impact. | Risk on system sizing due to under population. | [5 empty] | Risk on undefined project benefits. |  |  |  |  | Issues on Electro-Mechanical systems and devices |  | Risk due to changes in labor law. |  |  | Risk in changes in federal tax codes, laws and regulations. | [12 empty] | Risk on public acceptance of products, goods and commodoties. | [24 empty] | Risk on regulation of business commodoties. | [5 empty] | Risk on impact on forest. |  |  | Risk due to raw water source quality issues
[59 empty] | Risk on no response from known quality vendors or contractors. | Offers fail to meet needs risk. |  |  | Risk on failure of either party to fulfil the conditions of the contract |  |  |  | Issues on delays on design and drawing production. | Risk on failure to establish appropriate design criteria. |  | Risk due to failure to account insurance rate on project coverage. |  |  | Risk on resins hazards. |  | Hyperbaric (High Pressure) Environments risk | [12 empty] | Issues on technical pre-works | Risk on the issues of data accuracy on water demand projection. | [5 empty] | Unresolved punch list risk. |  |  |  |  | Issues on equipment and systems failures during process probing. |  | Risk due to changes in workers compensation. |  |  | Risk in non-compliance to tax laws. | [12 empty] | Risk on public acceptance of project. | [24 empty] | Risk on regulation of business industries. | [5 empty] | Risk on impact on groundwater |  |  | Risk due to used water influent quality issues.
[59 empty] | Risk on not enough contractors or vendors with sufficient project experience. |  |  |  | Risk on failure to deliver goods on time or delayed deliveries. |  |  |  | Issues on design on local control, plant systems coordination and SCADA. | Risk on failure to establish basis of design. |  | Risk on cost due to unaccounted code and regulatory compliance issues. |  |  | Risk on thinners hazards. |  | Hypobaric (Low Pressure) Environments risk | [12 empty] | LGU permits risk | Risk on using wrong models. | [10 empty] | Issues on insuffienct manpower and skilled workers. |  | Risk in occupational safety and health hazard policies. | [15 empty] | Risk on public acceptance of services. | [24 empty] | Risk on regulation of business sectors. | [5 empty] | Risk on impact on land. |  |  | Risk on fault line
[59 empty] | Risk on too many bid bulletin and bid addenda. |  |  |  | Risk on variances on delivered goods. |  |  |  | Issues on over design of plant systems, networks and equipment. | Risk on failure to identify technology champion within MWO. |  | Risk on cost impact caused by modifications directed by governmental authorities. |  |  |  |  | Ionizing Radiation risk | [12 empty] | Limited available real estate risk | [11 empty] | Issues on laydown areas |  | Social security issues. | [15 empty] | Risk on public sentiments and reactions due to community impact of the project. | [24 empty] | Risk on security legislation. | [5 empty] | Risk on impact on noise pollution. |  |  | Risk on flooding in or near the project area.
[63 empty] | Unauthorised increase in scope of work risk. |  |  |  | Operational and maintenance issues. | Risk on failure to institutionalize the adopted new technology. |  | Risk on cost impact of purchased utilities during construction. |  |  |  |  | Light, Lasers risk | [12 empty] | MMDA permits risk | [11 empty] | Issues on manpower loading as per project schedule and WBS. | [42 empty] | Risk on the issue of co-located and co-use Government facilities & properties. | [5 empty] | Risk on impact on rare endangered and threatened species. |  |  | Risk on geograhic location of the project.
[63 empty] | Variations in price and foreign exchange risk. |  |  |  | Poor design risk. | Risk on failure to provide sufficient data and information in the TOR. |  | Risk on failure to account cost of quality assurance such as materials testing. |  |  |  |  | Microwave and Radio-frequency risk | [12 empty] | New emerging technology risk | [11 empty] | Issues on MWO performance on project management. | [42 empty] | Risk on the issue of right of way | [5 empty] | Risk on impact on Riparian Habitat. |  |  | Risk on landslide along excavation.
[67 empty] | Risk in design simulation. | Risk on leadership culture towards technology adoption. |  | Risk on failure to account provisions on difficult site access. |  |  |  |  | Noise hazard risk. | [12 empty] | NGA certification issuance risk | [11 empty] | Issues on not meeting project objectives during process probing. | [42 empty] | Risk on the use of easements and buffer zones. | [5 empty] | Risk on impact on soil. |  |  | Risk on landslide near the project area
[67 empty] | Risk on design not in accord with good engineering practice. | Risk on non-technical adoption risk. |  | Risk on failure to allocate or define terms of warranty. |  |  |  |  | Non-Ionizing Radiation risk | [12 empty] | Operational Risk. | [11 empty] | Issues on not meeting the project benefits during and/or after process probing. | [48 empty] | Risk on impact on water. |  |  | Risk on low water table.
[67 empty] | Risk on failure to account as-built drawings in the design. | Risk on using outdated technology. |  | Risk on failure to identify cost on commissioning and startup costs. |  |  |  |  | Operation of heavy equipment and machineries risk. | [12 empty] | Proprietary technology risk | [11 empty] | Issues on project or Contractor's expatriate resopurces | [48 empty] | Risk on impact on wildlife. |  |  | Risk on narrow road pipe laying excavation
[67 empty] | Risk on failure to establish project critical path. |  |  | Risk on failure to include provisions on envirnmental control cost. |  |  |  |  | Power Frequency Electromagnetic Field (ELF) risk | [12 empty] | Public health illness risk. | [11 empty] | Issues on proper strorage of construction documentation. | [48 empty] | Risk on irreversible environmental impact. |  |  | Risk on poor access road condition
[67 empty] | Risk on failure to validate data inputs on design. |  |  | Risk on failure to include provisions on safety and industrial hygiene. |  |  |  |  | Radiation hazard risk. | [12 empty] | Public health process related risk. | [11 empty] | Issues on roadworks safety implementations. | [51 empty] | Risk on poor soil condition for pipeline excavation.
[67 empty] | Risk on Incomplete design. |  |  | Risk on failure to provide allowances on unforeseen items. |  |  |  |  | Seismic risk | [12 empty] | Reputation risk. | [11 empty] | Issues on Temfacil | [51 empty] | Risk on poor soil for foundation.
[67 empty] | Risk on the use of partial data and information from sampling. |  |  | Risk on failure to provide cost and identify sufficient areas for easements. |  |  |  |  | Slips, Trips and Falls risk | [12 empty] | ROW issues | [11 empty] | Issues on temporary electrical cable installation practices. | [51 empty] | Risk on roadworks safety on busy highways.
[67 empty] | Risk on using outdated or inconsistent as-built drawings in the design. |  |  | Risk on failure to provide cost on rental of heavy equipment. |  |  |  |  | Thermal hazard risk | [12 empty] | Safety risk. | [11 empty] | Issues on undocumented safety meetings. | [51 empty] | Risk on rock layers during excavation.
[70 empty] | Risk on failure to provide redundancy of equipment on critical works or process. |  |  |  |  | Tools and Machines Risk | [12 empty] | Site acquisition risk | [11 empty] | Issues on un-resolved construction punch lists. | [51 empty] | Risk on water source depletion.
[70 empty] | Risk on high cost due to construction methodology. |  |  |  |  | Ultraviolet/Sunlight risk | [12 empty] | Technology adaption risk | [11 empty] | Issues on workers not properly trained for the job.
[70 empty] | Risk on insufficient or no provision on temfacil. |  |  |  |  | Ventilation Risk | [12 empty] | Water source risk | [11 empty] | Project construction schedule issues.
[70 empty] | Risk on non-standard items. |  |  |  |  | Whole-Body Vibration risk | [24 empty] | Risk on Contractor's labor dispute and work strike.
[70 empty] | Risk on project geo-political location. |  |  |  |  | Working at heights risk. | [24 empty] | Risk on Contractor's procurement process of materials and equipment.
[70 empty] | Risk on site conditions. | [29 empty] | Risk on damage to existing structure and facilities.
[70 empty] | Risk on specialty works. | [29 empty] | Risk on failure of the Consultant to deliver the detailed design on time.
[70 empty] | Risk on studies and research required during construction phase. | [29 empty] | Risk on failure of the Contractor to complete on time approved scheduled construction drawings.
[70 empty] | Risk on volume-quantity. | [29 empty] | Risk on failure of the Contractor to enforce binding construction quality practices.
[70 empty] | Unsuitable Approved Business Project or ABP cost risk. | [29 empty] | Risk on failure to adhere to MWCI and industry best practice installation standards.
Risk on failure to comply on DOLE H&S regulatory requirements.
Risk on failure to comply on fire safety and emergency evacuation on city & national ordinance requirements.
Risk on failure to enforce safety protocols on handling flammable and combustible materials.
Risk on failure to enforce the health & safety organization and mandate.
Risk on failure to implement effective construction safety meetings.
Risk on failure to implement proper management of lay down areas.
Risk on failure to implement safety in the work place.
Risk on failure to implement safety protocol on locked out tagged out.
Risk on failure to perform due diligence on pre-construction phase.
Risk on failure to properly design evacuation and emergency procedures.
Risk on incompatible systems
Risk on insufficient construction health & safety training.
Risk on machine & equipment operators without the required training certificates.
Risk on project technical issues.
Risk on the availability of approved construction heavy equipment & machineries.
Risk on the use of uncertified and unlicensed construction equipment.
Risk on workers not trained in H&S in the workplace.
[40 empty] | RISK NAMES | [59 empty] | XX | [52 empty] | xxx
Procurement.Process.Evaluation
Disposals
Scope
Design
Technology.Adoption
Quality.Systems
Cost.Estimate
Project.Timeline
Chemicals.Substance.Hazard
Flammable.Substances
Biological.Infectious.Diseases
Physical.Hazards
Manual.Tasks.Hazards
Environmental.Hazards
Psychosocial.Hazards
Company.Culture
Change.Management
Joint.Ventures
Mission.Vision
Coordination.Communication
Leadership.Issues
Resource.Optimization
Program.Services.Collaboration
Business.Continuity
Project.Concept.Strategy
Initial.Systems.Design
Initial.Scope.Budget.Time
Project.Pre_Charter.Review
Feasibility.Studies.Options
Contingency.Provisioning
Scope.Cost.Time
Project.Acceptance
Equipment.Quality.Issues
Process.Quality.Issues
Project.Change.Management
Communication
Project.Execution.Issues
Government.Stability
Employment.Operational.Laws
Government.Leadership
Trade.Restrictions.Reform
Tax.Regulations
Corruption.Levels
Bureaucracy.Issues
Stability.Neighbors
Inflation
Taxes.Duties
Finance.Credit
Working.Practices
Exchange.Rates
Cost.Living
GDP.GNP
Globalization
Lifestyle
Attitude.Beliefs
Social.Mobility
Education
Demographics
Ethics.Religion
Historical.Issues
Cross_Cultural.Communication
Rate.of.Change
Use.of.Outsourcing
Research.Development
Knowledge.Management.System
Eliminate.Bottlenecks
Network.Coverage
Production.Efficiency
Quality.Pricing
Intellectual.Property
Patents.Licenses
Government.Activity.Legislation
Taxation
Employment
Consumer
Advertising
Import.Export
Occupational.Health.Safety
Workplace.Compliance
Regulatory.Bodies
Infrastructure
Cyclical.Weather
Energy.Availability.Cost
Social.Implications
Disposal.Materials
Ecological.Consequences
Legislation
Contamination
Geographic.Location
Biohazard.Pandemic
Note on DR218: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: • Crane safety • Excavation • Mobile equipment • Confined space • Hazardous Materials Handling • Exposure to chemicals • Compressed gasses • Flammable liquids • Fall Protection • Steel erection • Cutting burning and welding • Scaffolds • Suspended workloads • Temperature extremes • Altitude • Sources of Fumes • Hydraulic systems • Explosives • Explosive Actuated tools • Radiation • Painting • Rotating and moving parts • Robotics • Control of Hazardous Energy • Rigging • Ventilation • Sanitary Facilities • Fire and Evacuation Procedures • Alarms, Sirens, Horns and Flashing Lights • Restricted Area • PPE • Traffic patterns and speed • Process hazards

## Category
PROJECT RISK CATEGORY LIST
Category1 | Category2 | Category3 | Risk.Code | Risk Name | Definition for Risk Category 3
Internal | Executive | Project.Support | IR.EXE.010 | Issues on lack of executive support on the project by the Board. | Risks associated with the failure to provide executive support to the project; project team did not receive sufficient authority to execute critical decisions.
Internal | Executive | Project.Support | IR.EXE.010 | Issues on lack of sufficient authority of the project team. | Risks associated with the failure to provide executive support to the project; project team did not receive sufficient authority to execute critical decisions.
Internal | Executive | Executive.Stakeholder.Conflicts | IR.EXE.020 | Issues on Mancom member openly against the project | Risks arising from members of executive management that are combative to the project; there is a disagreement over project issues at executive level.
Internal | Executive | Executive.Stakeholder.Conflicts | IR.EXE.020 | Mancom project issues disagreement risk. | Risks arising from members of executive management that are combative to the project; there is a disagreement over project issues at executive level.
Internal | Executive | Executive.Turnover | IR.EXE.030 | Changes in corporate leadership risk. | Risks associated with the changes in the company leadership, executives leaving the company, disruption at the leadership level.
Internal | Executive | Executive.Turnover | IR.EXE.030 | Issues on disruptions at the executive level. | Risks associated with the changes in the company leadership, executives leaving the company, disruption at the leadership level.
Internal | Executive | Executive.Turnover | IR.EXE.030 | Issues on incumbent executives leaving the company. | Risks associated with the changes in the company leadership, executives leaving the company, disruption at the leadership level.
Internal | Operation | Business.Interruption | IR.OPS.010 | Crime or vandalism risk. | Risks arising from structure fires, utility services damage, loss of electricity or running water, equipment failure, third-party disruptions, crime or vandalism, natural disasters.
Internal | Operation | Business.Interruption | IR.OPS.010 | Equipment and machine failure risk. | Risks arising from structure fires, utility services damage, loss of electricity or running water, equipment failure, third-party disruptions, crime or vandalism, natural disasters.
Internal | Operation | Business.Interruption | IR.OPS.010 | Loss of electric power supply risk. | Risks arising from structure fires, utility services damage, loss of electricity or running water, equipment failure, third-party disruptions, crime or vandalism, natural disasters.
Internal | Operation | Business.Interruption | IR.OPS.010 | Loss of potable water risk. | Risks arising from structure fires, utility services damage, loss of electricity or running water, equipment failure, third-party disruptions, crime or vandalism, natural disasters.
Internal | Operation | Business.Interruption | IR.OPS.010 | MWO building premises and structure fire risk. | Risks arising from structure fires, utility services damage, loss of electricity or running water, equipment failure, third-party disruptions, crime or vandalism, natural disasters.
Internal | Operation | Business.Interruption | IR.OPS.010 | Natural disaster risk. | Risks arising from structure fires, utility services damage, loss of electricity or running water, equipment failure, third-party disruptions, crime or vandalism, natural disasters.
Internal | Operation | Business.Interruption | IR.OPS.010 | Third-party disruption risk. | Risks arising from structure fires, utility services damage, loss of electricity or running water, equipment failure, third-party disruptions, crime or vandalism, natural disasters.
Internal | Operation | Business.Interruption | IR.OPS.010 | Utility services damage risk. | Risks arising from structure fires, utility services damage, loss of electricity or running water, equipment failure, third-party disruptions, crime or vandalism, natural disasters.
Internal | Operation | Human.Factor | IR.OPS.020 | Behavioral risk. | Risks associated with human errors in the workplace with factors such as psychological, physiological, behavioral, lapses, mistakes and violations.
Internal | Operation | Human.Factor | IR.OPS.020 | Lapses risk. | Risks associated with human errors in the workplace with factors such as psychological, physiological, behavioral, lapses, mistakes and violations.
Internal | Operation | Human.Factor | IR.OPS.020 | Mistakes risk. | Risks associated with human errors in the workplace with factors such as psychological, physiological, behavioral, lapses, mistakes and violations.
Internal | Operation | Human.Factor | IR.OPS.020 | Physiological risk. | Risks associated with human errors in the workplace with factors such as psychological, physiological, behavioral, lapses, mistakes and violations.
Internal | Operation | Human.Factor | IR.OPS.020 | Psychological risk. | Risks associated with human errors in the workplace with factors such as psychological, physiological, behavioral, lapses, mistakes and violations.
Internal | Operation | Human.Factor | IR.OPS.020 | Violations risk. | Risks associated with human errors in the workplace with factors such as psychological, physiological, behavioral, lapses, mistakes and violations.
Internal | Operation | Equipment.Failure | IR.OPS.030 | Machine component fatigue risk. | Risks associated with machine failure such as malfunction, incompatibility, intermittent failure, permanent failure, component fatigue, system failure, structural collapse, etc.
Internal | Operation | Equipment.Failure | IR.OPS.030 | Machine incompatibility risk. | Risks associated with machine failure such as malfunction, incompatibility, intermittent failure, permanent failure, component fatigue, system failure, structural collapse, etc.
Internal | Operation | Equipment.Failure | IR.OPS.030 | Machine intermittent failure risk. | Risks associated with machine failure such as malfunction, incompatibility, intermittent failure, permanent failure, component fatigue, system failure, structural collapse, etc.
Internal | Operation | Equipment.Failure | IR.OPS.030 | Machine malfunction risk. | Risks associated with machine failure such as malfunction, incompatibility, intermittent failure, permanent failure, component fatigue, system failure, structural collapse, etc.
Internal | Operation | Equipment.Failure | IR.OPS.030 | Machine permanent failure risk. | Risks associated with machine failure such as malfunction, incompatibility, intermittent failure, permanent failure, component fatigue, system failure, structural collapse, etc.
Internal | Operation | Equipment.Failure | IR.OPS.030 | Supporting Structure collapse risk. | Risks associated with machine failure such as malfunction, incompatibility, intermittent failure, permanent failure, component fatigue, system failure, structural collapse, etc.
Internal | Operation | Equipment.Failure | IR.OPS.030 | System failure risk. | Risks associated with machine failure such as malfunction, incompatibility, intermittent failure, permanent failure, component fatigue, system failure, structural collapse, etc.
Internal | Operation | Health.Safety | IR.OPS.040 | H&S field works risk. | Internal H&S hazard in the operational workplaces such as in the offices, field works, project sites and plants which may affect project objectives.
Internal | Operation | Health.Safety | IR.OPS.040 | H&S office premises risk. | Internal H&S hazard in the operational workplaces such as in the offices, field works, project sites and plants which may affect project objectives.
Internal | Operation | Health.Safety | IR.OPS.040 | H&S plant and warehouse premises risk. | Internal H&S hazard in the operational workplaces such as in the offices, field works, project sites and plants which may affect project objectives.
Internal | Operation | Health.Safety | IR.OPS.040 | H&S project site risk. | Internal H&S hazard in the operational workplaces such as in the offices, field works, project sites and plants which may affect project objectives.
Internal | Operation | Health.Safety | IR.OPS.040 | H&S transport and mobility risk. | Internal H&S hazard in the operational workplaces such as in the offices, field works, project sites and plants which may affect project objectives.
Internal | Operation | System.Failure | IR.OPS.050 | Network SCADA and Telemetry failure risk. | Risks associated with failure of a system or network or series of equipment with inter-dependencies; failure of automation, telemetry and SCADA system.
Internal | Operation | System.Failure | IR.OPS.050 | Plant automation failure risk. | Risks associated with failure of a system or network or series of equipment with inter-dependencies; failure of automation, telemetry and SCADA system.
Internal | Operation | System.Failure | IR.OPS.050 | UW Lift stations failure risk. | Risks associated with failure of a system or network or series of equipment with inter-dependencies; failure of automation, telemetry and SCADA system.
Internal | Operation | System.Failure | IR.OPS.050 | Water network booster failure risk. | Risks associated with failure of a system or network or series of equipment with inter-dependencies; failure of automation, telemetry and SCADA system.
Internal | Operation | System.Failure | IR.OPS.050 | Water network system valving failure risk. | Risks associated with failure of a system or network or series of equipment with inter-dependencies; failure of automation, telemetry and SCADA system.
Internal | Operation | System.Failure | IR.OPS.050 | Water reservoir filling rate failure risk. | Risks associated with failure of a system or network or series of equipment with inter-dependencies; failure of automation, telemetry and SCADA system.
Internal | Operation | System.Failure | IR.OPS.050 | Water transmission pipe failure risk. | Risks associated with failure of a system or network or series of equipment with inter-dependencies; failure of automation, telemetry and SCADA system.
Internal | Operation | Outsourcing | IR.OPS.060 | Outsourcing engineering consultant firm/entity risk. | Risks associated with outsourced talents, workforce, specialists and consultants)
Internal | Operation | Outsourcing | IR.OPS.060 | Outsourcing minor works specialist vendors or contractors risk | Risks associated with outsourced talents, workforce, specialists and consultants)
Internal | Operation | Outsourcing | IR.OPS.060 | Outsourcing specialist and expert matter consultant risk. | Risks associated with outsourced talents, workforce, specialists and consultants)
Internal | Operation | Outsourcing | IR.OPS.060 | Outsourcing student internship (OJT) program risk. | Risks associated with outsourced talents, workforce, specialists and consultants)
Internal | Operation | Outsourcing | IR.OPS.060 | Outsourcing temporary rank and file staff risk. | Risks associated with outsourced talents, workforce, specialists and consultants)
Internal | Operation | Insufficient.Process | IR.OPS.070 | Issues on deep data, metrics and analytics on performance measurement | Risks associated with a process employed that is not meeting the required performance or output.
Internal | Operation | Insufficient.Process | IR.OPS.070 | Issues on IT & Data Network process. | Risks associated with a process employed that is not meeting the required performance or output.
Internal | Operation | Insufficient.Process | IR.OPS.070 | Issues on plant and production processes. | Risks associated with a process employed that is not meeting the required performance or output.
Internal | Operation | Insufficient.Process | IR.OPS.070 | Issues on process employed on SCADA & Telemetry. | Risks associated with a process employed that is not meeting the required performance or output.
Internal | Operation | Insufficient.Process | IR.OPS.070 | Issues on quality management process system. | Risks associated with a process employed that is not meeting the required performance or output.
Internal | Operation | Process.Failure | IR.OPS.080 | Construction process failure risk. | Risks associated with the failure of a process such as in construction methodology and plant processes.
Internal | Operation | Process.Failure | IR.OPS.080 | IT & Data Network process failure risk. | Risks associated with the failure of a process such as in construction methodology and plant processes.
Internal | Operation | Process.Failure | IR.OPS.080 | Plant process failure risk. | Risks associated with the failure of a process such as in construction methodology and plant processes.
Internal | Operation | Process.Failure | IR.OPS.080 | SCADA & Telemetry process failure risk. | Risks associated with the failure of a process such as in construction methodology and plant processes.
Internal | Operation | System.Quality | IR.OPS.090 | Construction quality management failure risk. | Risks associated with the failure of quality process in project sites or plant, failure to implement project controls and project management systems.
Internal | Operation | System.Quality | IR.OPS.090 | Plant quality management failure risk. | Risks associated with the failure of quality process in project sites or plant, failure to implement project controls and project management systems.
Internal | Operation | System.Quality | IR.OPS.090 | Project control & monitoring failure risk. | Risks associated with the failure of quality process in project sites or plant, failure to implement project controls and project management systems.
Internal | Operation | System.Quality | IR.OPS.090 | Project management failure risk. | Risks associated with the failure of quality process in project sites or plant, failure to implement project controls and project management systems.
Internal | Human.Resource | Strategic | IR.HR.010 | Ethical issues at executive level risk. | People-related issues that limit the ability to achieve strategic objectives. Key Sub-Areas: Talent Management and Succession, Planning, Ethics and Tone at the Top, Alignment of Pay and Performance.
Internal | Human.Resource | Strategic | IR.HR.010 | Issues & challenges on on talent planning. | People-related issues that limit the ability to achieve strategic objectives. Key Sub-Areas: Talent Management and Succession, Planning, Ethics and Tone at the Top, Alignment of Pay and Performance.
Internal | Human.Resource | Strategic | IR.HR.010 | Issues on compensation package | People-related issues that limit the ability to achieve strategic objectives. Key Sub-Areas: Talent Management and Succession, Planning, Ethics and Tone at the Top, Alignment of Pay and Performance.
Internal | Human.Resource | Strategic | IR.HR.010 | Issues on talent performance | People-related issues that limit the ability to achieve strategic objectives. Key Sub-Areas: Talent Management and Succession, Planning, Ethics and Tone at the Top, Alignment of Pay and Performance.
Internal | Human.Resource | Strategic | IR.HR.010 | Talent management risk. | People-related issues that limit the ability to achieve strategic objectives. Key Sub-Areas: Talent Management and Succession, Planning, Ethics and Tone at the Top, Alignment of Pay and Performance.
Internal | Human.Resource | Strategic | IR.HR.010 | Talent succession risk. | People-related issues that limit the ability to achieve strategic objectives. Key Sub-Areas: Talent Management and Succession, Planning, Ethics and Tone at the Top, Alignment of Pay and Performance.
Internal | Human.Resource | Strategic | IR.HR.010 | Tone at the top risk. | People-related issues that limit the ability to achieve strategic objectives. Key Sub-Areas: Talent Management and Succession, Planning, Ethics and Tone at the Top, Alignment of Pay and Performance.
Internal | Human.Resource | Compliance | IR.HR.020 | Issues with DOLE regulatory compliance | Processes/controls to keep a company out of trouble. Note that reducing these risks has little bearing on being able to make the business better. Key Sub-Areas: Regulatory compliance, Fraud, Monitoring regulatory changes.
Internal | Human.Resource | Compliance | IR.HR.020 | Issues with LGU particular or special provisions labor code compliance | Processes/controls to keep a company out of trouble. Note that reducing these risks has little bearing on being able to make the business better. Key Sub-Areas: Regulatory compliance, Fraud, Monitoring regulatory changes.
Internal | Human.Resource | Compliance | IR.HR.020 | Labor code regulation changes risk. | Processes/controls to keep a company out of trouble. Note that reducing these risks has little bearing on being able to make the business better. Key Sub-Areas: Regulatory compliance, Fraud, Monitoring regulatory changes.
Internal | Human.Resource | Compliance | IR.HR.020 | Talent regularization issues. | Processes/controls to keep a company out of trouble. Note that reducing these risks has little bearing on being able to make the business better. Key Sub-Areas: Regulatory compliance, Fraud, Monitoring regulatory changes.
Internal | Human.Resource | Operational | IR.HR.030 | HR internal controls risk. | Operational (Meeting organizational objectives through effective/efficient use of human resources. Key Sub-Areas: Internal controls, Policies and procedures, Resource vendor management and sourcing, Employee training and development.
Internal | Human.Resource | Operational | IR.HR.030 | HR policies and procedure risk. | Operational (Meeting organizational objectives through effective/efficient use of human resources. Key Sub-Areas: Internal controls, Policies and procedures, Resource vendor management and sourcing, Employee training and development.
Internal | Human.Resource | Operational | IR.HR.030 | HR resource vendor management risk. | Operational (Meeting organizational objectives through effective/efficient use of human resources. Key Sub-Areas: Internal controls, Policies and procedures, Resource vendor management and sourcing, Employee training and development.
Internal | Human.Resource | Operational | IR.HR.030 | HR talent sourcing risk. | Operational (Meeting organizational objectives through effective/efficient use of human resources. Key Sub-Areas: Internal controls, Policies and procedures, Resource vendor management and sourcing, Employee training and development.
Internal | Human.Resource | Operational | IR.HR.030 | HR talent training and development risk. | Operational (Meeting organizational objectives through effective/efficient use of human resources. Key Sub-Areas: Internal controls, Policies and procedures, Resource vendor management and sourcing, Employee training and development.
Internal | Human.Resource | Financial | IR.HR.040 | Compensation and salary risk. | Global organizations view this, along with compliance, as the most traditional categories of risk. Key Sub-Areas: Equity/incentive compensation, Financial accounting and disclosure, HR performance metrics and cost management.
Internal | Human.Resource | Financial | IR.HR.040 | Equity and incentive package. | Global organizations view this, along with compliance, as the most traditional categories of risk. Key Sub-Areas: Equity/incentive compensation, Financial accounting and disclosure, HR performance metrics and cost management.
Internal | Human.Resource | Financial | IR.HR.040 | HR cost management | Global organizations view this, along with compliance, as the most traditional categories of risk. Key Sub-Areas: Equity/incentive compensation, Financial accounting and disclosure, HR performance metrics and cost management.
Internal | Human.Resource | Financial | IR.HR.040 | HR financial accounting and disclosure risk. | Global organizations view this, along with compliance, as the most traditional categories of risk. Key Sub-Areas: Equity/incentive compensation, Financial accounting and disclosure, HR performance metrics and cost management.
Internal | Human.Resource | Financial | IR.HR.040 | HR performance metrics | Global organizations view this, along with compliance, as the most traditional categories of risk. Key Sub-Areas: Equity/incentive compensation, Financial accounting and disclosure, HR performance metrics and cost management.
Internal | Procurement | Needs.Analysis.Planning | IR.PRO.010 | Impractical timeframe risk. | Risks arising from project statement, user needs, funding, timeframe and probity.
Internal | Procurement | Needs.Analysis.Planning | IR.PRO.010 | Insufficient funding risk. | Risks arising from project statement, user needs, funding, timeframe and probity.
Internal | Procurement | Needs.Analysis.Planning | IR.PRO.010 | Needs overstatement risk. | Risks arising from project statement, user needs, funding, timeframe and probity.
Internal | Procurement | Needs.Analysis.Planning | IR.PRO.010 | Needs understatement risk. | Risks arising from project statement, user needs, funding, timeframe and probity.
Internal | Procurement | Needs.Analysis.Planning | IR.PRO.010 | Probity issues. | Risks arising from project statement, user needs, funding, timeframe and probity.
Internal | Procurement | Needs.Analysis.Planning | IR.PRO.010 | User needs misinterpretation risk. | Risks arising from project statement, user needs, funding, timeframe and probity.
Internal | Procurement | Specifications | IR.PRO.020 | Biased specification specification. | Developing the Specification (Risks associated with product or systems specification, project definition, statement of requirements.
Internal | Procurement | Specifications | IR.PRO.020 | Definition of inappropriate product or service risk. | Developing the Specification (Risks associated with product or systems specification, project definition, statement of requirements.
Internal | Procurement | Specifications | IR.PRO.020 | Inadequate statement of requirements risk. | Developing the Specification (Risks associated with product or systems specification, project definition, statement of requirements.
Internal | Procurement | Specifications | IR.PRO.020 | Narrow definition or brand model partisan risk. | Developing the Specification (Risks associated with product or systems specification, project definition, statement of requirements.
Internal | Procurement | Purchasing.Method | IR.PRO.030 | Failure to identify potential sources risk. | Selecting the Purchasing Method creates Risks in failure to identify potential sources and selecting procurement method.
Internal | Procurement | Purchasing.Method | IR.PRO.030 | Selecting inappropriate method risk. | Selecting the Purchasing Method creates Risks in failure to identify potential sources and selecting procurement method.
Internal | Procurement | Purchasing.Documentation | IR.PRO.040 | Bid documents not acceptable risk | Purchasing Documentation Risks arising from unacceptable Terms and Conditions and inadequate project information.
Internal | Procurement | Purchasing.Documentation | IR.PRO.040 | Erroneous contract risk | Purchasing Documentation Risks arising from unacceptable Terms and Conditions and inadequate project information.
Internal | Procurement | Purchasing.Documentation | IR.PRO.040 | Issue on not enough time for Contractor/Vendor to prepare bids. | Purchasing Documentation Risks arising from unacceptable Terms and Conditions and inadequate project information.
Internal | Procurement | Purchasing.Documentation | IR.PRO.040 | Providing inadequate information risk. | Purchasing Documentation Risks arising from unacceptable Terms and Conditions and inadequate project information.
Internal | Procurement | Purchasing.Documentation | IR.PRO.040 | Risk on contract not suitable for project. | Purchasing Documentation Risks arising from unacceptable Terms and Conditions and inadequate project information.
Internal | Procurement | Purchasing.Documentation | IR.PRO.040 | Terms and conditions unacceptable to tenderers risk. | Purchasing Documentation Risks arising from unacceptable Terms and Conditions and inadequate project information.
Internal | Procurement | Purchasing.Documentation | IR.PRO.040 | TOR incomplete with loop holes risk. | Purchasing Documentation Risks arising from unacceptable Terms and Conditions and inadequate project information.
Internal | Procurement | Purchasing.Documentation | IR.PRO.040 | TOR inimical to MWO risk. | Purchasing Documentation Risks arising from unacceptable Terms and Conditions and inadequate project information.
Internal | Procurement | Inviting.Clarifying.Closing.Offers | IR.PRO.050 | Issues on tender clarifications. | Inviting, clarifying and closing offers (Risks associated with Tender bid bulletin, favoritism, breach of confidentiality, and insufficient number of bidders.
Internal | Procurement | Inviting.Clarifying.Closing.Offers | IR.PRO.050 | Risk on actual or perceived breach of confidentiality. | Inviting, clarifying and closing offers (Risks associated with Tender bid bulletin, favoritism, breach of confidentiality, and insufficient number of bidders.
Internal | Procurement | Inviting.Clarifying.Closing.Offers | IR.PRO.050 | Risk on actual or perceived favouritism in providing information. | Inviting, clarifying and closing offers (Risks associated with Tender bid bulletin, favoritism, breach of confidentiality, and insufficient number of bidders.
Internal | Procurement | Inviting.Clarifying.Closing.Offers | IR.PRO.050 | Risk on failure to adequately address enquiries from tenderers. | Inviting, clarifying and closing offers (Risks associated with Tender bid bulletin, favoritism, breach of confidentiality, and insufficient number of bidders.
Internal | Procurement | Inviting.Clarifying.Closing.Offers | IR.PRO.050 | Risk on insufficient number of accredited and qualified product vendors and suppliers | Inviting, clarifying and closing offers (Risks associated with Tender bid bulletin, favoritism, breach of confidentiality, and insufficient number of bidders.
Internal | Procurement | Inviting.Clarifying.Closing.Offers | IR.PRO.050 | Risk on insufficient number of accredited consultants | Inviting, clarifying and closing offers (Risks associated with Tender bid bulletin, favoritism, breach of confidentiality, and insufficient number of bidders.
Internal | Procurement | Inviting.Clarifying.Closing.Offers | IR.PRO.050 | Risk on insufficient number of accredited contractors. | Inviting, clarifying and closing offers (Risks associated with Tender bid bulletin, favoritism, breach of confidentiality, and insufficient number of bidders.
Internal | Procurement | Inviting.Clarifying.Closing.Offers | IR.PRO.050 | Risk on insufficient number of accredited specialists. | Inviting, clarifying and closing offers (Risks associated with Tender bid bulletin, favoritism, breach of confidentiality, and insufficient number of bidders.
Internal | Procurement | Inviting.Clarifying.Closing.Offers | IR.PRO.050 | Risk on insufficient number of responses. | Inviting, clarifying and closing offers (Risks associated with Tender bid bulletin, favoritism, breach of confidentiality, and insufficient number of bidders.
Internal | Procurement | Inviting.Clarifying.Closing.Offers | IR.PRO.050 | Risk on no response from known quality vendors or contractors. | Inviting, clarifying and closing offers (Risks associated with Tender bid bulletin, favoritism, breach of confidentiality, and insufficient number of bidders.
Internal | Procurement | Inviting.Clarifying.Closing.Offers | IR.PRO.050 | Risk on not enough contractors or vendors with sufficient project experience. | Inviting, clarifying and closing offers (Risks associated with Tender bid bulletin, favoritism, breach of confidentiality, and insufficient number of bidders.
Internal | Procurement | Inviting.Clarifying.Closing.Offers | IR.PRO.050 | Risk on too many bid bulletin and bid addenda. | Inviting, clarifying and closing offers (Risks associated with Tender bid bulletin, favoritism, breach of confidentiality, and insufficient number of bidders.
Internal | Procurement | Evaluating.Offers | IR.PRO.060 | Bid failure risk | Risks in failure to follow bidding protocol, breach of security, offers fail to meet demands and subjective decisions.
Internal | Procurement | Evaluating.Offers | IR.PRO.060 | Breaches of security risk. | Risks in failure to follow bidding protocol, breach of security, offers fail to meet demands and subjective decisions.
Internal | Procurement | Evaluating.Offers | IR.PRO.060 | Decision made on subjective grounds risk. | Risks in failure to follow bidding protocol, breach of security, offers fail to meet demands and subjective decisions.
Internal | Procurement | Evaluating.Offers | IR.PRO.060 | Failure to follow effective evaluation procedures risk. | Risks in failure to follow bidding protocol, breach of security, offers fail to meet demands and subjective decisions.
Internal | Procurement | Evaluating.Offers | IR.PRO.060 | Failure to identify a clear winner risk. | Risks in failure to follow bidding protocol, breach of security, offers fail to meet demands and subjective decisions.
Internal | Procurement | Evaluating.Offers | IR.PRO.060 | Issues on Bidders requesting for time extension on tender submission. | Risks in failure to follow bidding protocol, breach of security, offers fail to meet demands and subjective decisions.
Internal | Procurement | Evaluating.Offers | IR.PRO.060 | Issues on Tender Evaluation | Risks in failure to follow bidding protocol, breach of security, offers fail to meet demands and subjective decisions.
Internal | Procurement | Evaluating.Offers | IR.PRO.060 | Issues on Tender offers exceeding the budget. | Risks in failure to follow bidding protocol, breach of security, offers fail to meet demands and subjective decisions.
Internal | Procurement | Evaluating.Offers | IR.PRO.060 | Issues on Tender offers excessively below budget. | Risks in failure to follow bidding protocol, breach of security, offers fail to meet demands and subjective decisions.
Internal | Procurement | Evaluating.Offers | IR.PRO.060 | Offers fail to meet needs risk. | Risks in failure to follow bidding protocol, breach of security, offers fail to meet demands and subjective decisions.
Internal | Procurement | Selection.Successful.Tenderer | IR.PRO.070 | Failure on due diligence risk. | Risks associated with selecting appropriate suppliers and selecting inappropriate product or Vendor/Contractor.
Internal | Procurement | Selection.Successful.Tenderer | IR.PRO.070 | Selecting an inappropriate contractor risk. | Risks associated with selecting appropriate suppliers and selecting inappropriate product or Vendor/Contractor.
Internal | Procurement | Selection.Successful.Tenderer | IR.PRO.070 | Selecting an inappropriate supplier or vendor risk. | Risks associated with selecting appropriate suppliers and selecting inappropriate product or Vendor/Contractor.
Internal | Procurement | Selection.Successful.Tenderer | IR.PRO.070 | Selecting inappropriate product risk. | Risks associated with selecting appropriate suppliers and selecting inappropriate product or Vendor/Contractor.
Internal | Procurement | Negotiations | IR.PRO.080 | Deadlock on details of agreement risk. | Risks associated with project expectation, deadlock on details of agreement or policy, failure to secure mandatory conditions, unfair contract conditions and failure to reflect terms offered in the contract.
Internal | Procurement | Negotiations | IR.PRO.080 | Failure to reflect the terms offered and agreed in the contract risk. | Risks associated with project expectation, deadlock on details of agreement or policy, failure to secure mandatory conditions, unfair contract conditions and failure to reflect terms offered in the contract.
Internal | Procurement | Negotiations | IR.PRO.080 | Inadvertently creating a contract without the delegate’s prior approval risk. | Risks associated with project expectation, deadlock on details of agreement or policy, failure to secure mandatory conditions, unfair contract conditions and failure to reflect terms offered in the contract.
Internal | Procurement | Negotiations | IR.PRO.080 | Risk on bloated or over budget bids. | Risks associated with project expectation, deadlock on details of agreement or policy, failure to secure mandatory conditions, unfair contract conditions and failure to reflect terms offered in the contract.
Internal | Procurement | Negotiations | IR.PRO.080 | Risk on failure to secure agreement in relation to Capdev Contracts Confidentiality Policy. | Risks associated with project expectation, deadlock on details of agreement or policy, failure to secure mandatory conditions, unfair contract conditions and failure to reflect terms offered in the contract.
Internal | Procurement | Negotiations | IR.PRO.080 | Risk on failure to secure mandatory conditions. | Risks associated with project expectation, deadlock on details of agreement or policy, failure to secure mandatory conditions, unfair contract conditions and failure to reflect terms offered in the contract.
Internal | Procurement | Negotiations | IR.PRO.080 | Risk on not matching the expectations of buyer and tenderer. | Risks associated with project expectation, deadlock on details of agreement or policy, failure to secure mandatory conditions, unfair contract conditions and failure to reflect terms offered in the contract.
Internal | Procurement | Negotiations | IR.PRO.080 | Unfair or onerous requirements on the tenderer in the contract conditions risk. | Risks associated with project expectation, deadlock on details of agreement or policy, failure to secure mandatory conditions, unfair contract conditions and failure to reflect terms offered in the contract.
Internal | Procurement | Contract.Management | IR.PRO.090 | Failure to meet liabilities of third parties (eg. royalties or third party property insurance) risk. | Risks in variations, Supplier unwilling to accept contract, failure of either party to fulfill contract, inadequate contract administration, unauthorize early works, unauthorize increase in scope of works, loss of intellectual property, failure to meet liabilities of third parties, loss or damage to goods in transit, fraud and key personnel not available.
Internal | Procurement | Contract.Management | IR.PRO.090 | Fraud risk. | Risks in variations, Supplier unwilling to accept contract, failure of either party to fulfill contract, inadequate contract administration, unauthorize early works, unauthorize increase in scope of works, loss of intellectual property, failure to meet liabilities of third parties, loss or damage to goods in transit, fraud and key personnel not available.
Internal | Procurement | Contract.Management | IR.PRO.090 | Inadequately administering the contract risk. | Risks in variations, Supplier unwilling to accept contract, failure of either party to fulfill contract, inadequate contract administration, unauthorize early works, unauthorize increase in scope of works, loss of intellectual property, failure to meet liabilities of third parties, loss or damage to goods in transit, fraud and key personnel not available.
Internal | Procurement | Contract.Management | IR.PRO.090 | Issue on Supplier or Contractor unwilling to accept contract. | Risks in variations, Supplier unwilling to accept contract, failure of either party to fulfill contract, inadequate contract administration, unauthorize early works, unauthorize increase in scope of works, loss of intellectual property, failure to meet liabilities of third parties, loss or damage to goods in transit, fraud and key personnel not available.
Internal | Procurement | Contract.Management | IR.PRO.090 | Key personnel not available risk. | Risks in variations, Supplier unwilling to accept contract, failure of either party to fulfill contract, inadequate contract administration, unauthorize early works, unauthorize increase in scope of works, loss of intellectual property, failure to meet liabilities of third parties, loss or damage to goods in transit, fraud and key personnel not available.
Internal | Procurement | Contract.Management | IR.PRO.090 | Loss of intellectual property risk. | Risks in variations, Supplier unwilling to accept contract, failure of either party to fulfill contract, inadequate contract administration, unauthorize early works, unauthorize increase in scope of works, loss of intellectual property, failure to meet liabilities of third parties, loss or damage to goods in transit, fraud and key personnel not available.
Internal | Procurement | Contract.Management | IR.PRO.090 | Loss or damage to goods in transit risk. | Risks in variations, Supplier unwilling to accept contract, failure of either party to fulfill contract, inadequate contract administration, unauthorize early works, unauthorize increase in scope of works, loss of intellectual property, failure to meet liabilities of third parties, loss or damage to goods in transit, fraud and key personnel not available.
Internal | Procurement | Contract.Management | IR.PRO.090 | Risk on Contractor or Vendor started work without NTP or signed Contract. | Risks in variations, Supplier unwilling to accept contract, failure of either party to fulfill contract, inadequate contract administration, unauthorize early works, unauthorize increase in scope of works, loss of intellectual property, failure to meet liabilities of third parties, loss or damage to goods in transit, fraud and key personnel not available.
Internal | Procurement | Contract.Management | IR.PRO.090 | Risk on failure of Contractor to provide timely construction equipment and materials as per project timeline. | Risks in variations, Supplier unwilling to accept contract, failure of either party to fulfill contract, inadequate contract administration, unauthorize early works, unauthorize increase in scope of works, loss of intellectual property, failure to meet liabilities of third parties, loss or damage to goods in transit, fraud and key personnel not available.
Internal | Procurement | Contract.Management | IR.PRO.090 | Risk on failure of either party to fulfil the conditions of the contract | Risks in variations, Supplier unwilling to accept contract, failure of either party to fulfill contract, inadequate contract administration, unauthorize early works, unauthorize increase in scope of works, loss of intellectual property, failure to meet liabilities of third parties, loss or damage to goods in transit, fraud and key personnel not available.
Internal | Procurement | Contract.Management | IR.PRO.090 | Risk on failure to deliver goods on time or delayed deliveries. | Risks in variations, Supplier unwilling to accept contract, failure of either party to fulfill contract, inadequate contract administration, unauthorize early works, unauthorize increase in scope of works, loss of intellectual property, failure to meet liabilities of third parties, loss or damage to goods in transit, fraud and key personnel not available.
Internal | Procurement | Contract.Management | IR.PRO.090 | Risk on variances on delivered goods. | Risks in variations, Supplier unwilling to accept contract, failure of either party to fulfill contract, inadequate contract administration, unauthorize early works, unauthorize increase in scope of works, loss of intellectual property, failure to meet liabilities of third parties, loss or damage to goods in transit, fraud and key personnel not available.
Internal | Procurement | Contract.Management | IR.PRO.090 | Unauthorised increase in scope of work risk. | Risks in variations, Supplier unwilling to accept contract, failure of either party to fulfill contract, inadequate contract administration, unauthorize early works, unauthorize increase in scope of works, loss of intellectual property, failure to meet liabilities of third parties, loss or damage to goods in transit, fraud and key personnel not available.
Internal | Procurement | Contract.Management | IR.PRO.090 | Variations in price and foreign exchange risk. | Risks in variations, Supplier unwilling to accept contract, failure of either party to fulfill contract, inadequate contract administration, unauthorize early works, unauthorize increase in scope of works, loss of intellectual property, failure to meet liabilities of third parties, loss or damage to goods in transit, fraud and key personnel not available.
Internal | Procurement | Procurement.Process.Evaluation | IR.PRO.100 | Risk on failure to evaluate procurement and management processes. | Risks associated with failure to evaluate procurement and management processes.
Internal | Procurement | Procurement.Process.Evaluation | IR.PRO.100 | Risk on failure to identify and address problems. | Risks associated with failure to evaluate procurement and management processes.
Internal | Procurement | Disposals | IR.PRO.110 | Collusive bidding at auction risk. | Risks associated with rigged auction bidding and inadequate tender management.
Internal | Procurement | Disposals | IR.PRO.110 | Inadequate disposal tender management risk. | Risks associated with rigged auction bidding and inadequate tender management.
Internal | Engineering | Scope | IR.ENG.010 | Failure to identify project drivers risk. | Risks resulting from poor scope definition, ambiguity, unclear, over scope, under scope, scope variations, scope creep and unrelated scope.
Internal | Engineering | Scope | IR.ENG.010 | Over scope risk. | Risks resulting from poor scope definition, ambiguity, unclear, over scope, under scope, scope variations, scope creep and unrelated scope.
Internal | Engineering | Scope | IR.ENG.010 | Poor scope definition risk. | Risks resulting from poor scope definition, ambiguity, unclear, over scope, under scope, scope variations, scope creep and unrelated scope.
Internal | Engineering | Scope | IR.ENG.010 | Risk on scope not related to the project. | Risks resulting from poor scope definition, ambiguity, unclear, over scope, under scope, scope variations, scope creep and unrelated scope.
Internal | Engineering | Scope | IR.ENG.010 | Risk on strategic scope not translated to engineering scope. | Risks resulting from poor scope definition, ambiguity, unclear, over scope, under scope, scope variations, scope creep and unrelated scope.
Internal | Engineering | Scope | IR.ENG.010 | Risk on undefined or varying WBS. | Risks resulting from poor scope definition, ambiguity, unclear, over scope, under scope, scope variations, scope creep and unrelated scope.
Internal | Engineering | Scope | IR.ENG.010 | Scope creep risk. | Risks resulting from poor scope definition, ambiguity, unclear, over scope, under scope, scope variations, scope creep and unrelated scope.
Internal | Engineering | Scope | IR.ENG.010 | Scope variations risk. | Risks resulting from poor scope definition, ambiguity, unclear, over scope, under scope, scope variations, scope creep and unrelated scope.
Internal | Engineering | Scope | IR.ENG.010 | Under scope risk. | Risks resulting from poor scope definition, ambiguity, unclear, over scope, under scope, scope variations, scope creep and unrelated scope.
Internal | Engineering | Design | IR.ENG.020 | Code compliance design issues. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Constructability issues. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Design approval issues. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Design deficiency risk. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Design flaw risk. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Design not in MWO Standard risk. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Design not in MWSS Standards or MWSS TAGS risk. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Insufficient details on the design risk. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Issues in Health and Safety in Design. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Issues on delays on design and drawing production. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Issues on design on local control, plant systems coordination and SCADA. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Issues on over design of plant systems, networks and equipment. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Operational and maintenance issues. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Poor design risk. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Risk in design simulation. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Risk on design not in accord with good engineering practice. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Risk on failure to account as-built drawings in the design. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Risk on failure to establish project critical path. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Risk on failure to validate data inputs on design. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Risk on Incomplete design. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Risk on the use of partial data and information from sampling. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Design | IR.ENG.020 | Risk on using outdated or inconsistent as-built drawings in the design. | Risks resulting from poor design, design flaws, incomplete design, design deficiency, code compliance design issues, insufficient details, design not in MWCI standard, health and safety in design, constructability issues, operational & maintenance issues and failure to determine project critical path.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Construction methodology risk. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Failure to identify tie-ins risk. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Issues on executives not supporting new emerging technologies. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Issues on technology adoption not aligned with business strategy. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Risk on adopting new process technology. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Risk on adopting proprietary technology. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Risk on failure of the leadership to adopt to emerging technologies. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Risk on failure to create guidelines and policies on the new adopted technology. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Risk on failure to do due diligence before adopting new technologies. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Risk on failure to establish appropriate design criteria. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Risk on failure to establish basis of design. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Risk on failure to identify technology champion within MWO. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Risk on failure to institutionalize the adopted new technology. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Risk on failure to provide sufficient data and information in the TOR. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Risk on leadership culture towards technology adoption. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Risk on non-technical adoption risk. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Technology.Adoption | IR.ENG.030 | Risk on using outdated technology. | Risks from adopting new systems and process affecting design, procurement, construction, operation and time frame of the project; new and unproven technology.
Internal | Engineering | Quality.Systems | IR.ENG.040 | Issues on design review exercises. | Risks associated with Quality Management Systems (QMS) issues, such as project process documentation, planning, reviews and resourcing.
Internal | Engineering | Quality.Systems | IR.ENG.040 | Risk on complete failure to fulfill Quality Management Systems of project. | Risks associated with Quality Management Systems (QMS) issues, such as project process documentation, planning, reviews and resourcing.
Internal | Engineering | Quality.Systems | IR.ENG.040 | Risk on failure on live project planning. | Risks associated with Quality Management Systems (QMS) issues, such as project process documentation, planning, reviews and resourcing.
Internal | Engineering | Quality.Systems | IR.ENG.040 | Risk on failure on process documentation. | Risks associated with Quality Management Systems (QMS) issues, such as project process documentation, planning, reviews and resourcing.
Internal | Engineering | Quality.Systems | IR.ENG.040 | Risk on failure to do project reviews. | Risks associated with Quality Management Systems (QMS) issues, such as project process documentation, planning, reviews and resourcing.
Internal | Engineering | Quality.Systems | IR.ENG.040 | Risk on project resourcing. | Risks associated with Quality Management Systems (QMS) issues, such as project process documentation, planning, reviews and resourcing.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Cost escalation risk due to inflation, availability of materials and location. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Cost risk due to expediting. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Cost risk due to unaccounted environmental impact of the project. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Cost risk due to unaccounted hazardous waste removal and containment. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Engineering cost estimate higher than ABP cost risk. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Issues on project base cost estimate. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Issues on project phasing. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Lead times risk. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Mode of payment risk. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk due to failure to account insurance rate on project coverage. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on cost due to unaccounted code and regulatory compliance issues. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on cost impact caused by modifications directed by governmental authorities. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on cost impact of purchased utilities during construction. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on failure to account cost of quality assurance such as materials testing. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on failure to account provisions on difficult site access. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on failure to allocate or define terms of warranty. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on failure to identify cost on commissioning and startup costs. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on failure to include provisions on envirnmental control cost. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on failure to include provisions on safety and industrial hygiene. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on failure to provide allowances on unforeseen items. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on failure to provide cost and identify sufficient areas for easements. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on failure to provide cost on rental of heavy equipment. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on failure to provide redundancy of equipment on critical works or process. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on high cost due to construction methodology. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on insufficient or no provision on temfacil. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on non-standard items. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on project geo-political location. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on site conditions. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on specialty works. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on studies and research required during construction phase. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Risk on volume-quantity. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Cost.Estimate | IR.ENG.050 | Unsuitable Approved Business Project or ABP cost risk. | Risks arising from project cost estimates impacted by base cost, project phase, project geo-political location, volume-qty, lead times, construction methodology, mode of payment, warranties, specialty works, non-standard items and site conditions.
Internal | Engineering | Project.Timeline | IR.ENG.060 | Issues on not aligned project timelines and WBS. | Risks associated with project schedule, work breakdown schedule, etc.
Internal | Engineering | Project.Timeline | IR.ENG.060 | Risk arising from moving project timelines and schedules. | Risks associated with project schedule, work breakdown schedule, etc.
Internal | Engineering | Project.Timeline | IR.ENG.060 | Risk on incomplete project timelines. | Risks associated with project schedule, work breakdown schedule, etc.
Internal | Engineering | Project.Timeline | IR.ENG.060 | Risk on insufficient project timelines. | Risks associated with project schedule, work breakdown schedule, etc.
Internal | Engineering | Project.Timeline | IR.ENG.060 | Risk on very long project timelines. | Risks associated with project schedule, work breakdown schedule, etc.
Internal | Work.Health.Safety | Chemicals.Substance.Hazard | IR.WHS.010 | Aerially deposited lead risk | Risks arising from hazardous substances and dangerous goods, asbestos, lead and waste management
Internal | Work.Health.Safety | Chemicals.Substance.Hazard | IR.WHS.010 | Asbestos risk. | Risks arising from hazardous substances and dangerous goods, asbestos, lead and waste management
Internal | Work.Health.Safety | Chemicals.Substance.Hazard | IR.WHS.010 | Dangerous goods risk. | Risks arising from hazardous substances and dangerous goods, asbestos, lead and waste management
Internal | Work.Health.Safety | Chemicals.Substance.Hazard | IR.WHS.010 | Leaks or release in air of toxic gas risk. | Risks arising from hazardous substances and dangerous goods, asbestos, lead and waste management
Internal | Work.Health.Safety | Chemicals.Substance.Hazard | IR.WHS.010 | Waste management risk | Risks arising from hazardous substances and dangerous goods, asbestos, lead and waste management
Internal | Work.Health.Safety | Flammable.Substances | IR.WHS.020 | Risk on acetone hazards. | LPG, acetylene, methane, ethanol, petrol, acetone, resins, and thinners for their fire and explosion risks and prevention.
Internal | Work.Health.Safety | Flammable.Substances | IR.WHS.020 | Risk on acetylene hazards. | LPG, acetylene, methane, ethanol, petrol, acetone, resins, and thinners for their fire and explosion risks and prevention.
Internal | Work.Health.Safety | Flammable.Substances | IR.WHS.020 | Risk on ethanol hazards. | LPG, acetylene, methane, ethanol, petrol, acetone, resins, and thinners for their fire and explosion risks and prevention.
Internal | Work.Health.Safety | Flammable.Substances | IR.WHS.020 | Risk on handling hydro-carbon derived hazardous materials. | LPG, acetylene, methane, ethanol, petrol, acetone, resins, and thinners for their fire and explosion risks and prevention.
Internal | Work.Health.Safety | Flammable.Substances | IR.WHS.020 | Risk on hydro derivative gas accumulation from STP tanks and chambers. | LPG, acetylene, methane, ethanol, petrol, acetone, resins, and thinners for their fire and explosion risks and prevention.
Internal | Work.Health.Safety | Flammable.Substances | IR.WHS.020 | Risk on LPG hazards | LPG, acetylene, methane, ethanol, petrol, acetone, resins, and thinners for their fire and explosion risks and prevention.
Internal | Work.Health.Safety | Flammable.Substances | IR.WHS.020 | Risk on methane hazards. | LPG, acetylene, methane, ethanol, petrol, acetone, resins, and thinners for their fire and explosion risks and prevention.
Internal | Work.Health.Safety | Flammable.Substances | IR.WHS.020 | Risk on paint hazards. | LPG, acetylene, methane, ethanol, petrol, acetone, resins, and thinners for their fire and explosion risks and prevention.
Internal | Work.Health.Safety | Flammable.Substances | IR.WHS.020 | Risk on petrol hazards. | LPG, acetylene, methane, ethanol, petrol, acetone, resins, and thinners for their fire and explosion risks and prevention.
Internal | Work.Health.Safety | Flammable.Substances | IR.WHS.020 | Risk on resins hazards. | LPG, acetylene, methane, ethanol, petrol, acetone, resins, and thinners for their fire and explosion risks and prevention.
Internal | Work.Health.Safety | Flammable.Substances | IR.WHS.020 | Risk on thinners hazards. | LPG, acetylene, methane, ethanol, petrol, acetone, resins, and thinners for their fire and explosion risks and prevention.
Internal | Work.Health.Safety | Biological.Infectious.Diseases | IR.WHS.030 | Canine bite rabis infection risk. | Risks related to infectious diseases and its outbreaks such as legionella, Hendra virus, SARS, insect bites, snake bites, etc.
Internal | Work.Health.Safety | Biological.Infectious.Diseases | IR.WHS.030 | Insect bites risk | Risks related to infectious diseases and its outbreaks such as legionella, Hendra virus, SARS, insect bites, snake bites, etc.
Internal | Work.Health.Safety | Biological.Infectious.Diseases | IR.WHS.030 | Localized contagious virus risk | Risks related to infectious diseases and its outbreaks such as legionella, Hendra virus, SARS, insect bites, snake bites, etc.
Internal | Work.Health.Safety | Biological.Infectious.Diseases | IR.WHS.030 | Snake bites risk. | Risks related to infectious diseases and its outbreaks such as legionella, Hendra virus, SARS, insect bites, snake bites, etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Cold Environments risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Collision and Impact risk. | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Compressed Gases | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Confined space risk. | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Drowning risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Electrical hazard risk. | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Fires risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Hand / Arm Vibration risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Hot Environments risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Hyperbaric (High Pressure) Environments risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Hypobaric (Low Pressure) Environments risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Ionizing Radiation risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Light, Lasers risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Microwave and Radio-frequency risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Noise hazard risk. | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Non-Ionizing Radiation risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Operation of heavy equipment and machineries risk. | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Power Frequency Electromagnetic Field (ELF) risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Radiation hazard risk. | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Seismic risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Slips, Trips and Falls risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Thermal hazard risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Tools and Machines Risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Ultraviolet/Sunlight risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Ventilation Risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Whole-Body Vibration risk | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Physical.Hazards | IR.WHS.040 | Working at heights risk. | Risks arising from the operation of equipment, confined spaces, electrical hazards, working at heights, vibration, noise, radiation, pressure , etc.
Internal | Work.Health.Safety | Manual.Tasks.Hazards | IR.WHS.050 | Manual lifting hazard risk. | Risks in the use of the human body to perform any kind of manual tasks.
Internal | Work.Health.Safety | Manual.Tasks.Hazards | IR.WHS.050 | Manual works hazard risk. | Risks in the use of the human body to perform any kind of manual tasks.
Internal | Work.Health.Safety | Environmental.Hazards | IR.WHS.060 | Air quality and air pollution hazard risk. | Risks in noise, lighting, surrounding environment (including uneven floor surfaces, etc.), cold, dust and heat stress
Internal | Work.Health.Safety | Environmental.Hazards | IR.WHS.060 | Dust hazard risk. | Risks in noise, lighting, surrounding environment (including uneven floor surfaces, etc.), cold, dust and heat stress
Internal | Work.Health.Safety | Environmental.Hazards | IR.WHS.060 | Gassy or potentially gassy operations risk. | Risks in noise, lighting, surrounding environment (including uneven floor surfaces, etc.), cold, dust and heat stress
Internal | Work.Health.Safety | Environmental.Hazards | IR.WHS.060 | Lighting hazard risk. | Risks in noise, lighting, surrounding environment (including uneven floor surfaces, etc.), cold, dust and heat stress
Internal | Work.Health.Safety | Environmental.Hazards | IR.WHS.060 | Noise hazard risk. | Risks in noise, lighting, surrounding environment (including uneven floor surfaces, etc.), cold, dust and heat stress
Internal | Work.Health.Safety | Environmental.Hazards | IR.WHS.060 | Project sitea area prone to landslide risk. | Risks in noise, lighting, surrounding environment (including uneven floor surfaces, etc.), cold, dust and heat stress
Internal | Work.Health.Safety | Environmental.Hazards | IR.WHS.060 | Surrounding environment hazard risk. | Risks in noise, lighting, surrounding environment (including uneven floor surfaces, etc.), cold, dust and heat stress
Internal | Work.Health.Safety | Environmental.Hazards | IR.WHS.060 | Temperature stress risk | Risks in noise, lighting, surrounding environment (including uneven floor surfaces, etc.), cold, dust and heat stress
Internal | Work.Health.Safety | Psychosocial.Hazards | IR.WHS.070 | Fatigue hazard risk. | Risks arising from fatigue, work-related stress, workplace harassment and occupational violence.
Internal | Work.Health.Safety | Psychosocial.Hazards | IR.WHS.070 | Occupational violence risk. | Risks arising from fatigue, work-related stress, workplace harassment and occupational violence.
Internal | Work.Health.Safety | Psychosocial.Hazards | IR.WHS.070 | Workplace harassment risk. | Risks arising from fatigue, work-related stress, workplace harassment and occupational violence.
Internal | Work.Health.Safety | Psychosocial.Hazards | IR.WHS.070 | Work-related stress risk. | Risks arising from fatigue, work-related stress, workplace harassment and occupational violence.
Internal | Organization | Company.Culture | IR.ORG.010 | Risk in company culture mismatch with project undertaking. | Risks associated with the failure in mismatch between the company culture/structure/process and the project undertaking.
Internal | Organization | Company.Culture | IR.ORG.010 | Risk in company process mismatch with project undertaking. | Risks associated with the failure in mismatch between the company culture/structure/process and the project undertaking.
Internal | Organization | Company.Culture | IR.ORG.010 | Risk in company structure mismatch with project undertaking. | Risks associated with the failure in mismatch between the company culture/structure/process and the project undertaking.
Internal | Organization | Change.Management | IR.ORG.020 | Change management risk | Risks associated with changes to management or major restructuring due to merger or acquisition throwing the project into chaos.
Internal | Organization | Change.Management | IR.ORG.020 | Company major restructuring risk. | Risks associated with changes to management or major restructuring due to merger or acquisition throwing the project into chaos.
Internal | Organization | Change.Management | IR.ORG.020 | Merger & acquisition risk. | Risks associated with changes to management or major restructuring due to merger or acquisition throwing the project into chaos.
Internal | Organization | Joint.Ventures | IR.ORG.030 | Joint ventures risk. | Risks from joint venture undertakings.
Internal | Organization | Joint.Ventures | IR.ORG.030 | Undertaking risk. | Risks from joint venture undertakings.
Internal | Organization | Mission.Vision | IR.ORG.040 | Change in company mandate risk. | Risks arising from changes on company mandates, objectives and rationale.
Internal | Organization | Mission.Vision | IR.ORG.040 | Change in company objectives risk. | Risks arising from changes on company mandates, objectives and rationale.
Internal | Organization | Mission.Vision | IR.ORG.040 | Change in company rationale risk. | Risks arising from changes on company mandates, objectives and rationale.
Internal | Organization | Coordination.Communication | IR.ORG.050 | Risk on failure to establish mechanism on coordination. | Risks arising from failure to establish strategic mechanisms on coordination & communication, creating confusion and disturbances.
Internal | Organization | Coordination.Communication | IR.ORG.050 | Risk on failure to establish mechanism on corporation communication. | Risks arising from failure to establish strategic mechanisms on coordination & communication, creating confusion and disturbances.
Internal | Organization | Leadership.Issues | IR.ORG.060 | Risk on erosion of organizational authority. | Risks for failure to establish formal leadership on key positions and functions within the organization; erosion of organizational authority.
Internal | Organization | Leadership.Issues | IR.ORG.060 | Risk on failure to establish formal leadership on key functions. | Risks for failure to establish formal leadership on key positions and functions within the organization; erosion of organizational authority.
Internal | Organization | Leadership.Issues | IR.ORG.060 | Risk on failure to establish formal leadership on key positions. | Risks for failure to establish formal leadership on key positions and functions within the organization; erosion of organizational authority.
Internal | Organization | Resource.Optimization | IR.ORG.070 | Risk due to failure of resource allocation. | Risks due to failure of resource allocation and resource optimization.
Internal | Organization | Resource.Optimization | IR.ORG.070 | Risk due to failure of resource optimization. | Risks due to failure of resource allocation and resource optimization.
Internal | Organization | Program.Services.Collaboration | IR.ORG.080 | Insufficient cooperation between programme and services level risk. | Risks for failure to achieve outcome due to lack or insufficient cooperation between programme level and services level initiatives.
Internal | Organization | Program.Services.Collaboration | IR.ORG.080 | Risk for failure to achieve outcome due to poor collaboration. | Risks for failure to achieve outcome due to lack or insufficient cooperation between programme level and services level initiatives.
Internal | Organization | Business.Continuity | IR.ORG.090 | Risk due to issues on contingency plans. | Risks arising from the Organization’s failure to identify and formulate policies for business continuity efforts such as resiliency, recovery time and contingency plan.
Internal | Organization | Business.Continuity | IR.ORG.090 | Risk due to lack or resiliency. | Risks arising from the Organization’s failure to identify and formulate policies for business continuity efforts such as resiliency, recovery time and contingency plan.
Internal | Organization | Business.Continuity | IR.ORG.090 | Risk due to recovery time issues. | Risks arising from the Organization’s failure to identify and formulate policies for business continuity efforts such as resiliency, recovery time and contingency plan.
Internal | Organization | Business.Continuity | IR.ORG.090 | Risk on failure to formulate policies on business continuity. | Risks arising from the Organization’s failure to identify and formulate policies for business continuity efforts such as resiliency, recovery time and contingency plan.
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Budget limitation risk | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Community opposition risk. | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Cost risk. | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Environmental risk. | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Governance and Regulation risk. | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | HOA MOA issues | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Inadequate or wrong assumptions risk | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Inadequate Planning Risk | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Issues on failure to exhaust all areas of potential impact. | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Issues on technical pre-works | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | LGU permits risk | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Limited available real estate risk | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | MMDA permits risk | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | New emerging technology risk | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | NGA certification issuance risk | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Operational Risk. | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Proprietary technology risk | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Public health illness risk. | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Public health process related risk. | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Reputation risk. | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | ROW issues | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Safety risk. | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Site acquisition risk | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Technology adaption risk | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Project.Concept.Strategy | IR.STR.010 | Water source risk | Risks associated with project concept, projects with accepted inherent risks
Internal | Strategy | Initial.Systems.Design | IR.STR.020 | Risk on errors on simulation. | Risks associated with erroneous initial designs without proper basis or filled with unfounded assumptions.
Internal | Strategy | Initial.Systems.Design | IR.STR.020 | Risk on initial design due to unaccounted regulatory requirements. | Risks associated with erroneous initial designs without proper basis or filled with unfounded assumptions.
Internal | Strategy | Initial.Systems.Design | IR.STR.020 | Risk on initial designs based on unfounded assumptions. | Risks associated with erroneous initial designs without proper basis or filled with unfounded assumptions.
Internal | Strategy | Initial.Systems.Design | IR.STR.020 | Risk on initial designs without proper basis. | Risks associated with erroneous initial designs without proper basis or filled with unfounded assumptions.
Internal | Strategy | Initial.Systems.Design | IR.STR.020 | Risk on initial plant sizing due to inconsistent load requirement analysis. | Risks associated with erroneous initial designs without proper basis or filled with unfounded assumptions.
Internal | Strategy | Initial.Systems.Design | IR.STR.020 | Risk on initial plant sizing due to inconsistent water source analysis. | Risks associated with erroneous initial designs without proper basis or filled with unfounded assumptions.
Internal | Strategy | Initial.Systems.Design | IR.STR.020 | Risk on over design of plant and systems. | Risks associated with erroneous initial designs without proper basis or filled with unfounded assumptions.
Internal | Strategy | Initial.Systems.Design | IR.STR.020 | Risk on system sizing due to over population. | Risks associated with erroneous initial designs without proper basis or filled with unfounded assumptions.
Internal | Strategy | Initial.Systems.Design | IR.STR.020 | Risk on system sizing due to under population. | Risks associated with erroneous initial designs without proper basis or filled with unfounded assumptions.
Internal | Strategy | Initial.Systems.Design | IR.STR.020 | Risk on the issues of data accuracy on water demand projection. | Risks associated with erroneous initial designs without proper basis or filled with unfounded assumptions.
Internal | Strategy | Initial.Systems.Design | IR.STR.020 | Risk on using wrong models. | Risks associated with erroneous initial designs without proper basis or filled with unfounded assumptions.
Internal | Strategy | Initial.Scope.Budget.Time | IR.STR.030 | Risk on intial project budgetary cost. | Risks resulting from issues on project initial scoping, budgeting and scheduling.
Internal | Strategy | Initial.Scope.Budget.Time | IR.STR.030 | Risk on intial project schedule and timeline. | Risks resulting from issues on project initial scoping, budgeting and scheduling.
Internal | Strategy | Initial.Scope.Budget.Time | IR.STR.030 | Risk on intial project scope, budget, schedule and timeline. | Risks resulting from issues on project initial scoping, budgeting and scheduling.
Internal | Strategy | Initial.Scope.Budget.Time | IR.STR.030 | Risk on intial project scoping. | Risks resulting from issues on project initial scoping, budgeting and scheduling.
Internal | Strategy | Project.Pre_Charter.Review | IR.STR.040 | Issues on project pre-charter review document missing or undocumented. | Risks associated with projects at its early stage Gate 0 without conducting a proper value assurance review.
Internal | Strategy | Project.Pre_Charter.Review | IR.STR.040 | Risk on project benefits not properly articulated or not documented. | Risks associated with projects at its early stage Gate 0 without conducting a proper value assurance review.
Internal | Strategy | Project.Pre_Charter.Review | IR.STR.040 | Risk on project pre-charter review not conducted. | Risks associated with projects at its early stage Gate 0 without conducting a proper value assurance review.
Internal | Strategy | Feasibility.Studies.Options | IR.STR.050 | Risk on errors in simulation. | Risks arising from lack of feasibility studies, or studies with full of errors, wrong assumptions and poor strategy.
Internal | Strategy | Feasibility.Studies.Options | IR.STR.050 | Risk on project with erroneous feasibility study report. | Risks arising from lack of feasibility studies, or studies with full of errors, wrong assumptions and poor strategy.
Internal | Strategy | Feasibility.Studies.Options | IR.STR.050 | Risk on project with feasibility studies having insufficient options. | Risks arising from lack of feasibility studies, or studies with full of errors, wrong assumptions and poor strategy.
Internal | Strategy | Feasibility.Studies.Options | IR.STR.050 | Risk on project with feasibility studies having poor strategies. | Risks arising from lack of feasibility studies, or studies with full of errors, wrong assumptions and poor strategy.
Internal | Strategy | Feasibility.Studies.Options | IR.STR.050 | Risk on project with feasibility studies using unfounded assumptions. | Risks arising from lack of feasibility studies, or studies with full of errors, wrong assumptions and poor strategy.
Internal | Strategy | Feasibility.Studies.Options | IR.STR.050 | Risk on project without feasibility studies. | Risks arising from lack of feasibility studies, or studies with full of errors, wrong assumptions and poor strategy.
Internal | Strategy | Feasibility.Studies.Options | IR.STR.050 | Risk on using wrong models. | Risks arising from lack of feasibility studies, or studies with full of errors, wrong assumptions and poor strategy.
Internal | Strategy | Contingency.Provisioning | IR.STR.060 | Risk on project with inadequate provision for contingency cost. | Risks due to lack of contingency provision or misguided contingency.
Internal | Strategy | Contingency.Provisioning | IR.STR.060 | Risk on project without provision for contingency cost. | Risks due to lack of contingency provision or misguided contingency.
Internal | Strategy | Contingency.Provisioning | IR.STR.060 | Unfounded provisioning for contingency risk. | Risks due to lack of contingency provision or misguided contingency.
Internal | PQM | Scope.Cost.Time | IR.PQM.010 | Risk on cost changes | Risks due to issues on project management scope, cost and time changes or variations that are unplanned and unrestrained affecting the project objectives.
Internal | PQM | Scope.Cost.Time | IR.PQM.010 | Risk on schedule changes | Risks due to issues on project management scope, cost and time changes or variations that are unplanned and unrestrained affecting the project objectives.
Internal | PQM | Scope.Cost.Time | IR.PQM.010 | Risk on scope changes. | Risks due to issues on project management scope, cost and time changes or variations that are unplanned and unrestrained affecting the project objectives.
Internal | PQM | Scope.Cost.Time | IR.PQM.010 | Risk on unplanned time extension | Risks due to issues on project management scope, cost and time changes or variations that are unplanned and unrestrained affecting the project objectives.
Internal | PQM | Scope.Cost.Time | IR.PQM.010 | Risk on unplanned variation order | Risks due to issues on project management scope, cost and time changes or variations that are unplanned and unrestrained affecting the project objectives.
Internal | PQM | Scope.Cost.Time | IR.PQM.010 | Risk on unrestrained cost escalation | Risks due to issues on project management scope, cost and time changes or variations that are unplanned and unrestrained affecting the project objectives.
Internal | PQM | Scope.Cost.Time | IR.PQM.010 | Risk on unrestrained project schedule delays | Risks due to issues on project management scope, cost and time changes or variations that are unplanned and unrestrained affecting the project objectives.
Internal | PQM | Project.Acceptance | IR.PQM.020 | Issues on incomplete systems and tie-ups | Risks due to project acceptance issues such as non-conformance, plant performance deficiencies, unresolved punch list, etc., which will greatly impact project and business objectives and goals.
Internal | PQM | Project.Acceptance | IR.PQM.020 | Issues on the availability of required subject matter expert. | Risks due to project acceptance issues such as non-conformance, plant performance deficiencies, unresolved punch list, etc., which will greatly impact project and business objectives and goals.
Internal | PQM | Project.Acceptance | IR.PQM.020 | Plant performance deficiency risk. | Risks due to project acceptance issues such as non-conformance, plant performance deficiencies, unresolved punch list, etc., which will greatly impact project and business objectives and goals.
Internal | PQM | Project.Acceptance | IR.PQM.020 | Risk on mismatch on original and final project benefits. | Risks due to project acceptance issues such as non-conformance, plant performance deficiencies, unresolved punch list, etc., which will greatly impact project and business objectives and goals.
Internal | PQM | Project.Acceptance | IR.PQM.020 | Risk on plant full performance test using partial loading only. | Risks due to project acceptance issues such as non-conformance, plant performance deficiencies, unresolved punch list, etc., which will greatly impact project and business objectives and goals.
Internal | PQM | Project.Acceptance | IR.PQM.020 | Risk on plant partial system test. | Risks due to project acceptance issues such as non-conformance, plant performance deficiencies, unresolved punch list, etc., which will greatly impact project and business objectives and goals.
Internal | PQM | Project.Acceptance | IR.PQM.020 | Risk on project benefits without proper metrics. | Risks due to project acceptance issues such as non-conformance, plant performance deficiencies, unresolved punch list, etc., which will greatly impact project and business objectives and goals.
Internal | PQM | Project.Acceptance | IR.PQM.020 | Risk on system non-conformance. | Risks due to project acceptance issues such as non-conformance, plant performance deficiencies, unresolved punch list, etc., which will greatly impact project and business objectives and goals.
Internal | PQM | Project.Acceptance | IR.PQM.020 | Risk on undefined project benefits. | Risks due to project acceptance issues such as non-conformance, plant performance deficiencies, unresolved punch list, etc., which will greatly impact project and business objectives and goals.
Internal | PQM | Project.Acceptance | IR.PQM.020 | Unresolved punch list risk. | Risks due to project acceptance issues such as non-conformance, plant performance deficiencies, unresolved punch list, etc., which will greatly impact project and business objectives and goals.
Internal | PQM | Equipment.Quality.Issues | IR.PQM.030 | Change of equipment brand model issues. | Risks arising from equipment quality issues such as defective products or equipment, non-standard installation, early failures, etc., which will directly impact the project objectives.
Internal | PQM | Equipment.Quality.Issues | IR.PQM.030 | Defective product or equipment risk. | Risks arising from equipment quality issues such as defective products or equipment, non-standard installation, early failures, etc., which will directly impact the project objectives.
Internal | PQM | Equipment.Quality.Issues | IR.PQM.030 | Early failures risk. | Risks arising from equipment quality issues such as defective products or equipment, non-standard installation, early failures, etc., which will directly impact the project objectives.
Internal | PQM | Equipment.Quality.Issues | IR.PQM.030 | Issues on installed products that are not type-approved. | Risks arising from equipment quality issues such as defective products or equipment, non-standard installation, early failures, etc., which will directly impact the project objectives.
Internal | PQM | Equipment.Quality.Issues | IR.PQM.030 | Non-standard installation risk. | Risks arising from equipment quality issues such as defective products or equipment, non-standard installation, early failures, etc., which will directly impact the project objectives.
Internal | PQM | Process.Quality.Issues | IR.PQM.040 | Issues on the use and operation of new technologies. | Risks arising from plant process control system issues, unsuitable process for the type of influent properties, process not meeting regulation requirements, process input requirements not sustainable, etc.
Internal | PQM | Process.Quality.Issues | IR.PQM.040 | Plant process control system issues. | Risks arising from plant process control system issues, unsuitable process for the type of influent properties, process not meeting regulation requirements, process input requirements not sustainable, etc.
Internal | PQM | Process.Quality.Issues | IR.PQM.040 | Plant process input requirements not sustainable. | Risks arising from plant process control system issues, unsuitable process for the type of influent properties, process not meeting regulation requirements, process input requirements not sustainable, etc.
Internal | PQM | Process.Quality.Issues | IR.PQM.040 | Plant process not meeting regulation requirements risk. | Risks arising from plant process control system issues, unsuitable process for the type of influent properties, process not meeting regulation requirements, process input requirements not sustainable, etc.
Internal | PQM | Process.Quality.Issues | IR.PQM.040 | Plant, system or process performance guarantee risk. | Risks arising from plant process control system issues, unsuitable process for the type of influent properties, process not meeting regulation requirements, process input requirements not sustainable, etc.
Internal | PQM | Process.Quality.Issues | IR.PQM.040 | Process proving issues | Risks arising from plant process control system issues, unsuitable process for the type of influent properties, process not meeting regulation requirements, process input requirements not sustainable, etc.
Internal | PQM | Process.Quality.Issues | IR.PQM.040 | Unsuitable plant process issues. | Risks arising from plant process control system issues, unsuitable process for the type of influent properties, process not meeting regulation requirements, process input requirements not sustainable, etc.
Internal | PQM | Project.Change.Management | IR.PQM.050 | Change of Contractor risk. | Risks resulting from changes in the management of project such as new project manager, scale down of work forces, change of Contractor and/or vendor, etc.
Internal | PQM | Project.Change.Management | IR.PQM.050 | Change of Owner's Engineer Consultant risk. | Risks resulting from changes in the management of project such as new project manager, scale down of work forces, change of Contractor and/or vendor, etc.
Internal | PQM | Project.Change.Management | IR.PQM.050 | Change of Supplier or Vendor risk. | Risks resulting from changes in the management of project such as new project manager, scale down of work forces, change of Contractor and/or vendor, etc.
Internal | PQM | Project.Change.Management | IR.PQM.050 | New construction manager risk. | Risks resulting from changes in the management of project such as new project manager, scale down of work forces, change of Contractor and/or vendor, etc.
Internal | PQM | Project.Change.Management | IR.PQM.050 | New project manager risk. | Risks resulting from changes in the management of project such as new project manager, scale down of work forces, change of Contractor and/or vendor, etc.
Internal | PQM | Project.Change.Management | IR.PQM.050 | Scaledown of work forces risk. | Risks resulting from changes in the management of project such as new project manager, scale down of work forces, change of Contractor and/or vendor, etc.
Internal | PQM | Project.Change.Management | IR.PQM.050 | Issues on project key personnel change. | Risks resulting from changes in the management of project such as new project manager, scale down of work forces, change of Contractor and/or vendor, etc.
Internal | PQM | Communication | IR.PQM.060 | Failure to communicate critical project risk and issues. | Risks arising from poor project communication such as incomplete or unsuitable weekly project report information, failure to communicate through proper channels critical project risk and issues, failure to complete project information, unwillingness to follow project management tools
Internal | PQM | Communication | IR.PQM.060 | Failure to communicate through proper channels risk. | Risks arising from poor project communication such as incomplete or unsuitable weekly project report information, failure to communicate through proper channels critical project risk and issues, failure to complete project information, unwillingness to follow project management tools
Internal | PQM | Communication | IR.PQM.060 | Incomplete weekly project report risk. | Risks arising from poor project communication such as incomplete or unsuitable weekly project report information, failure to communicate through proper channels critical project risk and issues, failure to complete project information, unwillingness to follow project management tools
Internal | PQM | Communication | IR.PQM.060 | Poor project communication risk. | Risks arising from poor project communication such as incomplete or unsuitable weekly project report information, failure to communicate through proper channels critical project risk and issues, failure to complete project information, unwillingness to follow project management tools
Internal | PQM | Communication | IR.PQM.060 | Risk on unwilingness to follow project management tools. | Risks arising from poor project communication such as incomplete or unsuitable weekly project report information, failure to communicate through proper channels critical project risk and issues, failure to complete project information, unwillingness to follow project management tools
Internal | PQM | Communication | IR.PQM.060 | Unsuitable project report information risk. | Risks arising from poor project communication such as incomplete or unsuitable weekly project report information, failure to communicate through proper channels critical project risk and issues, failure to complete project information, unwillingness to follow project management tools
Internal | PQM | Communication | IR.PQM.060 | Project design and construction coordination issues with critical Stakeholders. | Risks arising from poor project communication such as incomplete or unsuitable weekly project report information, failure to communicate through proper channels critical project risk and issues, failure to complete project information, unwillingness to follow project management tools
Internal | PQM | Communication | IR.PQM.060 | Issues on insufficient or outdated construction progress report. | Risks arising from poor project communication such as incomplete or unsuitable weekly project report information, failure to communicate through proper channels critical project risk and issues, failure to complete project information, unwillingness to follow project management tools
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Contractor general performance issues. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on availability of construction documents and information at site. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on availability of space for construction machineries and equipment. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on civil and site development works | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on construction equipment repair and maintenance. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on construction site hazard management. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on construction site proper house keeping. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on Contractor's performance on project management. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on Electro-Mechanical systems and devices | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on equipment and systems failures during process probing. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on insuffienct manpower and skilled workers. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on laydown areas | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on manpower loading as per project schedule and WBS. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on MWO performance on project management. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on not meeting project objectives during process probing. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on not meeting the project benefits during and/or after process probing. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on project or Contractor's expatriate resopurces | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on proper strorage of construction documentation. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on roadworks safety implementations. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on Temfacil | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on temporary electrical cable installation practices. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on undocumented safety meetings. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on un-resolved construction punch lists. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Issues on workers not properly trained for the job. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Project construction schedule issues. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on Contractor's labor dispute and work strike. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on Contractor's procurement process of materials and equipment. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on damage to existing structure and facilities. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on failure of the Consultant to deliver the detailed design on time. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on failure of the Contractor to complete on time approved scheduled construction drawings. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on failure of the Contractor to enforce binding construction quality practices. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on failure to adhere to MWCI and industry best practice installation standards. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on failure to comply on DOLE H&S regulatory requirements. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on failure to comply on fire safety and emergency evacuation on city & national ordinance requirements. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on failure to enforce safety protocols on handling flammable and combustible materials. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on failure to enforce the health & safety organization and mandate. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on failure to implement effective construction safety meetings. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on failure to implement proper management of lay down areas. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on failure to implement safety in the work place. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on failure to implement safety protocol on locked out tagged out. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on failure to perform due diligence on pre-construction phase. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on failure to properly design evacuation and emergency procedures. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on incompatible systems | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on insufficient construction health & safety training. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on machine & equipment operators without the required training certificates. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on project technical issues. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on the availability of approved construction heavy equipment & machineries. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on the use of uncertified and unlicensed construction equipment. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
Internal | PQM | Project.Execution.Issues | IR.PQM.070 | Risk on workers not trained in H&S in the workplace. | Risks associated with construction or systems installation which include labor, equipment, materials, site H&S, and technical.
External | Political | Government.Stability | ER.POL.010 | Change of government risk. | Project risks from local or national level such as political war, insurgents, public unrest, change of government and election turmoil.
External | Political | Government.Stability | ER.POL.010 | Election turmoil risk. | Project risks from local or national level such as political war, insurgents, public unrest, change of government and election turmoil.
External | Political | Government.Stability | ER.POL.010 | Military movements risk | Project risks from local or national level such as political war, insurgents, public unrest, change of government and election turmoil.
External | Political | Government.Stability | ER.POL.010 | Paramilitary and insurgent movements risk. | Project risks from local or national level such as political war, insurgents, public unrest, change of government and election turmoil.
External | Political | Government.Stability | ER.POL.010 | Political war risk. | Project risks from local or national level such as political war, insurgents, public unrest, change of government and election turmoil.
External | Political | Government.Stability | ER.POL.010 | Public unrest risk. | Project risks from local or national level such as political war, insurgents, public unrest, change of government and election turmoil.
External | Political | Government.Stability | ER.POL.010 | Terrorist activities risk. | Project risks from local or national level such as political war, insurgents, public unrest, change of government and election turmoil.
External | Political | Government.Stability | ER.POL.010 | Travel restrictions risk. | Project risks from local or national level such as political war, insurgents, public unrest, change of government and election turmoil.
External | Political | Employment.Operational.Laws | ER.POL.020 | Employee wrongful termination risk. | Project risks due to changes in labor law, worker’s compensation, employment discrimination, labor relations, family and medical leave, immigration, employee benefits, social security, wrongful termination, occupational safety and health hazard, social security retirement insurance (SSS/GSIS) and minimum wage.
External | Political | Employment.Operational.Laws | ER.POL.020 | Employees benefits risk. | Project risks due to changes in labor law, worker’s compensation, employment discrimination, labor relations, family and medical leave, immigration, employee benefits, social security, wrongful termination, occupational safety and health hazard, social security retirement insurance (SSS/GSIS) and minimum wage.
External | Political | Employment.Operational.Laws | ER.POL.020 | Employment discrimination risk. | Project risks due to changes in labor law, worker’s compensation, employment discrimination, labor relations, family and medical leave, immigration, employee benefits, social security, wrongful termination, occupational safety and health hazard, social security retirement insurance (SSS/GSIS) and minimum wage.
External | Political | Employment.Operational.Laws | ER.POL.020 | Family and medical leave risk. | Project risks due to changes in labor law, worker’s compensation, employment discrimination, labor relations, family and medical leave, immigration, employee benefits, social security, wrongful termination, occupational safety and health hazard, social security retirement insurance (SSS/GSIS) and minimum wage.
External | Political | Employment.Operational.Laws | ER.POL.020 | Immigration policies risk. | Project risks due to changes in labor law, worker’s compensation, employment discrimination, labor relations, family and medical leave, immigration, employee benefits, social security, wrongful termination, occupational safety and health hazard, social security retirement insurance (SSS/GSIS) and minimum wage.
External | Political | Employment.Operational.Laws | ER.POL.020 | Issues in social security retirment insurance SSS GSIS policies. | Project risks due to changes in labor law, worker’s compensation, employment discrimination, labor relations, family and medical leave, immigration, employee benefits, social security, wrongful termination, occupational safety and health hazard, social security retirement insurance (SSS/GSIS) and minimum wage.
External | Political | Employment.Operational.Laws | ER.POL.020 | Labor relations risk. | Project risks due to changes in labor law, worker’s compensation, employment discrimination, labor relations, family and medical leave, immigration, employee benefits, social security, wrongful termination, occupational safety and health hazard, social security retirement insurance (SSS/GSIS) and minimum wage.
External | Political | Employment.Operational.Laws | ER.POL.020 | Minimum wage issues. | Project risks due to changes in labor law, worker’s compensation, employment discrimination, labor relations, family and medical leave, immigration, employee benefits, social security, wrongful termination, occupational safety and health hazard, social security retirement insurance (SSS/GSIS) and minimum wage.
External | Political | Employment.Operational.Laws | ER.POL.020 | Risk due to changes in labor law. | Project risks due to changes in labor law, worker’s compensation, employment discrimination, labor relations, family and medical leave, immigration, employee benefits, social security, wrongful termination, occupational safety and health hazard, social security retirement insurance (SSS/GSIS) and minimum wage.
External | Political | Employment.Operational.Laws | ER.POL.020 | Risk due to changes in workers compensation. | Project risks due to changes in labor law, worker’s compensation, employment discrimination, labor relations, family and medical leave, immigration, employee benefits, social security, wrongful termination, occupational safety and health hazard, social security retirement insurance (SSS/GSIS) and minimum wage.
External | Political | Employment.Operational.Laws | ER.POL.020 | Risk in occupational safety and health hazard policies. | Project risks due to changes in labor law, worker’s compensation, employment discrimination, labor relations, family and medical leave, immigration, employee benefits, social security, wrongful termination, occupational safety and health hazard, social security retirement insurance (SSS/GSIS) and minimum wage.
External | Political | Employment.Operational.Laws | ER.POL.020 | Social security issues. | Project risks due to changes in labor law, worker’s compensation, employment discrimination, labor relations, family and medical leave, immigration, employee benefits, social security, wrongful termination, occupational safety and health hazard, social security retirement insurance (SSS/GSIS) and minimum wage.
External | Political | Government.Leadership | ER.POL.030 | Issues in economic development. | Project risks arising from poor leadership in the government, national or local, e.g., failure in administrative processes, public decision making, relationships, public services and economic development.
External | Political | Government.Leadership | ER.POL.030 | Issues in public decision making. | Project risks arising from poor leadership in the government, national or local, e.g., failure in administrative processes, public decision making, relationships, public services and economic development.
External | Political | Government.Leadership | ER.POL.030 | Issues in public relationships. | Project risks arising from poor leadership in the government, national or local, e.g., failure in administrative processes, public decision making, relationships, public services and economic development.
External | Political | Government.Leadership | ER.POL.030 | Issues in public services. | Project risks arising from poor leadership in the government, national or local, e.g., failure in administrative processes, public decision making, relationships, public services and economic development.
External | Political | Government.Leadership | ER.POL.030 | Local government poor leadership risk. | Project risks arising from poor leadership in the government, national or local, e.g., failure in administrative processes, public decision making, relationships, public services and economic development.
External | Political | Government.Leadership | ER.POL.030 | National government poor leadership risk. | Project risks arising from poor leadership in the government, national or local, e.g., failure in administrative processes, public decision making, relationships, public services and economic development.
External | Political | Government.Leadership | ER.POL.030 | Risk in the failure of administrative processes. | Project risks arising from poor leadership in the government, national or local, e.g., failure in administrative processes, public decision making, relationships, public services and economic development.
External | Political | Trade.Restrictions.Reform | ER.POL.040 | Risk in the import and export rates policies. | New import/export tariff rates, trade ban, trade sanctions and trade barriers.
External | Political | Trade.Restrictions.Reform | ER.POL.040 | Risk in trade ban. | New import/export tariff rates, trade ban, trade sanctions and trade barriers.
External | Political | Trade.Restrictions.Reform | ER.POL.040 | Risk in trade barriers. | New import/export tariff rates, trade ban, trade sanctions and trade barriers.
External | Political | Trade.Restrictions.Reform | ER.POL.040 | Risk in trade sanctions. | New import/export tariff rates, trade ban, trade sanctions and trade barriers.
External | Political | Tax.Regulations | ER.POL.050 | Issues in business and income tax reforms. | Business and income tax reforms, changes in federal tax codes, laws and regulations.
External | Political | Tax.Regulations | ER.POL.050 | Issues on compliance tax risk. | Business and income tax reforms, changes in federal tax codes, laws and regulations.
External | Political | Tax.Regulations | ER.POL.050 | Issues on financial accounting tax risk. | Business and income tax reforms, changes in federal tax codes, laws and regulations.
External | Political | Tax.Regulations | ER.POL.050 | Issues on operational tax risk. | Business and income tax reforms, changes in federal tax codes, laws and regulations.
External | Political | Tax.Regulations | ER.POL.050 | Issues on portfolio tax risk. | Business and income tax reforms, changes in federal tax codes, laws and regulations.
External | Political | Tax.Regulations | ER.POL.050 | Issues on reputational tax risk. | Business and income tax reforms, changes in federal tax codes, laws and regulations.
External | Political | Tax.Regulations | ER.POL.050 | Issues on tax risk management. | Business and income tax reforms, changes in federal tax codes, laws and regulations.
External | Political | Tax.Regulations | ER.POL.050 | Issues on transactional tax risk. | Business and income tax reforms, changes in federal tax codes, laws and regulations.
External | Political | Tax.Regulations | ER.POL.050 | Risk in changes in federal tax codes, laws and regulations. | Business and income tax reforms, changes in federal tax codes, laws and regulations.
External | Political | Tax.Regulations | ER.POL.050 | Risk in non-compliance to tax laws. | Business and income tax reforms, changes in federal tax codes, laws and regulations.
External | Political | Corruption.Levels | ER.POL.060 | Issues on high local corruption level index. | National and local corruption level index is high (e.g., Corruption Perception Index CPI score, https://www.transparency.org): bribery, clientelism, embezzlement, lobbying and patronage cases are high.
External | Political | Corruption.Levels | ER.POL.060 | Issues on high national corruption level index. | National and local corruption level index is high (e.g., Corruption Perception Index CPI score, https://www.transparency.org): bribery, clientelism, embezzlement, lobbying and patronage cases are high.
External | Political | Corruption.Levels | ER.POL.060 | Risk on high bribery issues. | National and local corruption level index is high (e.g., Corruption Perception Index CPI score, https://www.transparency.org): bribery, clientelism, embezzlement, lobbying and patronage cases are high.
External | Political | Corruption.Levels | ER.POL.060 | Risk on high clientelism issues. | National and local corruption level index is high (e.g., Corruption Perception Index CPI score, https://www.transparency.org): bribery, clientelism, embezzlement, lobbying and patronage cases are high.
External | Political | Corruption.Levels | ER.POL.060 | Risk on high embezzlement issues. | National and local corruption level index is high (e.g., Corruption Perception Index CPI score, https://www.transparency.org): bribery, clientelism, embezzlement, lobbying and patronage cases are high.
External | Political | Corruption.Levels | ER.POL.060 | Risk on high lobbying issues. | National and local corruption level index is high (e.g., Corruption Perception Index CPI score, https://www.transparency.org): bribery, clientelism, embezzlement, lobbying and patronage cases are high.
External | Political | Corruption.Levels | ER.POL.060 | Risk on patronage issues. | National and local corruption level index is high (e.g., Corruption Perception Index CPI score, https://www.transparency.org): bribery, clientelism, embezzlement, lobbying and patronage cases are high.
External | Political | Bureaucracy.Issues | ER.POL.070 | Risk on conflict of interest issues. | A bureaucracy is a large organization composed of appointed officials in which authority is divided among several managers. Issues in bureaucracy are red tape, conflict, duplication, imperialism, and waste.
External | Political | Bureaucracy.Issues | ER.POL.070 | Risk on delays on the issuance of permits. | A bureaucracy is a large organization composed of appointed officials in which authority is divided among several managers. Issues in bureaucracy are red tape, conflict, duplication, imperialism, and waste.
External | Political | Bureaucracy.Issues | ER.POL.070 | Risk on delays on the processing and issuance of Government documents. | A bureaucracy is a large organization composed of appointed officials in which authority is divided among several managers. Issues in bureaucracy are red tape, conflict, duplication, imperialism, and waste.
External | Political | Bureaucracy.Issues | ER.POL.070 | Risk on duplication issues. | A bureaucracy is a large organization composed of appointed officials in which authority is divided among several managers. Issues in bureaucracy are red tape, conflict, duplication, imperialism, and waste.
External | Political | Bureaucracy.Issues | ER.POL.070 | Risk on imperialism issues. | A bureaucracy is a large organization composed of appointed officials in which authority is divided among several managers. Issues in bureaucracy are red tape, conflict, duplication, imperialism, and waste.
External | Political | Bureaucracy.Issues | ER.POL.070 | Risk on LGU/NGA approval or no objection of design and studies. | A bureaucracy is a large organization composed of appointed officials in which authority is divided among several managers. Issues in bureaucracy are red tape, conflict, duplication, imperialism, and waste.
External | Political | Bureaucracy.Issues | ER.POL.070 | Risk on red tape issues. | A bureaucracy is a large organization composed of appointed officials in which authority is divided among several managers. Issues in bureaucracy are red tape, conflict, duplication, imperialism, and waste.
External | Political | Bureaucracy.Issues | ER.POL.070 | Risk on wastage issues. | A bureaucracy is a large organization composed of appointed officials in which authority is divided among several managers. Issues in bureaucracy are red tape, conflict, duplication, imperialism, and waste.
External | Political | Stability.Neighbors | ER.POL.080 | Issues on cessation of bilateral political coordination between countries. | Project risks arising from territorial claims, cessation of bilateral political coordination between countries, processes in neighboring countries that might destabilize the region, organized international crime, and infiltration.
External | Political | Stability.Neighbors | ER.POL.080 | Issues on sovereign territorial claims. | Project risks arising from territorial claims, cessation of bilateral political coordination between countries, processes in neighboring countries that might destabilize the region, organized international crime, and infiltration.
External | Political | Stability.Neighbors | ER.POL.080 | Risk on infiltration issues. | Project risks arising from territorial claims, cessation of bilateral political coordination between countries, processes in neighboring countries that might destabilize the region, organized international crime, and infiltration.
External | Political | Stability.Neighbors | ER.POL.080 | Risk on organized international crime. | Project risks arising from territorial claims, cessation of bilateral political coordination between countries, processes in neighboring countries that might destabilize the region, organized international crime, and infiltration.
External | Political | Stability.Neighbors | ER.POL.080 | Risk on regional destabilization due to processes in neighboring countries. | Project risks arising from territorial claims, cessation of bilateral political coordination between countries, processes in neighboring countries that might destabilize the region, organized international crime, and infiltration.
External | Economic | Inflation | ER.ECO.010 | Higher borrowing cost risk. | Project risk due to changes in inflation rates (CPI, annual variation in %) based on domestic performance and the international market.
External | Economic | Inflation | ER.ECO.010 | Issues on goods competitive disadvantage. | Project risk due to changes in inflation rates (CPI, annual variation in %) based on domestic performance and the international market.
External | Economic | Inflation | ER.ECO.010 | Purchasing power risk. | Project risk due to changes in inflation rates (CPI, annual variation in %) based on domestic performance and the international market.
External | Economic | Inflation | ER.ECO.010 | Risk due to changes in inflation rates. | Project risk due to changes in inflation rates (CPI, annual variation in %) based on domestic performance and the international market.
External | Economic | Taxes.Duties | ER.ECO.020 | Issues on Customs tax and duties rates. | Tax and duty rates are long term factors affecting projects.
External | Economic | Taxes.Duties | ER.ECO.020 | Issues on tax reforms. | Tax and duty rates are long term factors affecting projects.
External | Economic | Taxes.Duties | ER.ECO.020 | Issues on VAT on import and export of goods. | Tax and duty rates are long term factors affecting projects.
External | Economic | Taxes.Duties | ER.ECO.020 | Risk on additional duties and taxes on import and export of goods. | Tax and duty rates are long term factors affecting projects.
External | Economic | Taxes.Duties | ER.ECO.020 | Risk on changes on Customs tax and duties rates. | Tax and duty rates are long term factors affecting projects.
External | Economic | Finance.Credit | ER.ECO.030 | Credit rating assessment risk. | Sources of risk factors from sources and availability of funds for projects, credit lines and institution investment policies
External | Economic | Finance.Credit | ER.ECO.030 | Institution investment policies risk. | Sources of risk factors from sources and availability of funds for projects, credit lines and institution investment policies
External | Economic | Finance.Credit | ER.ECO.030 | Issues on credit lines. | Sources of risk factors from sources and availability of funds for projects, credit lines and institution investment policies
External | Economic | Finance.Credit | ER.ECO.030 | Sources of funds risk. | Sources of risk factors from sources and availability of funds for projects, credit lines and institution investment policies
External | Economic | Working.Practices | ER.ECO.040 | Risk due to failure of human interaction and communication. | Project risks due to working practices, de-skilling, e.g., loosing jobs due to implementation of machines and automation, people don’t speak to each other to get help as much anymore as they can find solution in the web, work motivation.
External | Economic | Working.Practices | ER.ECO.040 | Risk due to work force de-skilling issues. | Project risks due to working practices, de-skilling, e.g., loosing jobs due to implementation of machines and automation, people don’t speak to each other to get help as much anymore as they can find solution in the web, work motivation.
External | Economic | Working.Practices | ER.ECO.040 | Work motivation issue. | Project risks due to working practices, de-skilling, e.g., loosing jobs due to implementation of machines and automation, people don’t speak to each other to get help as much anymore as they can find solution in the web, work motivation.
External | Economic | Exchange.Rates | ER.ECO.050 | Forex rates fluctuation risk. | Exposure to changes in foreign exchange rates fundamentally affects the project budget, and subsequently scope and schedule performances.
External | Economic | Exchange.Rates | ER.ECO.050 | Transaction exposure risk. | Exposure to changes in foreign exchange rates fundamentally affects the project budget, and subsequently scope and schedule performances.
External | Economic | Exchange.Rates | ER.ECO.050 | Translation exposure risk. | Exposure to changes in foreign exchange rates fundamentally affects the project budget, and subsequently scope and schedule performances.
External | Economic | Cost.Living | ER.ECO.060 | Risk in high cost of living. | The negative impact of high cost of living in meeting project objectives and implementation.
External | Economic | GDP.GNP | ER.ECO.070 | Risk due to GDP growth rate issues. | The impact of GDP and GNP rating in meeting project objectives and implementation.
External | Economic | GDP.GNP | ER.ECO.070 | Risk due to GNP growth rate issues. | The impact of GDP and GNP rating in meeting project objectives and implementation.
External | Economic | Globalization | ER.ECO.080 | Risk on absortive capacity on cross-cultural context. | The impact of globalized economy on managing projects: impact on project management processes, impact on absorptive (learning) capacity on cross-cultural context, impact on temporal alignment (project schedule, WBS), impact on social alignment (offshoring, co-sourcing), impact on vendor engagement.
External | Economic | Globalization | ER.ECO.080 | Risk on project management processes. | The impact of globalized economy on managing projects: impact on project management processes, impact on absorptive (learning) capacity on cross-cultural context, impact on temporal alignment (project schedule, WBS), impact on social alignment (offshoring, co-sourcing), impact on vendor engagement.
External | Economic | Globalization | ER.ECO.080 | Risk on social alignment such as offshoring and co-sourcing. | The impact of globalized economy on managing projects: impact on project management processes, impact on absorptive (learning) capacity on cross-cultural context, impact on temporal alignment (project schedule, WBS), impact on social alignment (offshoring, co-sourcing), impact on vendor engagement.
External | Economic | Globalization | ER.ECO.080 | Risk on temporal alignment such as WBS and project schedule. | The impact of globalized economy on managing projects: impact on project management processes, impact on absorptive (learning) capacity on cross-cultural context, impact on temporal alignment (project schedule, WBS), impact on social alignment (offshoring, co-sourcing), impact on vendor engagement.
External | Economic | Globalization | ER.ECO.080 | Risk on vendor engagement. | The impact of globalized economy on managing projects: impact on project management processes, impact on absorptive (learning) capacity on cross-cultural context, impact on temporal alignment (project schedule, WBS), impact on social alignment (offshoring, co-sourcing), impact on vendor engagement.
External | Social | Lifestyle | ER.SOC.010 | Risk in behavior pattern of individual or society. | A way of living of individuals or the society as a whole expressed in works and behavior patterns that impacts the project objectives.
External | Social | Lifestyle | ER.SOC.010 | Risk in changing lifestyle. | A way of living of individuals or the society as a whole expressed in works and behavior patterns that impacts the project objectives.
External | Social | Lifestyle | ER.SOC.010 | Risk in way of living of individual or society. | A way of living of individuals or the society as a whole expressed in works and behavior patterns that impacts the project objectives.
External | Social | Lifestyle | ER.SOC.010 | Risk in work values of individual or society. | A way of living of individuals or the society as a whole expressed in works and behavior patterns that impacts the project objectives.
External | Social | Attitude.Beliefs | ER.SOC.020 | Issues on community open resistance to the project. | These are assumptions and convictions a person hold to be true based on past experiences, on individual and communal level, that impact the objectives of the project.
External | Social | Attitude.Beliefs | ER.SOC.020 | Issues on personal and communal value system. | These are assumptions and convictions a person hold to be true based on past experiences, on individual and communal level, that impact the objectives of the project.
External | Social | Attitude.Beliefs | ER.SOC.020 | Risk on conflicts of beliefs. | These are assumptions and convictions a person hold to be true based on past experiences, on individual and communal level, that impact the objectives of the project.
External | Social | Attitude.Beliefs | ER.SOC.020 | Risk on diversity in society and community. | These are assumptions and convictions a person hold to be true based on past experiences, on individual and communal level, that impact the objectives of the project.
External | Social | Attitude.Beliefs | ER.SOC.020 | Risk on individual or communal assumptions and convictions. | These are assumptions and convictions a person hold to be true based on past experiences, on individual and communal level, that impact the objectives of the project.
External | Social | Attitude.Beliefs | ER.SOC.020 | Risk on norms on the society. | These are assumptions and convictions a person hold to be true based on past experiences, on individual and communal level, that impact the objectives of the project.
External | Social | Attitude.Beliefs | ER.SOC.020 | Risk on paradigm shift. | These are assumptions and convictions a person hold to be true based on past experiences, on individual and communal level, that impact the objectives of the project.
External | Social | Attitude.Beliefs | ER.SOC.020 | Risk on perceived value system. | These are assumptions and convictions a person hold to be true based on past experiences, on individual and communal level, that impact the objectives of the project.
External | Social | Attitude.Beliefs | ER.SOC.020 | Risk on public acceptance of products, goods and commodoties. | These are assumptions and convictions a person hold to be true based on past experiences, on individual and communal level, that impact the objectives of the project.
External | Social | Attitude.Beliefs | ER.SOC.020 | Risk on public acceptance of project. | These are assumptions and convictions a person hold to be true based on past experiences, on individual and communal level, that impact the objectives of the project.
External | Social | Attitude.Beliefs | ER.SOC.020 | Risk on public acceptance of services. | These are assumptions and convictions a person hold to be true based on past experiences, on individual and communal level, that impact the objectives of the project.
External | Social | Attitude.Beliefs | ER.SOC.020 | Risk on public sentiments and reactions due to community impact of the project. | These are assumptions and convictions a person hold to be true based on past experiences, on individual and communal level, that impact the objectives of the project.
External | Social | Social.Mobility | ER.SOC.030 | Risk in the change of social status relative to current social location. | It is a change in social status relative to one's current social location within a given society and may impact project objectives.
External | Social | Education | ER.SOC.040 | Risk on educational level of the community. | The education level of individual or of the society in general will have wide ranging impact on the success of project objectives.
External | Social | Education | ER.SOC.040 | Risk on the education level of available local talents and resource. | The education level of individual or of the society in general will have wide ranging impact on the success of project objectives.
External | Social | Demographics | ER.SOC.050 | Issue on the statistical characteristics of human population. | Social demographics has to do with the statistical characteristics of human population, including population density, ethnicity, education level, health, economic status, religious affiliation, etc., which may impact the success or failure of the project objectives.
External | Social | Demographics | ER.SOC.050 | Issues on economic status. | Social demographics has to do with the statistical characteristics of human population, including population density, ethnicity, education level, health, economic status, religious affiliation, etc., which may impact the success or failure of the project objectives.
External | Social | Demographics | ER.SOC.050 | Issus on religious affiliation. | Social demographics has to do with the statistical characteristics of human population, including population density, ethnicity, education level, health, economic status, religious affiliation, etc., which may impact the success or failure of the project objectives.
External | Social | Demographics | ER.SOC.050 | Risk on community health. | Social demographics has to do with the statistical characteristics of human population, including population density, ethnicity, education level, health, economic status, religious affiliation, etc., which may impact the success or failure of the project objectives.
External | Social | Demographics | ER.SOC.050 | Risk on education level. | Social demographics has to do with the statistical characteristics of human population, including population density, ethnicity, education level, health, economic status, religious affiliation, etc., which may impact the success or failure of the project objectives.
External | Social | Demographics | ER.SOC.050 | Risk on ethnicity. | Social demographics has to do with the statistical characteristics of human population, including population density, ethnicity, education level, health, economic status, religious affiliation, etc., which may impact the success or failure of the project objectives.
External | Social | Demographics | ER.SOC.050 | Risk on population density. | Social demographics has to do with the statistical characteristics of human population, including population density, ethnicity, education level, health, economic status, religious affiliation, etc., which may impact the success or failure of the project objectives.
External | Social | Ethics.Religion | ER.SOC.060 | Issues on heritage areas. | The moral belief systems and ethical values of individuals, community and society that affects the progress of the project objectives. These are expressed in the veneration of shrines, heritage areas, value systems, customs, manner and behavior transcended in the work and market places.
External | Social | Ethics.Religion | ER.SOC.060 | Issues on the veneration of shrines. | The moral belief systems and ethical values of individuals, community and society that affects the progress of the project objectives. These are expressed in the veneration of shrines, heritage areas, value systems, customs, manner and behavior transcended in the work and market places.
External | Social | Ethics.Religion | ER.SOC.060 | Risk on communal and societal customs, manner and behavior. | The moral belief systems and ethical values of individuals, community and society that affects the progress of the project objectives. These are expressed in the veneration of shrines, heritage areas, value systems, customs, manner and behavior transcended in the work and market places.
External | Social | Ethics.Religion | ER.SOC.060 | Risk on value systems. | The moral belief systems and ethical values of individuals, community and society that affects the progress of the project objectives. These are expressed in the veneration of shrines, heritage areas, value systems, customs, manner and behavior transcended in the work and market places.
External | Social | Historical.Issues | ER.SOC.070 | Issues on customs with deep historical significance. | Social historical issues mostly are related to places, customs and people that may directly or indirectly impact the project objectives.
External | Social | Historical.Issues | ER.SOC.070 | Issues on local places with historical significance. | Social historical issues mostly are related to places, customs and people that may directly or indirectly impact the project objectives.
External | Social | Historical.Issues | ER.SOC.070 | Issues on society and its history. | Social historical issues mostly are related to places, customs and people that may directly or indirectly impact the project objectives.
External | Social | Cross_Cultural.Communication | ER.SOC.080 | Issues on local dialects. | Cross-cultural communication are susceptible to mis-understanding resulting to mis-coordination and has the potential to affect the project objectives.
External | Social | Cross_Cultural.Communication | ER.SOC.080 | Issues on perceived community values and customs. | Cross-cultural communication are susceptible to mis-understanding resulting to mis-coordination and has the potential to affect the project objectives.
External | Social | Cross_Cultural.Communication | ER.SOC.080 | Risk in failure to communicate. | Cross-cultural communication are susceptible to mis-understanding resulting to mis-coordination and has the potential to affect the project objectives.
External | Social | Cross_Cultural.Communication | ER.SOC.080 | Risk on the erosion of stakeholder local engagement. | Cross-cultural communication are susceptible to mis-understanding resulting to mis-coordination and has the potential to affect the project objectives.
External | Technology | Rate.of.Change | ER.TEC.010 | Risk in the adoption of innovative technologies. | The evolving risk of emerging technologies such as adoption of new plant process, a new control and automation system, or a new chemical agent.
External | Technology | Rate.of.Change | ER.TEC.010 | Risk in the adoption of new cloud-based SCADA system. | The evolving risk of emerging technologies such as adoption of new plant process, a new control and automation system, or a new chemical agent.
External | Technology | Rate.of.Change | ER.TEC.010 | Risk in the adoption of new plant process. | The evolving risk of emerging technologies such as adoption of new plant process, a new control and automation system, or a new chemical agent.
External | Technology | Rate.of.Change | ER.TEC.010 | Risk in the use of new control and automation system. | The evolving risk of emerging technologies such as adoption of new plant process, a new control and automation system, or a new chemical agent.
External | Technology | Rate.of.Change | ER.TEC.010 | Risk in the use of new model equipment. | The evolving risk of emerging technologies such as adoption of new plant process, a new control and automation system, or a new chemical agent.
External | Technology | Rate.of.Change | ER.TEC.010 | Risk in the use of newly developed checmial agents. | The evolving risk of emerging technologies such as adoption of new plant process, a new control and automation system, or a new chemical agent.
External | Technology | Rate.of.Change | ER.TEC.010 | Risk in the use of proprietary technologies. | The evolving risk of emerging technologies such as adoption of new plant process, a new control and automation system, or a new chemical agent.
External | Technology | Use.of.Outsourcing | ER.TEC.020 | Risk in the use of external resource. | Risks associated with the use of outside or foreign supplier of goods and/or services in lieu of internal resources. Project is exposed to loss of control, loss of innovation, loss of organizational trust, and higher than expected transaction cost.
External | Technology | Use.of.Outsourcing | ER.TEC.020 | Risk in the use of foreign services. | Risks associated with the use of outside or foreign supplier of goods and/or services in lieu of internal resources. Project is exposed to loss of control, loss of innovation, loss of organizational trust, and higher than expected transaction cost.
External | Technology | Use.of.Outsourcing | ER.TEC.020 | Risk in the use of foreign supplied goods and materials. | Risks associated with the use of outside or foreign supplier of goods and/or services in lieu of internal resources. Project is exposed to loss of control, loss of innovation, loss of organizational trust, and higher than expected transaction cost.
External | Technology | Research.Development | ER.TEC.030 | Risk in the new development in R&D. | Recent trend in R&D and technology direction will have impact on project objectives.
External | Technology | Research.Development | ER.TEC.030 | Risk in the obselences of the installed plant still in its prime economic condition. | Recent trend in R&D and technology direction will have impact on project objectives.
External | Technology | Research.Development | ER.TEC.030 | Risk in the obsolences of processes due to the latest R&D global direction. | Recent trend in R&D and technology direction will have impact on project objectives.
External | Technology | Knowledge.Management.System | ER.TEC.040 | Risk in inefficiency due to the ineffective management system. | Development or the lack of it in management system will have direct or indirect impact on project objectives. Knowledge-based management system based on old paradigm may not be suitable on new frontier projects; aggressive adoption of new management system may create confusion and gaps resulting in inefficiency with the end result of affecting the project objectives.
External | Technology | Knowledge.Management.System | ER.TEC.040 | Risk in the adoption of unsuitable management system. | Development or the lack of it in management system will have direct or indirect impact on project objectives. Knowledge-based management system based on old paradigm may not be suitable on new frontier projects; aggressive adoption of new management system may create confusion and gaps resulting in inefficiency with the end result of affecting the project objectives.
External | Technology | Knowledge.Management.System | ER.TEC.040 | Risk in the aggressive adoption of new management system. | Development or the lack of it in management system will have direct or indirect impact on project objectives. Knowledge-based management system based on old paradigm may not be suitable on new frontier projects; aggressive adoption of new management system may create confusion and gaps resulting in inefficiency with the end result of affecting the project objectives.
External | Technology | Knowledge.Management.System | ER.TEC.040 | Risk in the use of obsolete project management system. | Development or the lack of it in management system will have direct or indirect impact on project objectives. Knowledge-based management system based on old paradigm may not be suitable on new frontier projects; aggressive adoption of new management system may create confusion and gaps resulting in inefficiency with the end result of affecting the project objectives.
External | Technology | Eliminate.Bottlenecks | ER.TEC.050 | Risk in the use of technology in removing bottlenecks. | Risks associated in the use of technology in removing bottlenecks and improving business processes.
External | Technology | Eliminate.Bottlenecks | ER.TEC.050 | Risk in the use of technology to improve business processes. | Risks associated in the use of technology in removing bottlenecks and improving business processes.
External | Technology | Network.Coverage | ER.TEC.060 | Risk due to network communication availability. | Risks associated with the availability and quality of communication network coverage for cloud-based solution impacting the project objectives.
External | Technology | Network.Coverage | ER.TEC.060 | Issues on internet bandwidth availability. | Risks associated with the availability and quality of communication network coverage for cloud-based solution impacting the project objectives.
External | Technology | Network.Coverage | ER.TEC.060 | Risk on GSM coverage at remote project site. | Risks associated with the availability and quality of communication network coverage for cloud-based solution impacting the project objectives.
External | Technology | Production.Efficiency | ER.TEC.070 | Risk on the use of technology on systems and processes. | Risks associated with the implementation of systems and processes affecting production efficiencies that will impact the project objectives.
External | Technology | Production.Efficiency | ER.TEC.070 | Risk on technologies affecting efficiencies and production. | Risks associated with the implementation of systems and processes affecting production efficiencies that will impact the project objectives.
External | Technology | Quality.Pricing | ER.TEC.080 | Risk on the cost of technology. | The quality and pricing of technology devices, systems and processes will have an impact on the project objectives, e.g., risk of getting inferior products on a very highly competitive, unregulated and disruptive market.
External | Technology | Quality.Pricing | ER.TEC.080 | Risk on the quality of technological equipment. | The quality and pricing of technology devices, systems and processes will have an impact on the project objectives, e.g., risk of getting inferior products on a very highly competitive, unregulated and disruptive market.
External | Technology | Quality.Pricing | ER.TEC.080 | Risk on the quality of technology process and systems. | The quality and pricing of technology devices, systems and processes will have an impact on the project objectives, e.g., risk of getting inferior products on a very highly competitive, unregulated and disruptive market.
External | Technology | Quality.Pricing | ER.TEC.080 | Issues on using inferior products | The quality and pricing of technology devices, systems and processes will have an impact on the project objectives, e.g., risk of getting inferior products on a very highly competitive, unregulated and disruptive market.
External | Technology | Quality.Pricing | ER.TEC.080 | Risk on disruptive market technology. | The quality and pricing of technology devices, systems and processes will have an impact on the project objectives, e.g., risk of getting inferior products on a very highly competitive, unregulated and disruptive market.
External | Technology | Intellectual.Property | ER.TEC.090 | Risk on infringement. | Risks associated with issues on IP affecting the project objectives; e.g., infringement on intellectual property.
External | Technology | Intellectual.Property | ER.TEC.090 | Risk on intellectual property rights. | Risks associated with issues on IP affecting the project objectives; e.g., infringement on intellectual property.
External | Technology | Patents.Licenses | ER.TEC.100 | Risk on using patented products. | Risks associated with patents and licenses affecting the business objectives, e.g. expired government-issues license to operate.
External | Technology | Patents.Licenses | ER.TEC.100 | Risk on using patented process. | Risks associated with patents and licenses affecting the business objectives, e.g. expired government-issues license to operate.
External | Technology | Patents.Licenses | ER.TEC.100 | Risk on using patented systems. | Risks associated with patents and licenses affecting the business objectives, e.g. expired government-issues license to operate.
External | Technology | Patents.Licenses | ER.TEC.100 | Risk on using expired government-issued license. | Risks associated with patents and licenses affecting the business objectives, e.g. expired government-issues license to operate.
External | Technology | Government.Activity.Legislation | ER.TEC.110 | Risk on Government lack of technology and systems innovation. | Risks associated with Government initiatives, or the lack of it, on innovation, cybercrime, license regulation, adoption of new systems and technologies that will impact the project objectives.
External | Technology | Government.Activity.Legislation | ER.TEC.110 | Risk on Government initiative on cybercrime. | Risks associated with Government initiatives, or the lack of it, on innovation, cybercrime, license regulation, adoption of new systems and technologies that will impact the project objectives.
External | Technology | Government.Activity.Legislation | ER.TEC.110 | Risk on Government license regulation. | Risks associated with Government initiatives, or the lack of it, on innovation, cybercrime, license regulation, adoption of new systems and technologies that will impact the project objectives.
External | Technology | Government.Activity.Legislation | ER.TEC.110 | Risk on Government adoption on new systems. | Risks associated with Government initiatives, or the lack of it, on innovation, cybercrime, license regulation, adoption of new systems and technologies that will impact the project objectives.
External | Technology | Government.Activity.Legislation | ER.TEC.110 | Risk on Government adoption on new technologies. | Risks associated with Government initiatives, or the lack of it, on innovation, cybercrime, license regulation, adoption of new systems and technologies that will impact the project objectives.
External | Legal | Taxation | ER.LEG.010 | Risk on legal issues on tax framework for water utility services. | Legal issues on taxation of business and projects, e.g., tax framework for Internet use, taxation for highly regulated utility product and services such as water distribution.
External | Legal | Taxation | ER.LEG.010 | Risk on legal issues on tax framework on PPP portfolio projects. | Legal issues on taxation of business and projects, e.g., tax framework for Internet use, taxation for highly regulated utility product and services such as water distribution.
External | Legal | Employment | ER.LEG.020 | Risk on legal issue on use of social media in the workplace. | Legal issues on employment policies and laws, its implication affecting the nature of the business and project objectives; e.g., employee use of social media, marijuana in the work place, independent contractors/consultants.
External | Legal | Employment | ER.LEG.020 | Risk on legal issue on the use of substance in the workplace. | Legal issues on employment policies and laws, its implication affecting the nature of the business and project objectives; e.g., employee use of social media, marijuana in the work place, independent contractors/consultants.
External | Legal | Consumer | ER.LEG.030 | Risk on legal issue on the public use of MWO water supply. | Legal issues arising from the use of and consumption of product and services rendered by the Entity which will impact project objectives; e.g. consumer fraud issues, product safety and defects, personal injuries resulting from dangerous or defective products, false advertising and deceptive business practices.
External | Legal | Consumer | ER.LEG.030 | Risk on legal issue of consumer fraud. | Legal issues arising from the use of and consumption of product and services rendered by the Entity which will impact project objectives; e.g. consumer fraud issues, product safety and defects, personal injuries resulting from dangerous or defective products, false advertising and deceptive business practices.
External | Legal | Consumer | ER.LEG.030 | Risk on legal issue on product safety and defects. | Legal issues arising from the use of and consumption of product and services rendered by the Entity which will impact project objectives; e.g. consumer fraud issues, product safety and defects, personal injuries resulting from dangerous or defective products, false advertising and deceptive business practices.
External | Legal | Consumer | ER.LEG.030 | Risk on legal issue on personal injuries resulting from the use of contaminated water. | Legal issues arising from the use of and consumption of product and services rendered by the Entity which will impact project objectives; e.g. consumer fraud issues, product safety and defects, personal injuries resulting from dangerous or defective products, false advertising and deceptive business practices.
External | Legal | Consumer | ER.LEG.030 | Risk on legal issue on falsified advertising. | Legal issues arising from the use of and consumption of product and services rendered by the Entity which will impact project objectives; e.g. consumer fraud issues, product safety and defects, personal injuries resulting from dangerous or defective products, false advertising and deceptive business practices.
External | Legal | Consumer | ER.LEG.030 | Risk on legal issue on deceptive business practice. | Legal issues arising from the use of and consumption of product and services rendered by the Entity which will impact project objectives; e.g. consumer fraud issues, product safety and defects, personal injuries resulting from dangerous or defective products, false advertising and deceptive business practices.
External | Legal | Advertising | ER.LEG.040 | Risk on legal issue on advertisement. | Legal issues arising from advertisement and community engagement, such as fora on social and political issues surrounding the business and the project, posting of contents that violates terms and conditions, copyright
External | Legal | Advertising | ER.LEG.040 | Risk on legal issue on community engagement. | Legal issues arising from advertisement and community engagement, such as fora on social and political issues surrounding the business and the project, posting of contents that violates terms and conditions, copyright
External | Legal | Advertising | ER.LEG.040 | Risk on legal issue on fora on social & political issues surrounding the project. | Legal issues arising from advertisement and community engagement, such as fora on social and political issues surrounding the business and the project, posting of contents that violates terms and conditions, copyright
External | Legal | Advertising | ER.LEG.040 | Risk on legal issue on posting of contents violating terms & conditions. | Legal issues arising from advertisement and community engagement, such as fora on social and political issues surrounding the business and the project, posting of contents that violates terms and conditions, copyright
External | Legal | Advertising | ER.LEG.040 | Risk on legal issue on copyright. | Legal issues arising from advertisement and community engagement, such as fora on social and political issues surrounding the business and the project, posting of contents that violates terms and conditions, copyright
External | Legal | Import.Export | ER.LEG.050 | Trade restriction risk. | Legal issues on trade restrictions, supply contract, VAT, product compliance to technical requirements, product safety compliance issues, labeling and packaging and infringement on intellectual property rights.
External | Legal | Import.Export | ER.LEG.050 | Supply contract risk. | Legal issues on trade restrictions, supply contract, VAT, product compliance to technical requirements, product safety compliance issues, labeling and packaging and infringement on intellectual property rights.
External | Legal | Import.Export | ER.LEG.050 | Risk on VAT laws. | Legal issues on trade restrictions, supply contract, VAT, product compliance to technical requirements, product safety compliance issues, labeling and packaging and infringement on intellectual property rights.
External | Legal | Import.Export | ER.LEG.050 | Risk on product compliance to technical requirements. | Legal issues on trade restrictions, supply contract, VAT, product compliance to technical requirements, product safety compliance issues, labeling and packaging and infringement on intellectual property rights.
External | Legal | Import.Export | ER.LEG.050 | Product safety compliance issue. | Legal issues on trade restrictions, supply contract, VAT, product compliance to technical requirements, product safety compliance issues, labeling and packaging and infringement on intellectual property rights.
External | Legal | Import.Export | ER.LEG.050 | Labeling and packaging issues. | Legal issues on trade restrictions, supply contract, VAT, product compliance to technical requirements, product safety compliance issues, labeling and packaging and infringement on intellectual property rights.
External | Legal | Import.Export | ER.LEG.050 | Infringement on intellectual property rights. | Legal issues on trade restrictions, supply contract, VAT, product compliance to technical requirements, product safety compliance issues, labeling and packaging and infringement on intellectual property rights.
External | Legal | Occupational.Health.Safety | ER.LEG.060 | Risk on legal issue on occupational health safety. | Legal issues on occupational health and safety and safety in the workplace which will impact the project objectives.
External | Legal | Occupational.Health.Safety | ER.LEG.060 | Risk on legal issue on safety in the workplace.. | Legal issues on occupational health and safety and safety in the workplace which will impact the project objectives.
External | Legal | Occupational.Health.Safety | ER.LEG.060 | Issues on DOLE regulatory requirements. | Legal issues on occupational health and safety and safety in the workplace which will impact the project objectives.
External | Legal | Workplace.Compliance | ER.LEG.070 | Risk on compliance to Government requirements on employment lay. | These are employer’s legal issues requiring compliance to the Government’s requirements on workplaces, such as general employment lay, drug testing program, employment practice audits, employee investigations, etc.
External | Legal | Workplace.Compliance | ER.LEG.070 | Risk on compliance to Government requirements on drug testing. | These are employer’s legal issues requiring compliance to the Government’s requirements on workplaces, such as general employment lay, drug testing program, employment practice audits, employee investigations, etc.
External | Legal | Workplace.Compliance | ER.LEG.070 | Risk on compliance to Government requirements employment practice audit. | These are employer’s legal issues requiring compliance to the Government’s requirements on workplaces, such as general employment lay, drug testing program, employment practice audits, employee investigations, etc.
External | Legal | Workplace.Compliance | ER.LEG.070 | Risk on compliance to Government requirements on employee investigations. | These are employer’s legal issues requiring compliance to the Government’s requirements on workplaces, such as general employment lay, drug testing program, employment practice audits, employee investigations, etc.
External | Legal | Regulatory.Bodies | ER.LEG.080 | Issues on MOA of plant installation in private properties | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects.
External | Legal | Regulatory.Bodies | ER.LEG.080 | Issues on MOA of plant installation in public and Government properties | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects.
External | Legal | Regulatory.Bodies | ER.LEG.080 | Issues on land acquisitions | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects.
External | Legal | Regulatory.Bodies | ER.LEG.080 | Issues on land conversions | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects.
External | Legal | Regulatory.Bodies | ER.LEG.080 | Issues on the use of Government-owned raw water input common facilities. | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects.
External | Legal | Regulatory.Bodies | ER.LEG.080 | Risk on change of regulations. | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects.
External | Legal | Regulatory.Bodies | ER.LEG.080 | Risk on corporate legislation. | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects.
External | Legal | Regulatory.Bodies | ER.LEG.080 | Risk on industry legislation. | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects.
External | Legal | Regulatory.Bodies | ER.LEG.080 | Risk on regulation of business commodoties. | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects.
External | Legal | Regulatory.Bodies | ER.LEG.080 | Risk on regulation of business industries. | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects.
External | Legal | Regulatory.Bodies | ER.LEG.080 | Risk on regulation of business sectors. | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects.
External | Legal | Regulatory.Bodies | ER.LEG.080 | Risk on security legislation. | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects.
External | Legal | Regulatory.Bodies | ER.LEG.080 | Risk on the issue of co-located and co-use Government facilities & properties. | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects.
External | Legal | Regulatory.Bodies | ER.LEG.080 | Risk on the issue of right of way | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects.
External | Legal | Regulatory.Bodies | ER.LEG.080 | Risk on the use of easements and buffer zones. | Risks to project objectives associated with regulatory issues such as regulation of business sectors, industries and commodities. This includes regulatory risks, that is a change in regulations or legislation affecting security, company, or industry. It also includes issues on right of ways (ROW) for transmission projects.
External | Environmental | Infrastructure | ER.ENV.010 | Issues on above grade structures and facilities | These are built properties like buildings and infrastructures affecting the project objectives.
External | Environmental | Infrastructure | ER.ENV.010 | Issues on below grade utilities and structures. | These are built properties like buildings and infrastructures affecting the project objectives.
External | Environmental | Infrastructure | ER.ENV.010 | Issues on excavation along newly built roads. | These are built properties like buildings and infrastructures affecting the project objectives.
External | Environmental | Infrastructure | ER.ENV.010 | Risk on available space due to existing facilities and structures. | These are built properties like buildings and infrastructures affecting the project objectives.
External | Environmental | Infrastructure | ER.ENV.010 | Risk on un-accounted facilities in conflict with the project. | These are built properties like buildings and infrastructures affecting the project objectives.
External | Environmental | Cyclical.Weather | ER.ENV.020 | Risk on typhoons. | Typhoons, heavy rains, draught and other natural weather condition having direct or indirect impact on project objectives.
External | Environmental | Cyclical.Weather | ER.ENV.020 | Risk on heavy rains. | Typhoons, heavy rains, draught and other natural weather condition having direct or indirect impact on project objectives.
External | Environmental | Cyclical.Weather | ER.ENV.020 | Risk on draught. | Typhoons, heavy rains, draught and other natural weather condition having direct or indirect impact on project objectives.
External | Environmental | Cyclical.Weather | ER.ENV.020 | Risk on natural weather conditions. | Typhoons, heavy rains, draught and other natural weather condition having direct or indirect impact on project objectives.
External | Environmental | Cyclical.Weather | ER.ENV.020 | Risk on thunderstorm. | Typhoons, heavy rains, draught and other natural weather condition having direct or indirect impact on project objectives.
External | Environmental | Energy.Availability.Cost | ER.ENV.030 | Risk on fluctuating energy cost. | Impact of energy rate to production cost, affecting operation risk of projects.
External | Environmental | Energy.Availability.Cost | ER.ENV.030 | Risk on availability of energy at site. | Impact of energy rate to production cost, affecting operation risk of projects.
External | Environmental | Social.Implications | ER.ENV.040 | Issues on community open resistance to the project. | Acceptability of the project to the surrounding community, affecting project schedule, cost and scope.
External | Environmental | Social.Implications | ER.ENV.040 | Issues on project negatively affecting the community. | Acceptability of the project to the surrounding community, affecting project schedule, cost and scope.
External | Environmental | Social.Implications | ER.ENV.040 | Risk on community acceptance of the project. | Acceptability of the project to the surrounding community, affecting project schedule, cost and scope.
External | Environmental | Disposal.Materials | ER.ENV.050 | Issue on availability of disposal location. | Availability of disposal location, specialist contractor for disposal handling, internal resource capability for disposal of materials; these factors will affect project objectives.
External | Environmental | Disposal.Materials | ER.ENV.050 | Issue on availability of specialist contractor disposal handling. | Availability of disposal location, specialist contractor for disposal handling, internal resource capability for disposal of materials; these factors will affect project objectives.
External | Environmental | Disposal.Materials | ER.ENV.050 | Issue on MWO internal resource capability for disposal of materials. | Availability of disposal location, specialist contractor for disposal handling, internal resource capability for disposal of materials; these factors will affect project objectives.
External | Environmental | Disposal.Materials | ER.ENV.050 | Issue on illegal disposal | Availability of disposal location, specialist contractor for disposal handling, internal resource capability for disposal of materials; these factors will affect project objectives.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on Downstream effect. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on ecological consequences. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on impact on air. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on impact on biodiversity. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on impact on climate. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on impact on ecosystems. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on impact on fisheries and migrations. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on impact on flora and fauna. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on impact on forest. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on impact on groundwater | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on impact on land. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on impact on noise pollution. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on impact on rare endangered and threatened species. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on impact on Riparian Habitat. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on impact on soil. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on impact on water. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on impact on wildlife. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Ecological.Consequences | ER.ENV.060 | Risk on irreversible environmental impact. | Impact of the project to the environment creating ecological consequences; the project is a risk to the environment and its surrounding.
External | Environmental | Legislation | ER.ENV.070 | Environmental law risk. | Impact of environmental legislation to the project objectives.
External | Environmental | Legislation | ER.ENV.070 | Risk on changes on Environmental laws and regulations. | Impact of environmental legislation to the project objectives.
External | Environmental | Legislation | ER.ENV.070 | Risk on environmental sanction | Impact of environmental legislation to the project objectives.
External | Environmental | Contamination | ER.ENV.080 | Risk on carbon emmission using diesel Genset. | Projects with plant process effluent (gas, solid, liquid) can be a source of contamination to the environment.
External | Environmental | Contamination | ER.ENV.080 | Risk on chemical contamination. | Projects with plant process effluent (gas, solid, liquid) can be a source of contamination to the environment.
External | Environmental | Contamination | ER.ENV.080 | Risk on environmental surface contamination. | Projects with plant process effluent (gas, solid, liquid) can be a source of contamination to the environment.
External | Environmental | Contamination | ER.ENV.080 | Risk on fuel oil seepage. | Projects with plant process effluent (gas, solid, liquid) can be a source of contamination to the environment.
External | Environmental | Contamination | ER.ENV.080 | Risk on process plant effluent. | Projects with plant process effluent (gas, solid, liquid) can be a source of contamination to the environment.
External | Environmental | Geographic.Location | ER.ENV.090 | Issues on conflict or clashes with other foreseeable built structures or below ground networks. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Issues on deforestation. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Issues on municipal boundary dispute of project location. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Issues on not enough plot of land or properties for project development. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Issues on protected areas. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Issues on sewer influent flow rate. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Issues on site accessibility | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Issues on unsuitable project site location. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Risk due to raw water source quality issues | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Risk due to used water influent quality issues. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Risk on fault line | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Risk on flooding in or near the project area. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Risk on geograhic location of the project. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Risk on landslide along excavation. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Risk on landslide near the project area | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Risk on low water table. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Risk on narrow road pipe laying excavation | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Risk on poor access road condition | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Risk on poor soil condition for pipeline excavation. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Risk on poor soil for foundation. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Risk on roadworks safety on busy highways. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Risk on rock layers during excavation. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Geographic.Location | ER.ENV.090 | Risk on water source depletion. | Specific location of the project can be a risk impacting the project objectives; e.g., plant location is not suitable, not enough land for project development.
External | Environmental | Biohazard.Pandemic | ER.ENV.100 | Risk on pandemic. | Biological risk belonging to WHO Risk Group 4, a virus outbreak in a large community and spreading across the country or even globally without known treatment or preventive measures causing a pandemic that paralyzes the Government, commerce and industry.
External | Environmental | Biohazard.Pandemic | ER.ENV.100 | Risk on community quarantine. | Biological risk belonging to WHO Risk Group 4, a virus outbreak in a large community and spreading across the country or even globally without known treatment or preventive measures causing a pandemic that paralyzes the Government, commerce and industry.
External | Environmental | Biohazard.Pandemic | ER.ENV.100 | Risk on large-scale viral infection. | Biological risk belonging to WHO Risk Group 4, a virus outbreak in a large community and spreading across the country or even globally without known treatment or preventive measures causing a pandemic that paralyzes the Government, commerce and industry.
External | Environmental | Biohazard.Pandemic | ER.ENV.100 | Risk on viral infection on project site and barracks. | Biological risk belonging to WHO Risk Group 4, a virus outbreak in a large community and spreading across the country or even globally without known treatment or preventive measures causing a pandemic that paralyzes the Government, commerce and industry.
External | Environmental | Biohazard.Pandemic | ER.ENV.100 | Risk on viral infection on the nearest community of the project. | Biological risk belonging to WHO Risk Group 4, a virus outbreak in a large community and spreading across the country or even globally without known treatment or preventive measures causing a pandemic that paralyzes the Government, commerce and industry.
External | Environmental | Biohazard.Pandemic | ER.ENV.100 | Risk on industrial, commercial business limited mobility | Biological risk belonging to WHO Risk Group 4, a virus outbreak in a large community and spreading across the country or even globally without known treatment or preventive measures causing a pandemic that paralyzes the Government, commerce and industry.

## RiskRegister
| PROJECT RISK REGISTER FOR TYPES A,B & C PROJECTS | [15 empty] | This document is the property of Manila Water Company, Inc (MWCI). No material may be used, distributed or reproduced in whole or in part without the prior written consent of MWCI. All rights reserved. UNCONTROLLED DOCUMENTS WHEN PRINTED OR CONVERTED TO PDF.
| PROJECT PLANNING PHASE |  |  |  |  | Ver 1.2
| Project Name: |  |  | Long Term East Line 1 |  |  |  |  | Project Description: | [9 empty] | Signatories |  |  | Name / Dep / Grp |  |  | Signature | [5 empty] | Date
| Project Location: | [17 empty] | Prepared by:
| RR Project Code: | [7 empty] | Project Benefits:
| Project Base Cost: |  |  | 14000000000 |  | Project Base Duration (CDay): | 2500 | [11 empty] | Reviewed by:
| Mitigation |  | P90 | #VALUE! |  | Gross Provision for Risk Mitigation (CDay): | 336.75 |  | Project Type: | [6 empty] | Project Headline:
| Contingency |  | P90 | 82767444.5166 |  | Gross Provision for Risk Contingency (Cday): | 900 |  | Name of Proponent : | [9 empty] | Approved by:
| Total Project Cost: |  |  | #VALUE! |  | Cumulative Total Project Duration: | 3736.75 |  | Group/Dept:
| Risk Identification | [5 empty] | Risk Assessment | [5 empty] | Qualitative Risk Analysis Pre-Mitigation |  |  | Risk Mitigation |  |  |  | Qualitative Risk Analysis Post-Mitigation |  |  | Residual Risk Assessment |  | Risk Contingency |  |  |  | Risk Status
| No | Category1 | Category2 | Category3 | Risk Name | Risk Description (Sentence format: Issue, Risk, Impact) | Risk Trigger Date | Scope Impact (addition or removal of works) | Cost Impact (Php) | Schedule Impact (CDay) | Affected Proj Gate | Affected WBS | Impact | Probability | Index | Plan (use SMART Principle) | Cost of Mitigation (Php) | Add Duration for Mitigation (Cday) | Schedule Additive (%) | Impact | Probability | Index | Residual Cost Impact (Php) | Residual Schedule Impact (CDay) | Plan (Use SMART Principle) | Reserve Cost (Php) | Reserve Schedule (Cday) | Schedule Additive (%) | Status | Date | Resolution Statement
[9 empty] | 1585000000 | 3750 | [6 empty] | 164000000 | 336.75 |  |  |  |  | 60000000 | 1110 |  | 60000000 | 900
1 | 1 | External | Legal | Regulatory.Bodies | Risk on the use of easements and buffer zones. | Issue: Landing of pipe on both sides of DPWH floodway. (RCX-17) Risk: Acquisition of DPWH ROW on both sides of the Manggahan Floodway footbridge slope protection. Impact: Possible delays on the land acquisition and ROW | 2023-01-30 | Expropriation of lots for the pipe bridge landing | 35000000 | 0 | Gate.2_Delivery.Strategy.Tender.Preparation | Cost Estimate Final | Low | High | Low | Coordinate with DPWH…. | 0 | 0 | 0% | Low | Medium | Low | 35000000 | 0 | Proceed with expropriation. | 35000000 | 0 | 0% | Closed | 2023-02-22 | No longer relevant due to changed in alignment.
2 | 2 | External | Social | Attitude.Beliefs | Risk on public sentiments and reactions due to community impact of the project. | Issue: Pipelaying of 2 lines (along with Wawa 1600mm dia pipeline) in Roman Rojas Road will aggravate public sentiments and will generate numerous traffic complaints Risk: Work Stoppage Impact: Delays in the pipelaying construction and will eventually delay the project implementation | 2024-12-06 |  | 0 | 90 | Gate.4_Readiness.For.Service.Construction | Pipe Network Installation | Low | High | Low | Conduct public/stakeholder consultation and obtain "No objection letter" along with the barangay clearance from the barangay office. Contractor to establish Grievance Mechanism. This to be included in the TOR. | 0 | 0 | 0% | Low | Medium | Low | 0 | 0 |  | 0 | 0 | 0% | Open
3 | 3 | External | Political | Bureaucracy.Issues | Risk on delays on the issuance of permits. | Issue: Some politically aligned officer in the DENR may pose difficulty in acquiring Tree Cutting Permit Risk: Not able to get the tree cutting permit on time as per project schedule Impact: Delays in mobilization and will eventually delay the project implementation | 2024-12-06 |  | 0 | 180 | Gate.4_Readiness.For.Service.Construction | Civil and Site Development Works | High | High | High | MWCI to do early pre-selling activities with DENR and secure all the requirements and complete the documents as early as possible. | 0 | 0 | 0% | Medium | Medium | Medium | 0 | 60 |  | 0 | 60 | 0% | Open
4 | 4 | Internal | PQM | Project.Execution.Issues | Risk on damage to existing structure and facilities. | Issue: Damage to Existing Services and Utilities such as MERALCO distribution lines and poles. Risk: Excavation works cannot proceed. Impact: Delay in construction works | 2024-12-06 |  | 0 | 120 | Gate.4_Readiness.For.Service.Construction | Civil and Site Development Works | Medium | Very High | High | MWCI to do early coordination with MERALCO on the relocation of electrical poles. | 6000000 | 120 | 100% | Low | Low | Low | 0 | 0 | Add 30 days provision only for the early coordination of construction phase of water tower Shaft 3 and Pasig WTP | 0 | 0 | 0% | Open
5 | 5 | Internal | PQM | Project.Execution.Issues | Risk on damage to existing structure and facilities. | Issue: Damage to properties such as buildings and houses near or adjacent to the construction sites. Possibility of building/house owners will not agree to any settlements. Risk: Excavation works cannot proceed. Impact: Delay in construction works | 2024-12-06 |  | 150000000 | 360 | Gate.4_Readiness.For.Service.Construction | Civil and Site Development Works | Very High | Very High | High | MWCI to do early pre-selling activities with barangay up to LGU level. | 150000000 | 180 | 100% | Medium | Low | Medium | 25000000 | 0 | Add 60 days provision only for the TBM construction phase | 25000000 | 0 | 0% | Open
6 | 6 | Internal | Engineering | Design | Constructability issues. | Issue: Pipelaying construction challenges due to space constraints and creek crossings Risk: Pipe encroachment to private property area along the road shoulder Impact: Legal impediment leading to work stoppage and project delays | 2024-12-06 |  | 0 | 180 | Gate.4_Readiness.For.Service.Construction | Pipe Transmission Installation | Medium | Medium | Medium | Conduct stakeholder consultation and obtain "No objection letter" on each individual lot owner, along with the barangay clearance from the barangay office. | 8000000 | 0 | 0% | Low | Low | Low | 0 | 0 |  | 0 | 0 | 0% | Open
7 | 7 | Internal | PQM | Project.Execution.Issues | Issues on availability of space for construction machineries and equipment. | Issue: Width of the Road along Solid Cement Road Risk: ROW risk along solid cement road due to the width of the road and the space needed for public vehicles to pass on one lane. Impact: Project Delays | 2024-12-06 | Change of alignment and change of construction methodology |  |  | Gate.4_Readiness.For.Service.Construction | Pipe Transmission Installation | Medium | High | Medium | Arcadis to nominate viable alternative alignment | 0 |  |  | Low | Low | Low | 0 | 0 |  | 0 | 0 | 0% | Open
8 | 8 | External | Legal | Regulatory.Bodies | Risk on the use of easements and buffer zones. | Issue: Land for the Shaft 1 Risk: Negotiation with Antipolo LGU including WOP of less than 50meters Impact: Possible delays on the land acquisition | 2024-01-01 |  | 0 | 180 | Gate.2_Delivery.Strategy.Tender.Preparation | Engineering Drawings | Medium | Medium | Medium | Pre-selling activities with LGU and convince them of the positive benefits of the project. Coordinate closely with LGU, build relationship, and ensure their buy-in into the project. | 0 | 30 | 100% | Medium | Low | Medium | 0 | 0 |  | 0 | 0 | 0% | Open
9 | 9 | External | Legal | Regulatory.Bodies | Risk on the use of easements and buffer zones. | Issue: Land for the Intermediate Shaft (Shaft 2) is a private property and no knowledge in how many lots will be affected. Risk: Land Acquisition for the Shaft 2 Impact: Possible delays on the land acquisition and will negatively impact the project timeline. | 2024-01-01 | Change of alignment and change of construction methodology | 0 | 1200 | Gate.2_Delivery.Strategy.Tender.Preparation | Engineering Drawings | Very High | High | High | Arcadis to nominate viable alternative shafts | 0 | 45 | 5% | Medium | Medium | Medium | 0 | 30 | None | 0 | 30 | 100% | Open
10 | 10 | External | Social | Attitude.Beliefs | Risk on public sentiments and reactions due to community impact of the project. | Issue: High number of complaints and possible Temporary Restraining Order (TRO) due to noise during implementation for Shaft 2 and 3 from neighbours Risk: Work Stoppage Impact: Delays in the construction of shaft and will eventually delay the project implementation | 2024-12-06 |  | 0 | 180 | Gate.4_Readiness.For.Service.Construction | Mobilization | Medium | Medium | Medium | Conduct public/stakeholder consultation and obtain "No objection letter" along with the barangay clearance from the barangay office. | 0 | 0 | 0% | Low | Low | Low | 0 | 0 |  | 0 | 0 | 0% | Open
11 | 11 | Internal | PQM | Project.Execution.Issues | Issues on availability of space for construction machineries and equipment. | Issue: Risks related to concurrent construction of Pasig WTP and LTE Shaft 3 Risk: Risk on accessibility, mobility and storage issues Impact: May pose delay in construction timeline | 2026-01-15 |  | 0 | 90 | Gate.4_Readiness.For.Service.Construction | Construction Staging | Low | Medium | Low | Early coordination of WTP and LTE working committee for the alignment of works and activities and construction timeline. | 0 | 0 | 0% | Medium | Medium | Medium | 0 | 30 | Inform management on this issue. | 0 | 30 | 0% | Open
12 | 12 | Internal | Procurement | Contract.Management | Risk on failure of Contractor to provide timely construction equipment and materials as per project timeline. | Issue: Availability/Procurement of Tunnel Contractor using Tunnel Boring Machine (TBM) Risk: Risk in Timeline delays should TBM not readily available before implementation Impact: Project Delays | 2025-01-05 |  | 0 | 360 | Gate.3_Investment.Decision.Procurement | BAC Recommendation | Medium | Medium | Medium | Risk Accepted | 0 | 0 | 0% | Medium | Medium | Medium | 0 | 360 |  | 0 | 360 | 100% | Open
13 | 13 | Internal | Engineering | Design | Constructability issues. | Issue: TBM correct technical operation by construction personnel during the tunneling process is required to guarantee the safety of the tunnel project. Risk: The technical risks of TBM tunnel construction mainly include lining leakage, TBM tunneling offset, and anchor shaft force monitoring failing to meet the requirements. Meanwhile, a delay of pea-gravel back filling and grouting may induce a lack of timely support to surrounding rock, which increases the risk of TBM jamming. Impact: Work stoppage and project delays | 2025-12-31 |  | 0 | 30 | Gate.4_Readiness.For.Service.Construction | Tunnel horizontal boring works TBM | Low | Medium | Low | Risk Accepted | 0 | 0 | 0% | Low | Medium | Low | 0 | 30 | Add 30 days to the TBM work schedule, as provision only due to technical issues. | 0 | 30 | 100% | Open
14 | 14 | Internal | PQM | Equipment.Quality.Issues | Defective product or equipment risk. | Issue: TBM Equipment Failure Risk: Equipment risks include failure of the pipe assembly, failure of the jacking system, failure of the grouting system, mismatch of the operation model selection, consumption of disc cutters, and failure of the shield tail seal Impact: Work stoppage and project delays | 2025-06-15 |  | 0 | 120 | Gate.4_Readiness.For.Service.Construction | Tunnel horizontal boring works TBM | High | Medium | High | Risk Accepted | 0 | 0 | 0% | High | Medium | High | 0 | 120 | Add 120 days to the TBM work schedule, as provision only due to TBM equipment failure. | 0 | 120 | 100% | Open
15 | 15 | Internal | PQM | Equipment.Quality.Issues | Defective product or equipment risk. | Issue: Manufacturing, operation, and maintenance of TBMs. Risk: Operation risks exist in the processes of installation, starting, stepping, dismantling, and other procedures. Impact: Work stoppage and project delays | 2025-01-05 |  |  |  | Gate.4_Readiness.For.Service.Construction | Tunnel horizontal boring works TBM | Low | High | Low | Contractor to include in the offer the critical spare parts, consumable materials and standard part for the TBM are complete within the Contractor's warehouse. | 0 |  |  | Low | Low | Low | 0 | 0 |  | 0 | 0 | 0% | Open
16 | 16 | Internal | PQM | Project.Execution.Issues | Risk on project technical issues. | Issue: Operation and management of supporting facilities. Risk: Supporting facilities for muck removal, ventilation, power supply, water supply and drainage, and material transportation have the characteristics of safety, reliability, durable stability, energy conservation, and high efficiency. Impact: Work stoppage and project delays | 2025-12-31 |  |  |  | Gate.4_Readiness.For.Service.Construction | Tunnel horizontal boring works TBM | Low | High | Low | Contractor to include in the offer the critical spare parts, consumable materials and standard part for all supporting facilities are complete within the Contractor's warehouse. | 0 |  |  | Low | Low | Low | 0 | 0 |  | 0 | 0 | 0% | Open
17 | 17 | Internal | Work.Health.Safety | Environmental.Hazards | Air quality and air pollution hazard risk. | Issue: Working environment and labor security. Risk: Potential risks exist in the working environment, such as low ventilation quality around the tunnel face, de-dusting and cooling measures, pollutant emission, and noise control in the tunnel excavation. Impact: Work stoppage and project delays | 2025-12-31 |  |  |  | Gate.4_Readiness.For.Service.Construction | Tunnel horizontal boring works TBM | Medium | Medium | Medium | Contractor to include in the TOR the Contractor's Health and Safety Management Plan. | 0 |  |  | Low | Low | Low | 0 | 0 |  | 0 |  |  | Open
18 | 18 | Internal | Engineering | Design | Risk on failure to validate data inputs on design. | Issue: Run-through survey and traverse-survey control Risk: The tunnel is divided into sections. A lack of accuracy and reliability in the ground control net and in the traverse survey of the tunnel will present challenges to the creation of an accurate run-through of the tunnel Impact: Project delays | 2023-05-31 |  |  |  | Gate.4_Readiness.For.Service.Construction | Tunnel horizontal boring works TBM | Medium | Low | Medium | Designer to double check the accuracy of survey and survey control prior to approval. | 0 |  |  | Low | Low | Low | 0 | 0 |  | 0 |  |  | Open
19 | 19 | External | Environmental | Geographic.Location | Risk on fault line | Issue: Earthquakes during project construction will create ground shaking, landslides and rock burst inside the tunnel Risk: Affect the workers and equipment onsite. Impact: Workers injury and possible fatality. Damage of property resulting to work stoppage. | 2025-12-31 |  | 1400000000 | 180 | Gate.4_Readiness.For.Service.Construction | Tunnel horizontal boring works TBM | High | Medium | High | Use of special rings for earthquake protection along fault lines. A double lining is installed and filled by a porous material | 0 | 0 | 0% | Medium | Medium | Medium | 0 | 60 | Add 60 days to the work schedule, as provision for earthquake during project construction. | 0 | 60 | 0% | Open
20 | 20 | External | Environmental | Geographic.Location | Risk on rock layers during excavation. | Issue: TBM Geological Risk which include bad rock surroundings, cave-entrance landslide, high groundwater level, rock explosion, karst gushing water, and fault fracture zones, as well as old mines workings Risk: TBM is prone to various geological hazards when digging in poor geological sections Impact: Work stoppage and project delays | 2025-12-31 |  | 0 | 120 | Gate.4_Readiness.For.Service.Construction | Tunnel horizontal boring works TBM | High | Medium | High | 1. Geotechnical investigation using sufficient borehole spacing as recommended by the consultant/geodetic engineer. 2. Confirmatory geotechnical investigation by the design and build contractor. | 0 | 90 | 5% | Medium | Low | Medium | 0 | 0 |  | 0 | 0 | 0% | Open
21 | 21 | External | Environmental | Geographic.Location | Risk on fault line | Issue: Regional fault structure zones. Risk: The tunnel will pass through regional fault structure zones, which may trigger water inrush (flooding inside the tunnel), mud inrush, collapse, machine blockage, and personnel safety risks such as drowning and fatality. Impact: Work stoppage and project delays | 2025-12-31 |  |  |  | Gate.4_Readiness.For.Service.Construction | Tunnel horizontal boring works TBM | Very High | Medium | High | Risk Accepted | 0 |  |  | Very High | Medium | High | 0 | 60 |  | 0 | 60 | 100% | Open
22 | 22 | External | Environmental | Geographic.Location | Risk on rock layers during excavation. | Issue: Large plastic deformation of extremely soft rocks. The tunnel is deeply buried, and the level of underground water is very high. In addition, there might be soft cave sections. Thus, there is a risk of large plastic deformation. Risk: TBM direction misalignment. Impact: Work stoppage and project delays | 2025-12-31 |  |  |  | Gate.4_Readiness.For.Service.Construction | Tunnel horizontal boring works TBM | Low | Medium | Low | Risk Accepted | 0 |  |  | Low | Medium | Low | 0 | 60 | Add 60 days to the project work schedule, as provision only due to issues on soil plasticity along the tunnel (TBM). | 0 | 60 | 100% | Open
23 | 23 | External | Environmental | Geographic.Location | Risk on rock layers during excavation. | Issue: Hard rock excavation and moderate rock burst. Risk: Granite and biotite gneiss are types of hard rock with a compressive strength greater than 180 MPa and with a quartz content of 20%–30%. These rocks present risks of tool wear and machine blockage. In the deeply buried sections of the tunnel, there is also a great probability of encountering moderate rock burst. Impact: Work stoppage and project delays | 2025-12-31 |  |  |  | Gate.4_Readiness.For.Service.Construction | Tunnel horizontal boring works TBM | Low | Medium | Low | Risk Accepted | 0 |  |  | Low | Medium | Low | 0 | 60 | Add 60 days to the project work schedule, as provision only due to ihard rpck excavation and moderate rock burst. | 0 | 60 | 0% | Open
24 | 24 | Internal | Procurement | Contract.Management | Risk on failure of either party to fulfil the conditions of the contract | Issue: Construction Management Risk Risk: Insufficient construction control plan, low quality of management personnel, non-implementation of organization, poor construction control information, and backward effective control methods. Impact: Work stoppage and project delays | 2024-10-07 |  | 0 | 180 | Gate.4_Readiness.For.Service.Construction | Tunnel horizontal boring works TBM | High | Medium | High | Contractor to include in the TOR the Contractor's Construction Management Plan. | 0 | 0 | 0% | Medium | Medium | Medium | 0 | 60 | Add 60 days to the project work schedule, as provision only due to issues on construction management. | 0 | 60 | 100% | Open
25 | 25 | External | Political | Stability.Neighbors | Risk on regional destabilization due to processes in neighboring countries. | Issue: International conflict and war Risk: Delay on materials and spare parts availability and increase in cost Impact: Work stoppage and project delays | 2024-10-07 |  |  | 180 | Gate.4_Readiness.For.Service.Construction | Contractor's Procurement of Materials and Equipment | Medium | Low | Medium | Risk Accepted | 0 |  |  | Medium | Low | Medium | 0 | 180 | Contractor to provide alternative source of materials/spare parts from other non-conflicted countries. | 0 | 180 | 100% | Open
26 | 26 | Internal | PQM | Project.Execution.Issues | Risk on Contractor's labor dispute and work strike. | Issue: Disputes (Contractors) Risk: Contractor disputes occur during duration of project Impact: Significant delay/ work stoppage | 2024-10-07 |  |  |  | Gate.4_Readiness.For.Service.Construction | Pipe Network Installation | Medium | Low | Medium | Establish robust communication plan between Consultant, Manila Water and Contractor through shared document folders, continuous weekly meetings, minute meetings and other forms of communication | 0 |  |  | Low | Low | Low | 0 | 0 |  | 0 | 0 | 0% | Open
27 | 27 | Internal | PQM | Project.Execution.Issues | Risk on failure to implement safety in the work place. | Issue: Non-compliance of Contractor to safety requirements of site owner. Risk: Complaints and and non-compiance report from Manila Water Impact: Work stoppage/delay on project implementation | 2024-10-07 |  |  |  | Gate.4_Readiness.For.Service.Construction | Pipe Network Installation | High | Low | Medium | Provide Health and Safety Program and Briefing during pre-construction meeting. Ensure that an Occupational Health and Safety Committee is established with the safety officer present on site at all times. | 0 |  |  | Low | Low | Low | 0 | 0 |  | 0 | 0 | 0% | Open
28 | 28 | Internal | Work.Health.Safety | Biological.Infectious.Diseases | Insect bites risk | Issue: Biological hazards (i.e. snakes, insects, dogs etc.); Risk: People on site inspection may encounter danger such as be bitten by snakes, insects and others Impact: Injury and fatality. | 2024-10-07 |  |  |  | Gate.4_Readiness.For.Service.Construction | Pipe Network Installation | Medium | Low | Medium | - Clearing of work area prior to site walkthrough especially at vegetated area - Specific preventive measures in health and safety plan on management of biological hazards. | 0 |  |  | Low | Low | Low | 0 | 0 |  | 0 | 0 | 0% | Open
29 | 29 | Internal | Operation | Health.Safety | H&S transport and mobility risk. | Issue: COVID 19 related restrictions on mobility such as in the event of a stringent local quarantine Risk: Travel restriction where field crew may not to be able to mobilize Impact: Significant delay in the implementation schedule during the engineering, procurement and construction stage. | 2024-10-07 |  |  |  | Gate.4_Readiness.For.Service.Construction | Pipe Network Installation | Medium | Low | Medium | Early coordination with local government/authorities. | 0 |  |  | Low | Low | Low | 0 | 0 |  | 0 | 0 | 0% | Open
30 | 30 | Internal | Work.Health.Safety | Physical.Hazards | Electrical hazard risk. | Issue: Electrocution Risk: Electrocution due electrical wiring which maybe peeled during welding works Impact: Major incident. Fatality. Delays in work and possibly work stoppage | 2024-10-07 |  |  |  | Gate.4_Readiness.For.Service.Construction | Pipe Network Installation | Medium | Low | Medium | Ensure all wirings and connections are in good working condition | 0 |  |  | Low | Low | Low | 0 | 0 |  | 0 | 0 | 0% | Open
31 | 31 | Internal | Work.Health.Safety | Physical.Hazards | Fires risk | Issue: Fire hazard Risk: Possible occurrence of fire in the working area during welding works Impact: Major incident. Fatality. Delays in work and possibly work stoppage | 2024-10-07 |  |  |  | Gate.4_Readiness.For.Service.Construction | Pipe Network Installation | Medium | Low | Medium | Ensures that all workers must wear their PPE. | 0 |  |  | Low | Low | Low | 0 | 0 |  | 0 | 0 | 0% | Open
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
8 | 62
14 | 63
17 | 64
18 | 65
66
67
16 | 68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
| 194 | [7 empty] | 0
| 195 | [7 empty] | 0
| 196 | [7 empty] | 0
| 197 | [7 empty] | 0
| 198 | [7 empty] | 0
| 199 | [7 empty] | 0
| 200 | [7 empty] | 0
CONFIDENTIAL PROPERTY OF MWCI
CONFIDENTIAL PROPERTY OF MWCI
CONFIDENTIAL PROPERTY OF MWCI
CONFIDENTIAL PROPERTY OF MWCI
CONFIDENTIAL PROPERTY OF MWCI

## Assumption
ASSUMPTIONS AND CALCULATIONS ON COST AND SCHEDULE | [7 empty] | Project Name: |  | Long Term East Line 1
Risk Impact, Mitigation and Contingency
BASE FEE | [5 empty] | Prepared by: | [5 empty] | Date:
[18 empty] | 1 month | 30 | days
Prepared by: | [11 empty] | Date:
Risk No. | RISK IMPACT |  |  |  |  | RISK MITIGATION | [5 empty] | RISK CONTINGENCY
| Cost Impact (PhP) | Assumptions |  | Impact Schedule (in calendar days) | Total months affected in the schedule ( in months) | Cost of Mitigation (PhP) | Assumptions |  | Duration of Mitigation (in calendar days) |  | Schedule Additive (percentage) | Residual Cost Impact/Reserve Cost (PhP) | Assumptions |  | Reserve Schedule (in calendar days) |  | Schedule Additive (percentage)
|  | Particulars | Value |  |  |  | Particulars | Value | No. of days | Remarks |  |  | Particulars | Value | No. of days | Remarks
1 | 35000000 | Land Area Value | 15000000 | [8 empty] | 35000000 | Proceed with expropriation. | 35000000
|  | Property Value | 10000000
|  | Cost of Relocation | 10000000
2 |  |  |  | 90 | 3
Remarks: Pipelaying of 2 lines (along with Wawa 1600mm dia pipeline) in Roman Rojas Road
3 |  |  |  | 180 | 6 | [7 empty] | Number of trees |  | 60 | Remarks: Add 60 days provision only for the acquisition of DENR permit.
[5 empty] | Remarks: 6 months possible delay when not able to get the tree cutting permit on time as per project schedule | [7 empty] | Cost per tree (PhP)
4 |  |  |  | 120 | 4 | 6000000 | Assumed cost per kilometer | 2000000 | 120 | Remarks: Allocated three months for the relocation of electrical poles. | 100%
[5 empty] | Remarks: 2 months possible delay when excavation works cannot proceed due to damage to existing utility services such as MERALCO distribution lines and poles and additional 2 months for admin works. |  | Total length | 3
5 | 150000000 | Number of Houses Affected | 50 | 360 | 12 | 150000000 | Number of Houses Affected | 50 | 180 | Remarks: Allocated six months | 100% | 25000000 | Number of Houses Affected | 50
|  | Cost per house affected | 3000000 |  | Remarks: Allocated 12 months inclusive of litigation cases |  | Cost per house affected | 3000000 |  |  |  |  | Percentage | 50%
[13 empty] | Cost | 1000000
6 |  |  |  | 180 | 6 | 8000000 | XXX | 1600
[7 empty] | XXX | 2
[7 empty] | XXX | 2500
7
8 |  |  |  | 180 | 6 |  |  |  | 30 | Remarks: Pre-selling activities with LGU | 100%
Remarks: Allocated 6 months for the negotiation with Antipolo LGU
9 |  |  |  | 1200 | 40 |  |  |  | 45 | Remarks: Nomination of alternative shafts | 5% |  |  |  | 30 |  | 100%
Remarks: 40 months allocation for LTE 1B Construction Schedule
10 |  |  |  | 180 | 6
Remarks: High number of complaints and possible Temporary Restraining Order (TRO) due to noise during implementation for Shaft 2 and 3 from neighbours
11 |  |  |  | 90 | 3 | [9 empty] | 30 | Remarks: Add 30 days provision only for the early coordination of construction phase of water tower Shaft 3 and Pasig WTP
Remarks: Risk on accessibility, mobility and storage issues
12 |  |  |  | 360 | 12 | [9 empty] | 360 |  | 100%
Remarks: Risk in Timeline delays should TBM not readily available before implementation
13 |  |  |  | 30 | 1 | [9 empty] | 30 | Remarks: Add 30 days to the TBM work schedule, as provision only due to technical issues. | 100%
14 |  |  |  | 120 | 4 | [9 empty] | 120 | Remarks: Add 120 days to the TBM work schedule, as provision only due to TBM equipment failure. | 100%
15 |  |  |  | 60 | 2
16 |  |  |  | 60 | 2
17
18
19 | 1400000000 | Project Base Cost | 14000000000 | 180 | 6 |  | Use of special rings for earthquake protection along fault lines. | [7 empty] | 60 | Remarks: Add 60 days provision only for the TBM construction phase
|  | Percentage | 10% |  | Remarks: 6 months possible delay when earthquake occurs during project construction. |  | Cost of special rings already built-in to the budget. No need for cost mitigation.
20 |  |  |  | 120 | 4 |  |  |  | 90 |  | 5%
21 |  |  |  | 60 | 2 | [9 empty] | 60 |  | 100%
22 |  |  |  | 60 | 2 | [9 empty] | 60 |  | 100%
23
24 |  |  |  | 180 | 6 | [9 empty] | 60 | Remarks: Add 60 days to the project work schedule, as provision only due to issues on construction management. | 100%
25
26
27
28
29
30
31

## Risk-Based Cost Estimate
Risk-Based Project Cost Estimate |  |  |  | CONFIDENTIAL
Long Term East Line 1
Risk No | Mitigation Estimates |  |  | MC Distribution | P90 | Contingency Estimates |  |  | MC Distribution | P90
| Low | Most | High |  | 90% | Low | Most | High |  | 90% | P01 | 1%
1 | 0 | 0 | 0 | 0 | 0 | 28000000 | 35000000 | 56000000 | 28581486.5815 | 48218083.3224 | P02 | 2%
2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P03 | 3%
3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P04 | 4%
4 | 4200000 | 6000000 | 8100000 | 7656844.5567 | 7221440.0253 | 0 | 0 | 0 | 0 | 0 | P05 | 5%
5 | 105000000 | 150000000 | 202500000 | 164881547.7765 | 179551330.6946 | 20000000 | 25000000 | 40000000 | 29736150.5519 | 34549361.1942 | P06 | 6%
6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P07 | 7%
7 | #REF! | #REF! | #REF! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | P08 | 8%
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P09 | 9%
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P10 | 10%
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P11 | 11%
11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P12 | 12%
12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P13 | 13%
13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P14 | 14%
14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P15 | 15%
15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P16 | 16%
16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P17 | 17%
17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P18 | 18%
18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P19 | 19%
19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P20 | 20%
20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P21 | 21%
21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P22 | 22%
22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P23 | 23%
23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P24 | 24%
24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P25 | 25%
25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P26 | 26%
26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P27 | 27%
27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P28 | 28%
28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P29 | 29%
29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P30 | 30%
30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P31 | 31%
31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P32 | 32%
32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P33 | 33%
33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P34 | 34%
34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P35 | 35%
35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P36 | 36%
36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P37 | 37%
37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P38 | 38%
38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P39 | 39%
39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P40 | 40%
40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P41 | 41%
41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P42 | 42%
42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P43 | 43%
43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P44 | 44%
44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P45 | 45%
45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P46 | 46%
46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P47 | 47%
47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P48 | 48%
48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P49 | 49%
49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P50 | 50%
50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P51 | 51%
51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P52 | 52%
52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P53 | 53%
53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P54 | 54%
54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P55 | 55%
55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P56 | 56%
56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P57 | 57%
57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P58 | 58%
58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P59 | 59%
59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P60 | 60%
60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P61 | 61%
61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P62 | 62%
62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P63 | 63%
63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P64 | 64%
64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P65 | 65%
65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P66 | 66%
66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P67 | 67%
67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P68 | 68%
68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P69 | 69%
69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P70 | 70%
70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P71 | 71%
71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P72 | 72%
72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P73 | 73%
73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P74 | 74%
74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P75 | 75%
75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P76 | 76%
76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P77 | 77%
77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P78 | 78%
78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P79 | 79%
79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P80 | 80%
80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P81 | 81%
81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P82 | 82%
82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P83 | 83%
83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P84 | 84%
84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P85 | 85%
85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P86 | 86%
86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P87 | 87%
87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P88 | 88%
88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P89 | 89%
89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P90 | 90%
90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P91 | 91%
91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P92 | 92%
92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P93 | 93%
93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P94 | 94%
94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P95 | 95%
95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P96 | 96%
96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P97 | 97%
97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P98 | 98%
98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P99 | 99%
99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P100 | 100%
100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | #REF! | #REF! | #REF! |  | #VALUE! | 48000000 | 60000000 | 96000000 |  | 82767444.5166

## SimulationResults1 (hidden)
Results Summary |  | Percentile Distribution |  | Histogram Data |  | Interval Probability Data
Mean | #NAME? | Percentile | Value | Bin | Frequency | Value | Probability
Number of Trials | #NAME? | 0% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Standard error | #NAME? | 5% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
|  | 10% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Minimum | #NAME? | 15% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Maximum | #NAME? | 20% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Median | #NAME? | 25% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Range | #NAME? | 30% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
|  | 35% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Standard Deviation | #NAME? | 40% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Variance | #NAME? | 45% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
|  | 50% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Skewness | #NAME? | 55% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Kurtosis | #NAME? | 60% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
|  | 65% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
|  | 70% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
|  | 75% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
|  | 80% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
|  | 85% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
|  | 90% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
|  | 95% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
|  | 100% | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
2

## MC (hidden)
[6 empty] | Risk Cost |  |  |  | Risk Schedule Delays
[6 empty] | Low | Mid | High | MC | Low | Mid | High | MC
External | Political | Bureaucracy.Issues | Risk on delays on the issuance of permits. | Slow response and process of LGU Pasig City Hall Office for permitting acquisition due to current Pandemic and/or change of administration leading to limited personnel to assist on permitting application and data gathering for design reference. Hence, the work commencement cannot progress on time which may result to delay on project site implemention. | Delay of survey works, EOT for surveyors and Additional cost for team supporting the project | 4012000 | 4720000 | 5900000 | 5197427.3401 | 14 | 20 | 27 | 25.545
External | Environmental | Infrastructure | Risk on un-accounted facilities in conflict with the project. | Unavailability of comprehensive existing drainage data hence the network feasibility designs cannot progress on time which may result to delay commencing needed network alignment surveys. | Longer delivery of preliminary survey works and also delay in issuance of contractor's survey project specifications, EOT for surveyors, and designers to do FS and detailed design ( nos. of duration delays carried over already at permtting/stakeholders delays | 0 | 0 | 0 |  | 0 | 0 | 0
Internal | Strategy | Initial.Systems.Design | Risk on the issues of data accuracy on water demand projection. | Inaccurate sewage flow measurement if done during rainy season thus sewer distribution system may not be accurately sized which may result to network under-utilization or over-utilization that would increase of cost due to work duplication. | Conduct of survey flow validation/measurement of intercepted flow locations during dry season and redesign based on actual results | 3528000 | 5040000 | 6300000 | 5492902.0771 | 21 | 30 | 40.5 | 27.5312
External | Strategy | Feasibility.Studies.Options | Risk on project with feasibility studies having insufficient options. | Difficulty in procuring land for network pump/lift stations reason leading to difficulty and delay of Network designs finalization which may result to longer timelines for design feasibility approvals. Note: Exact Locations Coordinates has been given to MWCI Land Acquisition Team for market availability research. | Exploration of multiple feasibility options for pump/lift stations locations. Increase of standby Costs-say Php 150k/day plus expensive lot option | 42000000 | 60000000 | 75000000 | 61015678.15 | 21 | 30 | 40.5 | 28.5797
External | Strategy | Feasibility.Studies.Options | Risk on project with feasibility studies using unfounded assumptions. | Results of Ground Investigation Surveys may give very deep or poor ground conditions and liquefaction which may result to expensive ground improvement measures/solutions for network and pumps stations which could also impact cost effectiveness for buildability. | Entails higher project costs for foundation works which may not be able to consider during project bid, addl days for bigger foundation | 350000000 | 500000000 | 700000000 | 464537637.491 | 70 | 100 | 135 | 101.7371
External | Environmental | Biohazard.Pandemic | Risk on pandemic. | Covid-19 current pandemic which put Project team, subcontractors/surveyors and other supporting group at risk to be also infected which may result to work stoppages and further delays. | Project Delays and EOT, assumed 3 days budget /month for first year of worked | 5947200 | 8496000 | 10620000 | 9565411.9704 | 25.2 | 36 | 48.6 | 35.0055
Internal | Procurement | Inviting.Clarifying.Closing.Offers | Risk on insufficient number of accredited contractors. | Limited interested subcontractors with sufficient experience in micro- tunnelling which could compromise the quality of deliverables of project requirements that could lead to unsuccessful outcome of project and further delay of implementation. | Comprehensive evaluation of interested subcontractors. Note. Cost Impact to be considered on Contractor's LS costs | 0 | 0 | 0 |  | 9.8 | 14 | 18.9 | 15.9241
External | Economic | Globalization | Risk on vendor engagement. | Unavailability of equipment and construction materials due to slow production because of pandemic which may delay project implementation that would directly impact to time and cost for the long lead procurement of equipment and construction materials. | Additional cost for outscourcing project resources, 3% contingency | 267498603.8691 | 356664805.1588 | 499330727.2223 | 347041247.3576 | 0 |  | 0
External | Legal | Regulatory.Bodies | Risk on the issue of right of way | Existing Pasig Cockfight Arena at Brgy. Santolan could be the only access to Intake area has been identified with potential ROW issues which could block the road and could lead to redesign or realignment of the network that could cause addl cost and time delays for the project. | Acquisition of Lot or purchace land portion for access or Possible redesign of network alignment | 7000000 | 10000000 | 12500000 | 12180141.3839 | 21 | 30 | 40.5 | 37.662
External | Economic | Inflation | Risk due to changes in inflation rates. | Price escalation due to pandemic and slow economic growth which lead to increase of project (network alignment) construction materails that may lead to exceed project budget and may result the project to put on hold. | Estimated 6% annual estimated escalation on project budget | 534997207.7382 | 713329610.3176 | 1069994415.4764 | 792280910.772 | 0 |  | 0
External | Social | Social.Mobility | Risk in the change of social status relative to current social location. | Local hiring Ordinance of LGU which lead to shortage of skilled and capable manpower leading to slow overall project construction progress. | Delays in construction, EOT for contractors (5% Contingency for maintrunk budget) | 416108939.3519 | 594441341.9313 | 802495811.6073 | 557319124.9656 | 0 |  | 0
External | Political | Government.Leadership | Risk in the failure of administrative processes. | Change in the administration in NGA Offices (MMDA, DPWH, etc) that could lead double effort in data information gathering, coordination and clearance to start construction which may lead for further delay of project site works. | Delay in approvals i.e. MMDA, DPWH etc. Cost estimate for Consultant Standby, 14 days | 1470000 | 2100000 | 2625000 | 1931071.7125 | 9.8 | 14 | 18.9 | 13.9888
External | Environmental | Infrastructure | Issues on below grade utilities and structures. | Pipe laying LGU schedule and installation limitations may not in accordance with MWCI Contractor pipe laying activities programme which would lead time extension and project delays. | Delays in project completion, EOT for contractors, increase costs | 16170000 | 23100000 | 28875000 | 25956295.7983 | 53.9 | 77 | 103.95 | 81.8609
External | Environmental | Infrastructure | Risk on un-accounted facilities in conflict with the project. | Existing utilities and/or buried services such as pipes, fiber optic lines of MMDA, DPWH, telecom, Maynilad services along the network which may lead to redesign or realignment of network which will impact to increase cost and addl time delays for the project. | Validate with underground utility survey. EOT or additional time and costs ( Part of LS budget) | 0 | 0 | 0 |  | 0 |  | 0
External | Environmental | Infrastructure | Risk on available space due to existing facilities and structures. | On going Projects (DPWH, Maynilad, Manila Water) along the network alignment which would lead of several interfacing activities and potential clashing/conflict on network alignments which may result to redesign and realignment and further delay of project due to changes on construction stage. Project Name: Rehabilitation of Floodway East Embankment Road Cainta-Taytay, RizaL c/o Rizal Provincial Project. | Delay in project construction, increase costs | 0 | 0 | 0 |  | 0 |  | 0
External | Environmental | Ecological.Consequences | Risk on irreversible environmental impact. | Availability of trees on network location and pump stations which would require tree cutting permit application which may may delay construction schedule. | Delay in project construction, increase costs | 0 | 0 | 0 |  | 0 |  | 0
Internal | Engineering | Cost.Estimate | Unsuitable Approved Business Project or ABP cost risk. | Changes on Project Reqt. and Plans which affect change of CAPEX/OPEX estimates which lead to re-estimation and further budget approval which would delay project. | Re-budgeting and increase costs, 15% budget allocation for VO | 1159160616.7661 | 1783324025.794 | 2674986038.6909 | 1810222327.3825 | 21 | 30 | 40.5 | 31.7646
Internal | Engineering | Design | Constructability issues. | Pipe crossing bridge leading to several design considerations which leading to increase of cost and time. | Delay in project construction, increase costs | 0 | 0 | 0 |  | 0 |  | 0
External | Economic | Infrastructure | Risk on available space due to existing facilities and structures. | Narrow roads/walkways which lead to difficulty of Construction and maintenance may delay project time implementation. Note. Exact locations to be identified and confirmed in TMP report. | Delay in project construction, increase costs | 0 | 0 | 0 |  | 0 |  | 0
External | Social | Social.Mobility | Risk in the change of social status relative to current social location. | Community resistance (e.g loss of business, disruption to traffic) may cause delay of implementation or project delays which may lead to big cost exposure to MWCI. | Delay in project construction, increase costs | 7000000 | 10000000 | 12500000 | 8933900.487 | 21 | 30 | 40.5 | 32.0653
External | Environmental | Geographic.Location | Risk on geograhic location of the project. | STP location at Laguna lake side (both options: Taytay & Angono STP) which may result complication of construction methodology leading to increase in overall project cost. | Exploration of feasibile construction methodolgy, increase costs, | 0 | 0 | 0 |  | 0 |  | 0
External | Environmental | Ecological.Consequences | Risk on impact on climate. | Extreme flooding during construction that may result to work stoppage and limited access which may cause project construction delays and additional cost for standby fees. | Delay in project construction, EOT, increase costs | 1309000 | 1870000 | 2337500 | 1959892.64 | 7 | 10 | 13.5 | 12.4919
Internal | Engineering | Scope | Scope variations risk. | Splitting laterals out of the original scope for detailed design which may result to outdated design and considerations and impact for the main trunk network which may caused addl cost and time for the project. | Longer Feasibilities, detailed design duration, EOT, increase costs | 2310000 | 3300000 | 4125000 | 2564423.5821 | 21 | 30 | 40.5 | 26.4607
External | Environmental | Geographic.Location | Issues on unsuitable project site location. | Land and location for STP is still not available and defined which may delay finalization of the sewerage network design that would impact delays in target timeline and project cost | Longer survey site investigation on network, addl. network length (3km) , longer detailed design duration, time extention | 2178988830.9528 | 2793575424.2984 | 3771326822.8028 | 3495157406.63 | 126 | 180 | 243 | 177.7772
Internal | Engineering | Technology.Adoption | Construction methodology risk. | To ensure all methodology risks for micro tunnelling shall be considered and applied for the construction of main trunk sewer to avoid risk on ground engineering investigations which would impact both cost and time of project requirement. | Increase costs, risk in qualified contractors | 0 | 0 | 0 |  | 0 |  | 0
Internal | Engineering | Design | Issues in Health and Safety in Design. | Lacking of MWCI Standards for screen for PS/LS creates risks on access and safety both in design and operation which leads to addl costs and delay of work due to further clarification if not finalized. | Feasibile screen design is not per MWCI standards | 0 | 0 | 0 |  | 0 |  | 0
External | Environmental | Infrastructure | Risk on available space due to existing facilities and structures. | Poor response of Meralco for the power connection installation for pump ststions which would delay on commissioning works that may caused further delays on project timeline. | Delay on Operation/Construction leading to EOT and inc of cost due to standby | 0 | 0 | 0 |  | 0 |  | 0
External | Environmental | Infrastructure | Risk on un-accounted facilities in conflict with the project. | Poor Stakeholders Response in particular for Telcom and other private companies which delays the analysis and design of network due to no available data as project reference leading to addl time and cost requirement. | Delay on design, EOT, standby cost | 0 | 0 | 0 |  | 0 |  | 0
External | Political | Bureaucracy.Issues | Risk on delays on the issuance of permits. | Slow response and process of LGU Cainta Municipal Hall Office for permitting acquisition due to current Pandemic and/or Change of Administration leading to limited personnel to assist on permitting application and data gathering for design reference.Hence, the work commencement cannot progress on time which may result to delay on project site implementation. | Delay of survey works, EOT for surveyors and Additional cost for team supporting the project | 3304000 | 4720000 | 5900000 | 4263145.6692 | 14 | 20 | 27 | 19.6798
External | Political | Bureaucracy.Issues | Risk on delays on the issuance of permits. | Slow response and process of LGU Antipolo City Hall Office for permitting acquisition due to current Pandemic and/or Change of Administration leading to limited personnel to assist on permitting application and data gathering for design reference. Hence, the work commencement cannot progress on time which may result to delay on project site implementation. | Delay of survey works, EOT for surveyors and Additional cost for team supporting the project | 3304000 | 4720000 | 5900000 | 4197377.8089 | 14 | 20 | 27 | 20.1839
External | Political | Bureaucracy.Issues | Risk on delays on the issuance of permits. | Slow response and process of LGU Taytay Municipal Hall Office for permitting acquisition due to current Pandemic and/or Change of Administration leading to limited personnel to assist on permitting application and data gathering for design reference. Hence, the work commencement cannot progress on time which may result to delay on project site implementation. | Delay of survey works, EOT for surveyors | 3304000 | 4720000 | 5900000 | 4715909.4512 | 14 | 20 | 27 | 18.0567
External | Strategy | Feasibility.Studies.Options | Risk on project with feasibility studies using unfounded assumptions. | Results of Ground Investigation surveys may give very deep or poor ground conditions and liquefaction which may result to expensive ground improvement measures/solutions for STP location which could also impact cost effectiveness for buildability. | Entails higher project costs for ground improvement/mitigation, addl days for bigger foundation | 490000000 | 700000000 | 875000000 | 599274629.2777 | 70 | 100 | 135 | 92.2307
External | Legal | Regulatory.Bodies | Risk on the issue of right of way | Existing Warehouse at Brgy. Santolan, Pasig City adjacent Marikina River will be needed as addl. access to Intake area which has been identified with potential ROW issues which could block the road and could lead to redesign or realignment of the network that could cause addl cost and time delays for the project. | Possible redesign of network alignment | 7000000 | 10000000 | 12500000 | 9439727.1834 | 42 | 60 | 81 | 56.0468
External | Legal | Regulatory.Bodies | Risk on the issue of right of way | Existing illegal settlers at the end of Brgy Santolan Pasig "New Road" has also been identified with potential ROW issues which blocking the road that might lead network re-alignment and redesign of the network that could cause addl cost and time delays for the project. | Possible redesign of network alignment | 7000000 | 10000000 | 12500000 | 11110043.6196 | 42 | 60 | 81 | 61.5409
External | Legal | Regulatory.Bodies | Risk on the issue of right of way | Existing Road Warranty/ Road Moratorium on the Network Alignment which may prevent for further development in the same area which may require redesign and addl time and cost for the propose project. | Possible redesign/rerouting of network alignment, amt budget for design fees | 7000000 | 10000000 | 12500000 | 8719737.0516 | 42 | 60 | 81 | 55.5287
External | Political | Government.Leadership | Risk in the failure of administrative processes. | Change in the administration in Regulator's Offices (MWSS, DENR, LLDA) that could lead double effort in getting data information gathering , coordination and clearance to start construction which may lead for further delay of project site works. | Delay in approvals of MWSS, DENR, LLDA, etc. | 1470000 | 2100000 | 2625000 | 2235657.0002 | 9.8 | 14 | 18.9 | 15.9546
External | Environmental | Ecological.Consequences | Risk on impact on climate. | Extreme flooding during Operations that may result to operation downtime and limited access which may cause project construction delays and additional cost for standby fees. | Delay and operation downtime,increase costs | 70000 | 100000 | 125000 | 96457.8253 | 2.8 | 4 | 5.4 | 4.7463
External | Political | Bureaucracy.Issues | Risk on delays on the issuance of permits. | Slow response and process of LGU Angono Municipal Hall Office for permitting acquisition due to current Pandemic and/or Change of Administration leading to limited personnel to assist on permitting application and data gathering for design reference. Hence, the work commencement cannot progress on time which may result to delay on project site implemenation. | Delay of survey works, EOT for surveyors and Additional cost for team supporting the project | 3304000 | 4720000 | 5900000 | 5359310.1653 | 14 | 20 | 27 | 20.434
Internal | Engineering | Design | Risk on failure to validate data inputs on design. | Inaccurate sewer return factor used in the sewer model design simulation which risks the design capacity of sewerage system leading to over design or under design. | Longer Feasibilities, detailed design duration, EOT, increase costs | 0 | 0 | 0 |  | 0 |  | 0
External | Legal | Regulatory.Bodies | Issues on land acquisitions | Land swap arrangement of Angono LGU for the location of STP site which risks overall project timeline since more thorough investigations is needed to validate the viability and feasibility of the lot in the swamp area leading to higher construction cost and timeline delays. | Longer Feasibilities, detailed design duration, EOT, increase costs | 553000000 | 700000000 | 875000000 | 633925047.9204 | 255.5 | 365 | 492.75 | 367.3588
External | Political | Bureaucracy.Issues | Risk on LGU/NGA approval or no objection of design and studies. | Strict Pasig LGU excavation permit requirements for GI survey works which risks commencement of borehole drilling leading to survey EOT and data evaluation delays. | Longer Feasibilities and detailed design duration, EOT, increase costs | 0 | 0 | 0 |  | 0 | 0 | 0
External | Environmental | Social.Implications | Issues on community open resistance to the project. | Permanent change of traffic routing in Pasig City which risks the output of the traffic simulation modelling leading to reassessments and revalidation. | Longer Feasibilities, detailed design duration, EOT, increase costs | 0 | 0 | 0 |  | 0 |  | 0
Internal | Engineering | Scope | Scope variations risk. | Variation order for additional area or road scope of topographical surveys which risks the survey timeline leading to EOT and delay in finalization of the network alignment designs. | Longer Feasibilities, detailed design duration, EOT, increase costs but already considered on item 23 budget | 0 | 0 | 0 |  | 0 |  | 0
External | Legal | Regulatory.Bodies | Issues on land acquisitions | Negotiation with Sta. Lucia Land Inc. developers to seek support on the network alignment in Greenland Subdivision Cainta which risks the finalization of network alignment leading to meet the developer's demands/request entailing additional cost | Longer Feasibilities, detailed design duration, EOT, increase costs | 0 | 0 | 0 |  | 0 |  | 0
External | Environmental | Cyclical.Weather | Risk on heavy rains. | Inclement weather. Continuous rain hampers the mobility of subcontractors | Longer Feasibilities, detailed design duration, EOT, increase costs | 0 | 0 | 0 |  | 0 |  | 0
External | Environmental | Biohazard.Pandemic | Risk on pandemic. | National government's reimposition of heightened GCQ and ECQ from 06Aug2021 up to 20Aug2021. The ECQ might be extended depending on the situation of Covid19 infections to the populace. Aug 22 to Sept 7, 2021, NCR at MECQ category | Longer Feasibilities, detailed design duration, EOT, increase costs | 0 | 0 | 0 |  | 0 |  | 0
External | Political | Bureaucracy.Issues | Risk on LGU/NGA approval or no objection of design and studies. | Change in LGU/ Barangay requirements in the conduct GPR prior to issuance of approved permit might delay the permitting process that might eventually delay the GI drilling activities. | Longer Feasibilities and detailed design duration, EOT, increase costs | 0 | 0 | 0 |  | 0 |  | 0
External | Political | Bureaucracy.Issues | Risk on delays on the issuance of permits. | Strict Rizal LGU excavation permit requirements for GI survey works which risks commencement of borehole drilling leading to survey EOT and data evaluation delays. | Longer Feasibilities, detailed design duration, EOT, increase costs | 0 | 0 | 0 |  | 0 |  | 0
External | Political | Bureaucracy.Issues | Risk on delays on the issuance of permits. | Temporary closure of DPWH Rizal office from Sep. 2-20, 2021 due to Covid19 pandemic which affects securing excavation permit of the subcontractor. | Longer Feasibilities, detailed design duration, EOT, increase costs | 0 | 0 | 0 |  | 14 | 20 | 27 | 22.0494
Internal | Engineering | Project.Timeline | Risk on failure to validate data inputs on design. | Delay on the post processing report of the engineering surveys such as GPR surveys which impact the commencement of borehole drilling and road & profiles which delays the topographic evaluation of the network design. | Longer Feasibilities, detailed design duration, EOT, increase costs | 0 | 0 | 0 |  | 21 | 30 | 40.5 | 31.6639
[8 empty] | TOTAL RISK COST PHP | 8884692842.7127 |  |  | TOTAL RISK DELAYS DAYS | 1433.8687
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## RTAGlobal (hidden)
1433.8687 | '[20230324 - Project Risk Planning - Template Planning Type-ABC V1.2_.xlsx]MC'!$R$54
8884692842.7127 | '[20230324 - Project Risk Planning - Template Planning Type-ABC V1.2_.xlsx]MC'!$M$54
43082119275279

## Risk Sched Sensitivity (hidden)
| Spider Chart: 'MC'!$R$54 | [17 empty] | Tornado Chart: 'MC'!$R$54
| Input | [8 empty] | Output
Name | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | Downside | Upside | Range
MC'!$R$43 | 308.5672 | 326.8246 | 341.4551 | 354.648 | 367.3235 | 380.1067 | 393.6475 | 408.9671 | 428.5975 | 1374.3086 | 1392.566 | 1407.1965 | 1420.3894 | 1433.0649 | 1445.8481 | 1459.3889 | 1474.7085 | 1494.3389 | 1374.3086 | 1494.3389 | 120.0303
MC'!$R$27 | 152.1701 | 161.1738 | 168.3888 | 174.8949 | 181.1458 | 187.4499 | 194.1275 | 201.6824 | 211.3631 | 1404.0892 | 1413.0929 | 1420.3079 | 1426.814 | 1433.0649 | 1439.3689 | 1446.0466 | 1453.6015 | 1463.2822 | 1404.0892 | 1463.2822 | 59.193
MC'!$R$8 | 84.539 | 89.541 | 93.5493 | 97.1638 | 100.6366 | 104.1388 | 107.8486 | 112.0458 | 117.424 | 1416.9673 | 1421.9693 | 1425.9777 | 1429.5922 | 1433.0649 | 1436.5671 | 1440.2769 | 1444.4741 | 1449.8523 | 1416.9673 | 1449.8523 | 32.885
MC'!$R$35 | 84.539 | 89.541 | 93.5493 | 97.1638 | 100.6366 | 104.1388 | 107.8486 | 112.0458 | 117.424 | 1416.9673 | 1421.9693 | 1425.9777 | 1429.5922 | 1433.0649 | 1436.5671 | 1440.2769 | 1444.4741 | 1449.8523 | 1416.9673 | 1449.8523 | 32.885
MC'!$R$16 | 65.095 | 68.9466 | 72.033 | 74.8162 | 77.4902 | 80.1869 | 83.0434 | 86.2752 | 90.4165 | 1420.6697 | 1424.5213 | 1427.6077 | 1430.3909 | 1433.0649 | 1435.7616 | 1438.6182 | 1441.85 | 1445.9912 | 1420.6697 | 1445.9912 | 25.3215
MC'!$R$36 | 50.7234 | 53.7246 | 56.1296 | 58.2983 | 60.3819 | 62.4833 | 64.7092 | 67.2275 | 70.4544 | 1423.4063 | 1426.4076 | 1428.8126 | 1430.9813 | 1433.0649 | 1435.1662 | 1437.3921 | 1439.9104 | 1443.1373 | 1423.4063 | 1443.1373 | 19.731
MC'!$R$37 | 50.7234 | 53.7246 | 56.1296 | 58.2983 | 60.3819 | 62.4833 | 64.7092 | 67.2275 | 70.4544 | 1423.4063 | 1426.4076 | 1428.8126 | 1430.9813 | 1433.0649 | 1435.1662 | 1437.3921 | 1439.9104 | 1443.1373 | 1423.4063 | 1443.1373 | 19.731
MC'!$R$38 | 50.7234 | 53.7246 | 56.1296 | 58.2983 | 60.3819 | 62.4833 | 64.7092 | 67.2275 | 70.4544 | 1423.4063 | 1426.4076 | 1428.8126 | 1430.9813 | 1433.0649 | 1435.1662 | 1437.3921 | 1439.9104 | 1443.1373 | 1423.4063 | 1443.1373 | 19.731
MC'!$R$9 | 30.434 | 32.2348 | 33.6778 | 34.979 | 36.2292 | 37.49 | 38.8255 | 40.3365 | 42.2726 | 1427.2698 | 1429.0705 | 1430.5135 | 1431.8147 | 1433.0649 | 1434.3257 | 1435.6612 | 1437.1722 | 1439.1084 | 1427.2698 | 1439.1084 | 11.8386
MC'!$R$53 | 25.3617 | 26.8623 | 28.0648 | 29.1491 | 30.191 | 31.2416 | 32.3546 | 33.6137 | 35.2272 | 1428.2356 | 1429.7362 | 1430.9387 | 1432.0231 | 1433.0649 | 1434.1156 | 1435.2285 | 1436.4877 | 1438.1011 | 1428.2356 | 1438.1011 | 9.8655
MC'!$R$6 | 25.3617 | 26.8623 | 28.0648 | 29.1491 | 30.191 | 31.2416 | 32.3546 | 33.6137 | 35.2272 | 1428.2356 | 1429.7362 | 1430.9387 | 1432.0231 | 1433.0649 | 1434.1156 | 1435.2285 | 1436.4877 | 1438.1011 | 1428.2356 | 1438.1011 | 9.8655
MC'!$R$7 | 25.3617 | 26.8623 | 28.0648 | 29.1491 | 30.191 | 31.2416 | 32.3546 | 33.6137 | 35.2272 | 1428.2356 | 1429.7362 | 1430.9387 | 1432.0231 | 1433.0649 | 1434.1156 | 1435.2285 | 1436.4877 | 1438.1011 | 1428.2356 | 1438.1011 | 9.8655
MC'!$R$12 | 25.3617 | 26.8623 | 28.0648 | 29.1491 | 30.191 | 31.2416 | 32.3546 | 33.6137 | 35.2272 | 1428.2356 | 1429.7362 | 1430.9387 | 1432.0231 | 1433.0649 | 1434.1156 | 1435.2285 | 1436.4877 | 1438.1011 | 1428.2356 | 1438.1011 | 9.8655
MC'!$R$20 | 25.3617 | 26.8623 | 28.0648 | 29.1491 | 30.191 | 31.2416 | 32.3546 | 33.6137 | 35.2272 | 1428.2356 | 1429.7362 | 1430.9387 | 1432.0231 | 1433.0649 | 1434.1156 | 1435.2285 | 1436.4877 | 1438.1011 | 1428.2356 | 1438.1011 | 9.8655
MC'!$R$23 | 25.3617 | 26.8623 | 28.0648 | 29.1491 | 30.191 | 31.2416 | 32.3546 | 33.6137 | 35.2272 | 1428.2356 | 1429.7362 | 1430.9387 | 1432.0231 | 1433.0649 | 1434.1156 | 1435.2285 | 1436.4877 | 1438.1011 | 1428.2356 | 1438.1011 | 9.8655
MC'!$R$26 | 25.3617 | 26.8623 | 28.0648 | 29.1491 | 30.191 | 31.2416 | 32.3546 | 33.6137 | 35.2272 | 1428.2356 | 1429.7362 | 1430.9387 | 1432.0231 | 1433.0649 | 1434.1156 | 1435.2285 | 1436.4877 | 1438.1011 | 1428.2356 | 1438.1011 | 9.8655
MC'!$R$4 | 16.9078 | 17.9082 | 18.7099 | 19.4328 | 20.1273 | 20.8278 | 21.5697 | 22.4092 | 23.4848 | 1429.8454 | 1430.8458 | 1431.6475 | 1432.3704 | 1433.0649 | 1433.7654 | 1434.5073 | 1435.3467 | 1436.4224 | 1429.8454 | 1436.4224 | 6.577
MC'!$R$32 | 16.9078 | 17.9082 | 18.7099 | 19.4328 | 20.1273 | 20.8278 | 21.5697 | 22.4092 | 23.4848 | 1429.8454 | 1430.8458 | 1431.6475 | 1432.3704 | 1433.0649 | 1433.7654 | 1434.5073 | 1435.3467 | 1436.4224 | 1429.8454 | 1436.4224 | 6.577
MC'!$R$33 | 16.9078 | 17.9082 | 18.7099 | 19.4328 | 20.1273 | 20.8278 | 21.5697 | 22.4092 | 23.4848 | 1429.8454 | 1430.8458 | 1431.6475 | 1432.3704 | 1433.0649 | 1433.7654 | 1434.5073 | 1435.3467 | 1436.4224 | 1429.8454 | 1436.4224 | 6.577
MC'!$R$34 | 16.9078 | 17.9082 | 18.7099 | 19.4328 | 20.1273 | 20.8278 | 21.5697 | 22.4092 | 23.4848 | 1429.8454 | 1430.8458 | 1431.6475 | 1432.3704 | 1433.0649 | 1433.7654 | 1434.5073 | 1435.3467 | 1436.4224 | 1429.8454 | 1436.4224 | 6.577

## Risk Cost Sensitivity (hidden)
| Spider Chart: TOTAL RISK COST PHP | [17 empty] | Tornado Chart: TOTAL RISK COST PHP
| Input | [8 empty] | Output
Name | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | Downside | Upside | Range
MC'!$M$27 | 2467069614.9358 | 2579156519.9317 | 2671549304.7327 | 2756618215.372 | 2839830886.1451 | 2925183157.1065 | 3017169112.9643 | 3123261770.421 | 3262633877.1819 | 8066345823.6894 | 8178432728.6854 | 8270825513.4863 | 8355894424.1257 | 8439107094.8988 | 8524459365.8602 | 8616445321.7179 | 8722537979.1747 | 8861910085.9355 | 8066345823.6894 | 8861910085.9355 | 795564262.2461
MC'!$M$20 | 1454989168.2598 | 1565234315.621 | 1655207290.9904 | 1737445521.1299 | 1817388377.1958 | 1898907812.2833 | 1986243049.5668 | 2086311762.3315 | 2216666581.7324 | 8076707885.9628 | 8186953033.324 | 8276926008.6933 | 8359164238.8328 | 8439107094.8988 | 8520626529.9863 | 8607961767.2697 | 8708030480.0344 | 8838385299.4353 | 8076707885.9628 | 8838385299.4353 | 761677413.4726
MC'!$M$13 | 616866596.5617 | 651805404.1156 | 681238079.0918 | 708767009.6921 | 736055849.6185 | 764394154.0932 | 795315599.7731 | 831466250.5198 | 879779741.4734 | 8319917841.842 | 8354856649.3959 | 8384289324.3721 | 8411818254.9724 | 8439107094.8988 | 8467445399.3735 | 8498366845.0534 | 8534517495.8001 | 8582830986.7537 | 8319917841.842 | 8582830986.7537 | 262913144.9117
MC'!$M$14 | 502534469.2195 | 532268703.0227 | 556095939.9964 | 577581986.2521 | 598225440.1643 | 619044147.9653 | 641096799.6739 | 666046404.7276 | 698016623.2757 | 8343416123.954 | 8373150357.7572 | 8396977594.7309 | 8418463640.9865 | 8439107094.8988 | 8459925802.6998 | 8481978454.4084 | 8506928059.4621 | 8538898278.0101 | 8343416123.954 | 8538898278.0101 | 195482154.0562
MC'!$M$35 | 595801014.4606 | 627841592.816 | 652787801.1168 | 674798092.567 | 695543845.9726 | 716083233.0452 | 737426332.7203 | 761050934.0542 | 790458640.5777 | 8339364263.3868 | 8371404841.7422 | 8396351050.043 | 8418361341.4932 | 8439107094.8988 | 8459646481.9714 | 8480989581.6465 | 8504614182.9804 | 8534021889.5039 | 8339364263.3868 | 8534021889.5039 | 194657626.1171
MC'!$M$8 | 421622922.7044 | 447592271.7671 | 468653226.3231 | 487814451.2318 | 506366603.3821 | 525213501.3625 | 545327638.7025 | 568276103.8839 | 598005427.2195 | 8354363414.2211 | 8380332763.2838 | 8401393717.8398 | 8420554942.7484 | 8439107094.8988 | 8457953992.8791 | 8478068130.2192 | 8501016595.4005 | 8530745918.7362 | 8354363414.2211 | 8530745918.7362 | 176382504.5151
MC'!$M$43 | 624078476.2923 | 648726208.1107 | 668512864.7265 | 686379221.3877 | 703564901.6731 | 720915677.0592 | 739315794.1777 | 760159752.439 | 786913822.6531 | 8359620669.5181 | 8384268401.3365 | 8404055057.9523 | 8421921414.6134 | 8439107094.8988 | 8456457870.2849 | 8474857987.4035 | 8495701945.6647 | 8522456015.8788 | 8359620669.5181 | 8522456015.8788 | 162835346.3608
MC'!$M$11 | 309270594.2933 | 325560583.8794 | 338995510.7431 | 351370271.2079 | 363479016.8826 | 375902951.1193 | 389296673.0143 | 404749743.3987 | 425059115.2506 | 8384898672.3095 | 8401188661.8956 | 8414623588.7593 | 8426998349.224 | 8439107094.8988 | 8451531029.1355 | 8464924751.0305 | 8480377821.4149 | 8500687193.2668 | 8384898672.3095 | 8500687193.2668 | 115788520.9573
MC'!$M$7 | 51068658.3823 | 53814993.6699 | 55953240.0957 | 57839836.5057 | 59618043.9405 | 61378562.8324 | 63207971.376 | 65232937.2046 | 67753597.7638 | 8430557709.3406 | 8433304044.6282 | 8435442291.054 | 8437328887.464 | 8439107094.8988 | 8440867613.7907 | 8442697022.3343 | 8444721988.1629 | 8447242648.7221 | 8430557709.3406 | 8447242648.7221 | 16684939.3815
MC'!$M$16 | 19661433.4772 | 20718772.5629 | 21541997.4369 | 22268337.0547 | 22952946.9171 | 23630746.6905 | 24335068.9798 | 25114680.8238 | 26085135.1391 | 8435815581.4589 | 8436872920.5446 | 8437696145.4185 | 8438422485.0364 | 8439107094.8988 | 8439784894.6722 | 8440489216.9615 | 8441268828.8055 | 8442239283.1208 | 8435815581.4589 | 8442239283.1208 | 6423701.6619
MC'!$M$12 | 8511443.0637 | 8969165.6117 | 9325540.016 | 9639972.751 | 9936340.6568 | 10229760.4721 | 10534661.896 | 10872156.2008 | 11292266.294 | 8437682197.3058 | 8438139919.8537 | 8438496294.258 | 8438810726.993 | 8439107094.8988 | 8439400514.7141 | 8439705416.138 | 8440042910.4428 | 8440463020.536 | 8437682197.3058 | 8440463020.536 | 2780823.2302
MC'!$M$23 | 8511443.0637 | 8969165.6117 | 9325540.016 | 9639972.751 | 9936340.6568 | 10229760.4721 | 10534661.896 | 10872156.2008 | 11292266.294 | 8437682197.3058 | 8438139919.8537 | 8438496294.258 | 8438810726.993 | 8439107094.8988 | 8439400514.7141 | 8439705416.138 | 8440042910.4428 | 8440463020.536 | 8437682197.3058 | 8440463020.536 | 2780823.2302
MC'!$M$36 | 8511443.0637 | 8969165.6117 | 9325540.016 | 9639972.751 | 9936340.6568 | 10229760.4721 | 10534661.896 | 10872156.2008 | 11292266.294 | 8437682197.3058 | 8438139919.8537 | 8438496294.258 | 8438810726.993 | 8439107094.8988 | 8439400514.7141 | 8439705416.138 | 8440042910.4428 | 8440463020.536 | 8437682197.3058 | 8440463020.536 | 2780823.2302
MC'!$M$37 | 8511443.0637 | 8969165.6117 | 9325540.016 | 9639972.751 | 9936340.6568 | 10229760.4721 | 10534661.896 | 10872156.2008 | 11292266.294 | 8437682197.3058 | 8438139919.8537 | 8438496294.258 | 8438810726.993 | 8439107094.8988 | 8439400514.7141 | 8439705416.138 | 8440042910.4428 | 8440463020.536 | 8437682197.3058 | 8440463020.536 | 2780823.2302
MC'!$M$38 | 8511443.0637 | 8969165.6117 | 9325540.016 | 9639972.751 | 9936340.6568 | 10229760.4721 | 10534661.896 | 10872156.2008 | 11292266.294 | 8437682197.3058 | 8438139919.8537 | 8438496294.258 | 8438810726.993 | 8439107094.8988 | 8439400514.7141 | 8439705416.138 | 8440042910.4428 | 8440463020.536 | 8437682197.3058 | 8440463020.536 | 2780823.2302
MC'!$M$9 | 7231322.0269 | 7620203.1037 | 7922978.7976 | 8190120.8492 | 8441915.022 | 8691204.4971 | 8950248.7468 | 9236983.9082 | 9593909.4434 | 8437896501.9038 | 8438285382.9805 | 8438588158.6744 | 8438855300.726 | 8439107094.8988 | 8439356384.3739 | 8439615428.6237 | 8439902163.785 | 8440259089.3202 | 8437896501.9038 | 8440259089.3202 | 2362587.4164
MC'!$M$6 | 4289767.3041 | 4520459.4683 | 4700072.168 | 4858546.2665 | 5007915.691 | 5155799.2779 | 5309469.5956 | 5479566.7252 | 5691302.2122 | 8438388946.5119 | 8438619638.6761 | 8438799251.3758 | 8438957725.4743 | 8439107094.8988 | 8439254978.4857 | 8439408648.8034 | 8439578745.933 | 8439790481.4199 | 8438388946.5119 | 8439790481.4199 | 1401534.908
MC'!$M$41 | 4017401.1261 | 4233446.1687 | 4401654.8875 | 4550067.1385 | 4689952.79 | 4828446.9428 | 4972360.4149 | 5131657.7268 | 5329949.6908 | 8438434543.2349 | 8438650588.2775 | 8438818796.9963 | 8438967209.2473 | 8439107094.8988 | 8439245589.0516 | 8439389502.5237 | 8439548799.8356 | 8439747091.7996 | 8438434543.2349 | 8439747091.7996 | 1312548.5647
MC'!$M$32 | 4017401.1261 | 4233446.1687 | 4401654.8875 | 4550067.1385 | 4689952.79 | 4828446.9428 | 4972360.4149 | 5131657.7268 | 5329949.6908 | 8438434543.2349 | 8438650588.2775 | 8438818796.9963 | 8438967209.2473 | 8439107094.8988 | 8439245589.0516 | 8439389502.5237 | 8439548799.8356 | 8439747091.7996 | 8438434543.2349 | 8439747091.7996 | 1312548.5647
MC'!$M$33 | 4017401.1261 | 4233446.1687 | 4401654.8875 | 4550067.1385 | 4689952.79 | 4828446.9428 | 4972360.4149 | 5131657.7268 | 5329949.6908 | 8438434543.2349 | 8438650588.2775 | 8438818796.9963 | 8438967209.2473 | 8439107094.8988 | 8439245589.0516 | 8439389502.5237 | 8439548799.8356 | 8439747091.7996 | 8438434543.2349 | 8439747091.7996 | 1312548.5647

## ModelRiskDSN (hidden)
DSN Files Count: | 0